| IN THE SUPREME COURT OF VICTORIA |  | Not Restricted |
| --- | --- | --- |

AT MELBOURNE

COMMERCIAL AND EQUITY DIVISION

BUILDING CASES LIST

No. 6897 of 2001

| KANE CONSTRUCTIONS PTY LTD (ACN 007 354 396) | Plaintiff |
| --- | --- |
| v |  |
| COLE SOPOV AND ORS | Defendants |

---

| JUDGE: | WARREN, C.J. |  |
| --- | --- | --- |
| WHERE HELD: | Melbourne |  |
| DATE OF HEARING: | 21-22, 25, 27-29 August 2003; 2- 3, 9-12, 16-19, 23-26, 30 September 2003; 1-2, 7-10, 14-17, 20-21, 29-31 October 2003 |  |
| DATE OF JUDGMENT: | 30 June 2005 |  |
| CASE MAY BE CITED AS: | Kane Constructions v Sopov |  |
| MEDIUM NEUTRAL CITATION: | [2005] VSC 237 | 1st revision 26 July 2005 |

---

CONTRACT — Building contract — Construction — Progress certificates — Claims for payment — Evidence and information in support of progress claims — Whether material supporting claims condition precedent to issue of a payment certificate — Validity of late progress claims — Validity of late progress certificates — Assessment procedures — Estoppel — Delay and extension of time claims — Liquidated damages — Right of principal to deduct liquidated damages from progress payments — Role of the superintendent — Undue influence — Suspension of works under the contract — Right of principal to access retention moneys under the contract — Substantial breach — Repudiation — Termination — Alternative rights and remedies available to aggrieved party as a result of repudiation — Contractual damages — Quantum meruit — Whether contractual provision may exclude claim for quantum meruit following termination — Clause 44.10 of AS 2124-1992 — Whether ss.16 and 33 of the Domestic Building Contracts Act 1995 (Vic) apply — Whether s.51A of the Trade Practices Act 1974 (Cth) applies

RESTITUTION — Contract — Unjust enrichment — Claim for variations

DEFENCE AND COUNTERCLAIM — Costs to complete — Claim for defective work — Deduction variations — Whether plaintiff breached contract by serving notice to show cause and suspending works — Costs of completion certificate issued by the superintendent — Extent of completion at the time the plaintiff left building site

---

| APPEARANCES: | Counsel | Solicitors |
| --- | --- | --- |
| For the Plaintiff | Mr G.J. Digby Q.C. with Mr M.J. Stirling | Deacons |
| For the Defendants | Mr E.N. Magee Q.C. with Mr K.C. Oliver | Pilley & Associates |

TABLE OF CONTENTS

INTRODUCTION/OVERVIEW	2

PLEADINGS	3

TERMS OF CONTRACT (AND DOCUMENTS INCLUDED)	3

SUMMARIES OF WITNESSES’ EVIDENCE	3

PLAINTIFF’S EVIDENCE	3

(1) TIVENDALE	3

(2) FORSTER	3

(3) LUCAS	3

(4) ISAACSON	3

(5) SKARAJEW	3

(6) WILLIAMSON	3

(7) OMOND	3

(8) SWARBRICK	3

(9) QI SHAO	3

(10) DORDEVIC	3

(11) THOMAS	3

(12) LYNAS	3

(13) LEE	3

(14) GILFILLAN	3

DEFENDANTS’ EVIDENCE	3

(1) SOPOV	3

(2) JEFFERY	3

(3) BROWN	3

(4) LONG	3

(5) PANDOV	3

(6) DEGENHARDT	3

(7) GOODWIN	3

(8) PERMEWAN	3

SUBMISSIONS ON EXPERT EVIDENCE: LYNAS AND DEGENHARDT	3

Role of THE Superintendent	3

SET-OUT: STRUCTURAL STEEL AND EOT 4	3

EOTs 1 - 18	3

TERMINATION	3

DEFECTS	3

COSTS TO COMPLETE	3

QUANTUM MERUIT	3

OTHER RELIEF	3

MISLEADING AND DECEPTIVE CONDUCT	3

DOMESTIC BUILDING CONTRACTS ACT	3

SCOTT SCHEDULE	3

SUMMARY OF CONCLUSIONS	3

HER HONOUR:

INTRODUCTION/OVERVIEW

# The dispute arises from a building contract between the plaintiff as builder, and the defendants, as owners, in relation to a disused, former industrial building at 158-172 Oxford Street, Collingwood in inner Melbourne. The works under the building contract concern the renovation and extension of a disused boilerhouse that was originally part of the Foy & Gibson empire, the founders of which were famous outfitters and haberdashery manufacturers and merchants in Melbourne during the 19th and 20th centuries. The works involved the internal construction and installation within an existing building of a gallery, office space, restaurant space, basement car park and entrance areas. They included, also, the construction of additional floor levels on the existing roof of the building by way of erection of a steel framework to provide for 14 new residential units including balconies. The design was described for marketing purposes as “industrial boheme” and the project was known as the “Boilerhouse”.

# The plaintiff and the defendants executed a written contract on 20 August 1999. The agreement followed a tender process when the builder was invited, along with other selected builders, to submit a tender for the building works. The builder was advised by the owners, by letter dated 20 May 1999, that its tender was successful. On 31 May 1999, the builder was given possession of the site and commenced works, although the contractual terms at that time were not finalised. In the following 11-12 week period, up until 20 August 1999, the builder and the owners engaged in negotiations upon the terms of the contract.

# The works were to be completed in 130 working days. However, a series of delays occurred such that, a year later, the works were incomplete. The builder complained of a long list of matters: insufficient detail in plans and drawings necessitating delays in shop drawings and works, the lack of a suitably qualified superintendent, the refusal or insufficient allowance of extensions of time by the superintendent, the failure to issue certain progress certificates and the failure to allow certain variations under the contract. These complaints culminated when the builder served a progress claim No. 14 on the owners on 23 August 2000 for the sum of $340,562. The defendants responded to the notice by deducting from the amount claimed liquidated damages and goods and services tax (“GST”), leaving a balance of $132,618.20, which amount the owners paid on 28 August 2000. The builder alleged that the owners breached the contract when progress certificate No. 14 was not paid, in full and on time, and that the liquidated damages were wrongfully deducted from the amount certified. As a consequence, on 8 September 2000, the builder served a show cause notice on the owners as to why the builder should not exercise its contractual rights under cl.44.9 of the contract. The defendants responded on 11 September 2000 and purported to show cause which the plaintiff rejected. On 14 September 2000, the superintendent certified progress certificate No. 15 in the sum of $220,800.

# On 18 September 2000, the plaintiff suspended the works. The defendants responded with their own show cause notice asserting that the builder improperly suspended the work and claiming undue delays in the work. On 2 October 2000, the owners purported to serve a notice under cl.44.4 of the contract to call up the securities, namely the bank guarantees. The builder asserted that the owners were not entitled to do so and treated the action as repudiatory of the contract. On 6 October 2000, the builder accepted the alleged repudiation and terminated the agreement. From about 29 September 2000 and up until about 2 October 2000, without warning to the owners, the builder removed its plant and equipment and vacated the site.

# Thereafter, the owners assumed control of the site and set about completion, largely through the engagement of the sub-contractors previously retained by the builder. The builder alleged that at the time of termination the works were completed to the level of 90 per cent. Conversely, the owners alleged that the works were completed to the level of 70 per cent. The owners also alleged that there were extensive rectification works they had to perform to the builder’s works.

# Arising from these broadly described circumstances, the builder made a series of alternative claims in the proceeding. In summary, they were based on a quantum meruit, restitution for unjust enrichment, damages for misleading and deceptive conduct in breach of s.52 of the Trade Practices Act 1974 or s.11 of the Fair Trading Act 1999, a claim under s.3 3 of the Domestic Building Contracts Act 1995, and a claim of undue influence by the owners over the superintendent, Mr Jeffery. The builder also claimed variously for amounts under the contract or on account. The quantum of the amounts claimed under the various causes of action was $2,452,253.01, consisting of the works performed and a proportionate share in the value of the renovated building; alternatively, $1,034,728.64 said to be outstanding under progress certificates 14 and 15, if liquidated damages were not deducted or $440,800.00 if such damages were deducted; further, in the alternative, $968,790.95 being for works performed in the nature of variations and the sum of $763,908.00 being for extra costs incurred by certain delays for which the builder held the owners responsible. The builder also sought consequential relief, including declaratory orders.

# Essentially, the owners denied and disputed the builder’s claims. The owners invoked various provisions of the Domestic Building Contracts Act as a foundation of their disputation of the builder’s claims. The owners rejected progress certificates 14 and 15 as invalid pursuant to certain terms of the agreement. They also relied on certain acts as constituting waiver, estoppel and acquiescence by the builder with respect to progress certificates 14 and 15. In addition, the owners counterclaimed against the builder for the costs of completing the works totalling $1,181,548 and for rectification of defective works performed by the builder totalling $	325,529.44. The owners also counterclaimed for the deduction of a number of variation amounts and also an allowance with respect to GST obligations.

PLEADINGS

# In its statement of claim, the plaintiff relied upon the contract between it and the defendants, dated 20 August 1999, whereby there was agreement to construct the works for the sum of $3,474,000.00. The agreement was alleged to be in writing and constituted by the document AS 2124-1992. In particular, the plaintiff relied upon cll.3.1, 5, 8.1, 23, 35.5, 36, 40, 42.1 and 42.9 of the general conditions of the agreement and the implied terms that the defendants were precluded from issuing a cl.44.2 notice under the agreement or having recourse to the security while in substantial breach of the agreement.

# The defendants admitted the agreement, save to allege that it was varied by and subject to the provisions of the Domestic Building Contracts Act and, in particular, ss.15, 16(1) and 33 of that Act. The plaintiff relied upon the letter of 1 August 2000, submitting progress claim number 14 and alleged that the superintendent failed to issue a payment certificate within 14 days after receiving that claim. The plaintiff then relied upon a facsimile, dated 23 August 2000, whereby the superintendent issued certificate number 14 but reduced the amount certified to the sum of $340,562.00. The plaintiff further relied upon the fact that, under cover of letter dated 28 August 2000, the defendants made payment in respect of progress claim 14 in the sum of $132,618.00. As a consequence, the plaintiff alleged that the defendants breached the agreement by failing, pursuant to cl.42.1 of the agreement, to pay to the plaintiff the amount of progress claim 14; alternatively, by failing, pursuant to cl.42.1 of the agreement, to pay the amount certified by certificate number 14 within 14 days; and, in any event, deducting from the amount paid to the plaintiff, in respect of progress claim number 14, the amount of $220,000, purportedly in the nature of liquidated damages.

# The defendants denied the breach. The defendants further denied that there was an obligation to pay on payment certificate number 14 as issued by the plaintiff or, alternatively, as certified by the superintendent. The defendants alleged that the agreement was varied by the arrangements and conduct under the agreement between the parties, in particular, between the superintendent from time to time and Le Hy Ta on behalf of the plaintiff as its contract administrator. The defendants further alleged in their defence that, by virtue of the conduct of the plaintiff with respect to progress claim number 14 being issued in breach of the agreement, that this amounted to a waiver by the plaintiff of the requirements of cl.42.1 of the agreement, and which waiver had been accepted. The defendants also alleged that an estoppel arose by virtue of the conduct of the plaintiff and the defendants, and also by virtue of s.33 of Domestic Building Contracts Act such that the plaintiff was estopped from alleging non-compliance with respect to payment certificate number 14. The defendants further alleged acquiescence on the part of the plaintiff by its conduct.

# In addition to denying breach of the agreement as alleged by the plaintiff, the defendants alleged that if they were obliged to pay the amount of either $340,562.00 in respect of progress claim number 14, or obliged to pay the amount of $1,216,546.64 as originally claimed by the plaintiff in respect of progress claim number 14, then such amounts had been superseded and the obligation of the defendants thereto avoided by virtue of payment certificate number 15.

# The plaintiff further alleged that the defendants, by their agent, the superintendent, failed to grant the plaintiff extensions of time under the agreement to which it was entitled. The defendants claimed liquidated damages arising from and relating to the extensions of time in the sum of $913,000.00. The defendants alleged that the superintendent granted the plaintiff extensions of time totalling 11 days and six hours and otherwise rejected all other claims for extensions of time. The defendants disputed three days of the extensions of time granted by the superintendent and otherwise conceded that the plaintiff was entitled to an extension of time in total of only six days and three hours. The extension of time entitlement conceded by the defendants was contained in a schedule to their defence. The defendants relied upon the provision in the agreement that the works were to be brought to practical completion in consequence of the adjusted date for practical completion of 21 December 1999 and not the date of practical completion as events transpired, namely, 31 March 2002. In consequence, the defendants claimed they were entitled to liquidated damages in the amounts sought consisting of liquidated damages at the rate of $1,100 per day from 22 December 1999 until 31 March 2002, that is, a total of 830 days at $1,100 per day, thereby giving rise to a total sum of $913,000.00. The defendants alleged that the plaintiff wrongfully, and in breach of the agreement as varied by the Domestic Building Contracts Act, claimed and was paid sums over and above amounts to which it was entitled. The defendants alleged that they had overpaid the plaintiff and counterclaimed for the amounts of the over payments.

# The plaintiff further claimed that the defendants wrongfully served a show cause response dated 11 September 2000 in response to the plaintiff’s show cause notice. The plaintiff alleged that the defendants, by letter 11 September 2000, failed to show reasonable cause because they failed to demonstrate any basis on which the defendants were entitled to deduct liquidated damages from progress claim number 14; they failed to demonstrate any basis on which the defendants were not obliged to pay progress claim number 14; and the letter of 11 September 2000 was not a valid and substantial response to the plaintiff, pursuant to cl.44.9 of the agreement. The plaintiff pleaded that, as a consequence, they were entitled by their notice dated 18 September 2000 to suspend the whole of the work under the agreement.

# Subsequently, as the plaintiff pleaded its claim, the defendants delivered a show cause notice by a document dated 21 September 2000. The plaintiff pleaded that the defendants’ show cause notice was invalid and of no effect because the defendants were in substantial breach of the agreement at the time, and further, that the defendants’ show cause notice was contrary to the implied term of preclusion from resort to cl.44.2 or the security under the agreement while in substantial breach of the agreement. The plaintiff further relied upon the fact of the suspension of the work by it at the time of the service of the defendants’ show cause notice. It further alleged that it was not open to the defendants to allege failure to proceed with due expedition and without delay, as was alleged in the defendants’ show cause notice, when the plaintiff had made and was entitled to extensions of time to the date for practical completion which had been wrongfully refused or not responded to by the superintendent.

# As a consequence, the plaintiff alleged that the defendants’ conduct, by the service on 2 October 2000 of the purported notice under cl.44.4 of the contract taking the work out of the hands of the contractor, constituted repudiation of the agreement. The plaintiff also alleged that, in further breach of the agreement, the defendants had recourse to the security provided by the plaintiff under the agreement and that the plaintiff was thereby entitled to accept the defendants’ repudiation and thereby terminate the agreement as it did through its solicitor’s letter dated 6 October 2000.

# The defendants admitted service of the two show cause notices but denied that its show cause notice was invalid. It further alleged that the plaintiff’s show cause notice was invalid because it failed to state the date by which the defendants were to show cause and wrongfully alleged that the defendants were required to pay an amount of $1,216,546.64; did not raise any allegation against the defendants concerning the deduction of liquidated damages; was issued after the plaintiff agreed to and accepted the amount of payment certificate number 14 as certified by the superintendent, such agreement arising from the plaintiff issuing a tax invoice on 24 August 2000 inclusive of GST in the sum of $374,618.20; the plaintiff did not submit a tax invoice to the defendants for the sum of $1,216,546.64 as required by the GST legislation; and, finally, the notice to show cause was based on claims made in breach of the agreement as varied by the Domestic Building Contracts Act.

# The defendants further alleged that they, in any event, showed cause pursuant to the terms of the agreement, by their letters to the plaintiff dated 11 September 2000 and 15 September 2000. The defendants relied, further, upon purported admissions by the plaintiff that the sum due to be paid under payment claim number 14 was the sum of $347,618.20 by virtue of the issuing of a tax invoice inclusive of GST on 24 August 2000. The defendants further alleged that they were not required to show cause, in any event, under the show cause notice, as to their entitlement to the deduction of liquidated damages. Further, the defendants alleged that the plaintiff wrongfully purported to suspend the whole of the work under the agreement. The defendants also alleged that the plaintiff, wrongfully, between about 29 September 2000 and 2 October 2000, removed from the works certain site sheds, materials, construction plant and equipment, and temporary works including unfixed materials. The defendants alleged that the removal of the equipment and other items from the site of the works constituted a substantial breach of the agreement.

# The defendants also alleged that they were entitled to take the work to be completed out of the hands of the plaintiff and denied any wrongful conduct on their part. The defendants alleged that the plaintiff breached the agreement by removing from the site materials and other plant and equipment of which the defendants were the owners. The defendants alleged that, in the circumstances, the plaintiff had wrongfully failed and refused to deliver up such plant and equipment to the defendants and thereby converted such items to their own use.

# The defendants also alleged, under cl.44.6 of the agreement, to the effect that the works were to be completed by a specified date but in fact were not completed until 31 March 2002. The defendants relied upon a certificate dated 30 August 2002, issued pursuant to cl.44.6 of the agreement, whereby the superintendent certified that the cost incurred by the defendants for the completion of works was $1,181,548.00. The defendants alleged, therefore, that there was a debt due to them from the plaintiff in the sum of $1,401,954.00. The amount was calculated as follows:

| # Contract Sum | # $3,474,00.00 |
| --- | --- |
| # Less liquidated damages | # $ 913,000.00 |
| # Amount the defendants claimed would have been paid to the plaintiff if the work had been completed by the plaintiff | # $2,561,00.00 |
| # Less the amount actually paid by the defendants | # $2,781,406.00 |
| # Less cost of completion of the works to the defendants | # $1,181,548.00 |
| # Total amount of debt alleged by the defendants against the plaintiff under clause 44.6 of the agreement | # $1,401.954.00 |

# The defendants further relied upon the issuing by the superintendent of the final certificate, pursuant to cll.42.1 and 42.8 of the agreement, on 28 April 2003, in which the superintendent certified that the amount due by the plaintiff to the defendants was $1,515,199.00. The defendants alleged that the plaintiff had failed to pay the amount of the final payment under the agreement and was thereby indebted to the defendants in the amount claimed. The defendants acknowledged that they received a facsimile dated 5 October 2000 from plaintiff’s solicitor sent to the defendants’ solicitor, informing the plaintiff that the defendants’ conduct was repudiatory. Nevertheless, the defendants denied that their conduct was, in the events which occurred, repudiatory. The defendants alleged that they were entitled to have recourse to the agreement and admitted such recourse.

# The defendants further alleged that if they in fact repudiated the agreement, then such agreement was affirmed by the plaintiff. Affirmation of the agreement by the plaintiff was said by the defendants to be constituted by the provision of details with respect to progress claim number 14, as provided by the plaintiff to the superintendent on request; the issuing of a tax invoice on 24 August 2000 by the plaintiff; the issuing of progress claim number 15 on about 1 September 2000; the issuing of a notice under cl.44.7 of the agreement by the plaintiff on about 8 September 2000; the purported suspension of the works by the plaintiff in accordance with cl.44.9 of the agreement by notice dated 18 September 2000; the response by the plaintiff to the defendants’ show cause notice thereby affirming the agreement; and the issue by the plaintiff of progress claim number 16 on about 28 September 2000.

# The plaintiff relied, also, upon a claim based on quantum meruit. The claim was alleged to arise by reason of the termination of the agreement, or its discharge, and the entitlement of the plaintiff to be paid for the work it performed. The defendants denied any entitlement to a quantum meruit on the part of the plaintiff. They alleged that there was no entitlement under the Domestic Building Contracts Act to make such a claim and that it was invalid. The plaintiff further claimed restitution against the defendants. The restitution claim was based upon the plaintiff allegedly suffering a detriment in that it expended labour, materials and money in carrying out works at the instruction of the defendants and the superintendent and that thereby the defendants had been unjustly enriched by receiving the benefit of such works without paying the plaintiff for them. As a consequence, the plaintiff alleged it would be unconscientious for the defendants to receive the benefit of the works. Consequently, the plaintiff claimed that the defendants were obliged to pay it the sum of $2,452,253.01 being the fair and reasonable price for the work; alternatively, in relation to the items of extra work performed by it, the sum of $440,800.00.

# The defendants denied any unconscionability and denied the claim based on restitution. It further alleged that the basis upon which the plaintiff sought restitution was prohibited by the Domestic Building Contracts Act. The plaintiff also alleged that the defendants breached the provisions of the Fair Trading Act and the Trade Practices Act by engaging in misleading and deceptive conduct. The conduct was said to be constituted by representations made by the defendants to the plaintiff that they would jointly and severally pay the plaintiff for the work performed by it, pursuant to the agreement and in accordance with the terms of the agreement relating to payment and the measure of value of work. The plaintiff relied upon the representations said to be constituted by the agreement, letters to the plaintiff, and oral statements by the superintendent and the defendants about the payment for extra work. The plaintiff alleged that it was induced by, and relied upon, the representations of the defendants, and that it performed the works pursuant to the agreement and upon the instruction of the defendants in the expectation that it would be paid for such works in accordance with the terms of the agreement. The plaintiff further alleged that the first and second defendants, namely, Sopov and Walker, aided, abetted, counselled or procured; alternatively, induced; or further and alternatively, were knowingly concerned in, or a party to, the contraventions under the provisions of the Trades Practices Act. In consequence, the plaintiff claimed damages for misleading and deceptive conduct against the defendants. The defendants denied the allegations of deceptive and misleading conduct.

# The plaintiff further claimed that it was entitled to be paid upon a quantum meruit for the amount of works and variations, pursuant to the agreement and cll.40.1, 40.3 and 40.5, in the amount of $968,790.95, being on account of having performed the works and variations. It also claimed, pursuant to cl.36 of the agreement, an amount of $763,908.00 in the nature of delay costs. It also claimed, pursuant to cl.35.5 of the agreement, an extension of time to the date for practical completion of 180 days. The plaintiff claimed to be entitled to the amount of the works and variations. Alternatively, the plaintiff alleged that, in breach of cll.23(a), (b) and (c) of the agreement, the defendants had failed to fairly and reasonably determine and certify a reasonable value for the extra work performed by it. In consequence, the plaintiff claimed loss and damage in the sum of $968,790.95. It also alleged that, in the course of performing the works, the plaintiff incurred delay on account of latent conditions, industrial action, directions by the superintendent and inclement weather. As a consequence, the plaintiff claimed an entitlement to a period totalling 180 days in respect of these delays, thereby constituting extensions of time. The particulars of the request for extensions of time were appended to the plaintiff’s statement of claim. In consequence, the plaintiff claimed to be entitled to the sum of extra costs in the amount of $763,908.00. The plaintiff further alleged that the defendants had failed to fairly and reasonably determine and certify the time extension to which the plaintiff was entitled and was thereby entitled to the amount claimed.

# Further and alternatively, the plaintiff claimed that it was entitled to be paid a sum pursuant to s.53 of the Domestic Building Contracts Act. Alternatively, the plaintiff claimed that, if it was affected by the operation of ss.16 and 33 of that Act, it was entitled to be paid the fair and reasonable price for the performance of the works which the defendants maintained it was not so entitled to be paid for by reason of the said ss.16 and 33 of the Act. Accordingly, the plaintiff sought a variation of the terms of the contract by way of the insertion of the prescribed warning under s.33 of the Act, or alternatively, an order of the court dispensing with the obligation of the plaintiff to comply with the requirements of s.33 of the Domestic Building Contracts Act. The plaintiff further alleged that there was a mutual mistake and thereby the agreement should be rectified to insert the requisite warning under s.33 of the Act. It relied upon correspondence between the parties in support of the allegation of mutual mistake.

# The defendants denied the claims of the plaintiff with respect to variations, extensions of time and delay costs. If the plaintiff was entitled to extensions of time, the plaintiff applied for such extensions amounting only to 169 days and seven hours and failed to apply for extensions of time for a further 10 days and one hour. In the circumstances, the defendants alleged that the plaintiff was barred, by reason of cl.35.5 of the agreement, from claiming the further 10 days and one hour extension of time sought. The plaintiff also alleged that the defendants unduly influenced the superintendent in about January 2000 and thereafter, in relation to decisions and certification which the superintendent was required to make about the plaintiff’s claims for variations and extensions of time under the agreement. The plaintiff alleged that the superintendent, Jeffery, was unduly influenced by Degenhardt as to the determination of the extensions of time. The plaintiff claimed that it suffered loss and damage in the sum of the delay costs which the superintendent should have certified in respect of the extension of time claims 1-17 and as a result of liquidated damages claimed and deducted by the defendants. The defendants denied the allegations.

# The defendants claimed entitlement to a set-off of the amount of their counterclaim in extinction of the plaintiff’s claims. They further claimed, by counterclaim, liquidated damages arising from the failure of the plaintiff to bring the works to practical completion by the extended date for practical completion of 21 December 1999. The defendants further claimed loss and damage arising from the failure of the plaintiff to bring the works to practical completion by the extended date.

# The defendants also made claims by counterclaim for alleged defective work. They alleged that there were terms of the agreement whereby the plaintiff warranted that works would be carried out in a proper and workmanlike manner and in accordance with the plans and specifications set out in the agreement; and that all materials to be supplied by the plaintiff would be good and suitable for the purposes for which they were to be used. That is, the materials would be new; the works would be carried out in accordance with, and would apply with, all laws and legal requirements, including the Building Act 1993 and the regulations under that Act; the works would be carried out with reasonable care and skill; the works and any material used would be reasonably fit for that purpose or of such a nature or quality that might reasonably be expected to achieve that result; and any provisional sum included by the plaintiff in the agreement had been calculated with reasonable care and skill.

# These allegations were described by the defendants as the “warranties”. The warranties were alleged to be included in the annexure part B of the agreement. The defendants also relied upon ss.8 and 20 of the Domestic Building Contracts Act. The defendants alleged that the plaintiff breached the agreement by breaching the various warranties. By reason of the alleged breaches, the defendants claimed loss and damage. The defendants also claimed deduction variations, thereby reducing the contract price by the amount of $1,024,077.00.

# The plaintiff sought consequential declaratory relief and damages including, in the alternative, damages pursuant to statute. It also sought rectification to effect compliance with s.33(2) of the Domestic Building Contracts Act and, further, pursuant to s.53 of that Act, provision for a fair price for the work including the extra work.

# In addition to the denials contained in their pleading, the defendants claimed loss and damage arising from alleged breaches of the agreement. The loss and damage claim was in the nature of loss of interest on the liquidated damages claimed, loss of income and opportunity, loss of interest on income and opportunity, loss of interest on the decreased value of the works and loss of interest on payment of GST. The defendants also claimed that the variations claimed by the plaintiff were based on a provision of the agreement as varied by the Domestic Building Contracts Act and were invalid and/or of no effect.

# The defendants also alleged that there was a consequential liability to pay GST. As a consequence, the defendants claimed an amount of 10 per cent of any judgment sum in respect of GST liability. They also alleged that they had overpaid sums due under the agreement. In consequence of the denials and the matters alleged, the defendants claimed declaratory relief, damages, liquidated damages, damages for conversion, interest, indemnity, and orders that the plaintiff deliver up to the defendants specified items. The defendants further sought a refund from the plaintiff of the sum of $102,241.00 and other relief in the nature of damages. They also claimed interest.

# By way of reply and defence to the counterclaim, the plaintiff denied the allegations against it made by the defendants and the defendants’ claims. In particular, the plaintiff made the following allegations:

(1)	That from the date of execution of the agreement until early October 2000, the defendants represented, promised or conducted themselves in such a way that the defendants would meet their obligations under the agreement;

(2)	It would be unconscientious and, thereby, the defendants are estopped from resiling from the representations and promises made as to compliance by them with the agreement by way of reliance upon the effect of ss.15, 16(1) and 33 of the Domestic Building Contracts Act;

(3)	If the defendants are entitled to relief under ss.15, 16(1) and 33 of the Domestic Building Contracts Act then the plaintiff is entitled to an order pursuant to s.87 of the Trade Practices Act or s.41 of the Fair Trading Act to vary the terms of the agreement so that it complies with the provisions of the Domestic Building Contracts Act and ss. 15, 16(1) and 33 of that Act;

(4)	Relief under s.53(1), (2) (c) and (e) of the Domestic Building Contracts Act;

(5)	Pursuant to s.15(2) of the Domestic Building Contracts Act, the provisions of the Act do not apply to the agreement;

(6)	Relief in light of exceptional circumstances, significant or exceptional hardship by operation of ss.38 (6)(a) and (b) of the Domestic Building Contracts Act, thereby entitling the plaintiff to recover the price of the variations;

(7)	The plaintiff submitted progress claim number 14 in the same form as progress claims 1 to 13 in reliance upon information provided by the superintendent;

(8)	In consequence thereof, the defendants are estopped from relying upon the plaintiff’s alleged omission to include supporting material in respect of progress claim number 14;

(9)	That the final certificate issued by the superintendent was invalid and ineffectual because the superintendent was functus officio and the certificate did not comply with the agreement;

(10)	The agreement was in the form of a lump sum contract whereby the defendants were not entitled to adjust the contract sum by reason of an increase or decrease in the actual cost;

(11)	The superintendent represented that the variations were authorised;

(12)	As a consequence, the defendants are estopped from denying the variations claimed by the plaintiff;

(13)	Further, the defendants are estopped from recovering from the plaintiff the sum of any costs saving to the plaintiff which may have arisen by reason of the superintendent requiring or requesting or authorising the variations.

# In summary, the plaintiff denied the claims of the defendants.

TERMS OF CONTRACT (AND DOCUMENTS INCLUDED)

# The agreement between the parties was primarily constituted by the written contract signed between the parties dated 20 August 1999 and executed by the plaintiff and the first and second defendants and Stacks Properties Pty Ltd, jointly and severally. The contract consisted of the Australian Standard General Conditions of Contract (AS 2124-1992) together with General Conditions of Tendering and Form of Tender (AS 2125-1992) and Form of Formal Instrument of Agreement (AS 2127-1992). The agreement consisted, further, of attached specifications for mechanical services, electrical services, hydraulic and fire services, and the specific specification for alterations and additions to the Boilerhouse generally referred to as “the specification”.

# The contract also consisted of documents termed “other documents”, namely, a copy of the tender letter of the plaintiff dated 17 May 1999 and a copy of the defendants’ acceptance by letter dated 20 May 1999. It should be noted that the contract itself referred to the singular when referring to the defendants (“principal” as opposed to “principals”). It is clear however that the word “principal” in the contract referred to any and all of the defendants who were parties to the contract. The contract contained the standard conditions with respect to construction and interpretations and the documents said to constitute the “contract documents”.

# Clause 5 of the contract was concerned with security, retention moneys and performance undertakings (appendix A). It made provision for security, retention monies and performance undertakings for the purpose of ensuring the due and proper performance of the contract. The form of the security consisted of cash, bonds or inscribed stock.

SECURITY

# Clause 5.5 was of particular relevance because of the eventual recourse by the defendants to the securities. Clause 5.5 provided:

5.5 Recourse to Retention Moneys and Conversion of Security

A party may have recourse to retention moneys and/or cash security and/or may convert into money security that does not consist of money where –

(a) 	the party has become entitled to exercise a right under the contract in respect of the retention moneys and/or security; and

(b)	the party has given the other party notice in writing for the period stated in the Annexure, or if no period is stated, five days of the party’s intention to have recourse to the retention moneys and/or cash security and/or to convert the security; and

(c)	the period stated in the Annexure, or if no period is stated, five days has or have elapsed since the notice was given.

LATENT CONDITIONS

# Clause 12 was concerned with latent conditions. It defined (cl.12.1) latent conditions as physical conditions on the site or its surroundings which differ materially from the physical conditions that should reasonably have been anticipated. It also provided (cl.12.2) that if, during the execution of the work, the contractor became aware of a latent condition then it was required to give written notice to the superintendent forthwith. There was also provision (cl.12.3) that where delay was caused by a latent condition it may justify an extension of time under cl.35.5 of the contract if it caused the contractor to carry out additional work, use additional constructional plant, or incur extra cost which the contractor could not reasonably have anticipated in which case a variation could be made under cl.40.5 of the contract. Clause 12 is set out in appendix B.

STATUTORY COMPLIANCE

# Clause 14 of the standard contract provided that the contractor must comply with various specified statutes, including, the Acts of Victoria and other statutory provisions. It further provided that, if a requirement was at variance with a provision of the contract, then the contractor was obliged to notify the superintendent in writing of the difference. If a requirement necessitated a change to the works or method of working as specified in the contract, the superintendent was bound to direct a variation under cl.40.1 of the contract. Specifically, the clause provided that, except to the extent that the contract provided for reimbursement, then the contractor was obliged to bear the cost of compliance with such statutory requirement whether the requirement existed at the time of tendering or not.

# Clause 14 of the contract is set out in appendix C to these reasons.

THE SUPERINTENDENT

# The role and performance of the superintendent was a significant issue in the proceedings. Clause 23 of the contract set out the obligations of the superintendent. Clause 24, as amended, provided for a representative of the superintendent from time to time.

# Clause 23 provided:

“23 SUPERINTENDENT

The principal shall ensure that at all times there is a Superintendent and that in the exercise of the functions of the Superintendent under the Contract, the Superintendent –

(a)	Acts honestly and fairly;

(b) 	Acts within the time proscribed under the Contract or where no time is proscribed within a reasonable time;

(c)	Arrives at a reasonable measure or value of work, quantities or time.

If, pursuant to a provision of the Contract enabling the Superintendent to give directions, the Superintendent gives a direction, the Contractor shall comply with the direction.

….”

# Clause 24 provided:

“SUPERINTENDENTS’ REPRESENTATIVE

The Superintendent shall ensure that at all times there is appointed a registered architect as Superintendent’s Representative under the Contract to exercise the usual duties of a supervising architect but not more than one Superintendent’s Representative shall be delegated the same function at the same time.”

# Clauses 23 and 24 of the contract are set out in appendix D to the reasons.

CONTRACTOR’S REPRESENTATIVE

# Clause 25 of the contract provided that the contractor shall personally superintend the execution of the work and have a competent representative present on-site and, if required by the superintendent, at other places at which activities relating to the contract take place.

THE SITE

# Clause 27 of the contract provided that the principal was to give the contractor possession of the site. It further provided that, if the contractor was in breach of cl.21.1, then the principal may refuse to give the contractor possession of the site or any part of the site until the contractor had complied with the requirements of cl.21. Clause 21 was concerned with insurance arrangements.

THE SET-OUT

# Clause 28 of the contract provided for the setting out of the works. It required the superintendent to supply to the contractor the information and survey marks necessary to enable the contractor to set out the works and the survey marks specified in the contract. Clause 28.3 was concerned with errors in setting out. It provided that, if the contractor discovered an error in the position, level, dimensions or alignment of any work under the contract, then the contractor was required to immediately notify the superintendent and the contractor would rectify the error unless the superintendent otherwise directed. The sub-clause also provided that, if the error was caused by incorrect information, survey marks or data supplied by the superintendent, then, the cost incurred by the contractor in rectifying the error was to be valued under cl.40.5 as a variation.

MATERIALS AND WORK

# Clauses 29 and 30 of the contract were concerned with the provision of materials, labour and constructional plant and also the quality of materials.

# Clause 29.1 provided that the contractor was required to supply everything necessary for the proper performance of its obligations and discharge of its liabilities under the contract. Clause 29.2 provided that the superintendent may direct the contractor not to remove from the site constructional plant or materials. Clause 29.3 provided that the superintendent could direct the contractor to supply particulars of the mode and place of manufacture and the like.

# Clause 30 required the contractor to use materials and standards of workmanship required by the contract and in the absence of any requirement to the contrary for the contractor to use suitable new materials. Clause 30 also provided that, if the superintendent discovered material or work which was not in accordance with the contract, then the superintendent was entitled to direct the contractor to remove the material, demolish the work, reconstruct, replace or correct the material or work. Clause 30 further provided that, if the contractor failed to comply with such a direction, then provided seven days had elapsed, the principal may have the work performed and the performance of such work was a debt due from the contractor to the principal. Clause 30 further provided that the superintendent may direct a variation pursuant to cl.40 of the contract to be valued, and if the variation causes an increase or decrease in the value to the principal of the works, then regard should be had to that effect; and that if the variation results in the contractor incurring more or less cost than would reasonably have been incurred, then regard was to be had to that difference also.

# Clauses 29 and 30 are set out in appendix E to these reasons.

PROGRESS AND PROGRAMMING OF THE WORKS

# Clause 33 of the contract provided that the contractor was to proceed with the work with due expedition and without delay. The contractor was precluded from suspending the progress of the whole or any part of the work except for suspension as provided for under cl.44.9, or as directed or approved by the superintendent under cl.34. Clause 44 related to default or insolvency, and cl.34 related to suspension of the works with respect to insurance arrangements.

# Clause 33 required the contractor to give the superintendent reasonable advance notice of when it required any information, materials, documents or instructions from the superintendent or the principal. Clause 33 further provided that the superintendent could direct the order and times at which various stages or parts of the work under the contract were to be performed. If the contractor was able to reasonably comply with the direction, then the contractor was obliged to do so. If the contractor could not reasonably comply with the direction, then the contractor was required to notify the superintendent in writing of that fact and provide reasons. Clause 33 also provided that if compliance with the direction caused the contractor to incur more or less cost than otherwise would have been incurred, then the difference would be valued under cl.40.5 as a variation.

# Clause 33 also provided for a construction program to be constituted as a statement in writing showing the times by which the various stages or parts of the work under the contract were to be executed or completed. Clause 33 further provided that the contractor was precluded from departing from the construction program included in the contract or a construction program furnished to the superintendent. It also provided that the furnishing of a further construction program would not relieve the contractor of any obligations under the contract, including the obligation to not depart from an earlier construction program without reasonable cause.

# Clause 33 of the contract is contained in appendix F to the reasons.

SUSPENSION OF THE WORKS

# Clause 34 was concerned with suspension of the works by the superintendent or the contractor. It specifically provided for the superintendent to be empowered to suspend the whole or part of the work if considered necessary because of an act or omission of the principal, the superintendent or an employee or the contractor; for safety reasons; or to comply with an order of the Court. It also provided that the contractor may suspend the whole or part of the work under the contract with the written approval of the superintendent. Clause 34 also provided that any cost incurred by the contractor by reason of a suspension under cl.34 was to be borne by the contractor, but if the suspension was due to an act or omission of the principal, the superintendent, or an employee, then, if the suspension caused the contractor to incur more or less cost than would otherwise have been incurred, the difference was to be valued under cl.40.5 as a variation.

# Clause 34 is set out in appendix G to the reasons.

TIMES FOR COMMENCEMENT AND PRACTICAL COMPLETION

# Clause 35 of the contract set out the requirements with respect to the time for commencement of work on the site and, in particular, time for practical completion. Specifically, the clause provided for the contractor to complete the work under the contract to “Practical Completion by the Date for Practical Completion”. The interpretation and definition provisions of the contract, clause 2, provided that the “Date for Practical Completion” meant:

(a)	Where the Annexure provides a Date for Practical Completion, 	the date;

(b)	Where the Annexure provides a period of time for Practical 	Completion, the last day of the period,

but if any extension of time for Practical Completion is granted by the Superintendent or allowed in any arbitration or litigation it means the date resulting therefrom”.

# The date for practical completion provided in the contract was 10 December 1999. Clause 2 of the contract further provided for the definition of “Date of Practical Completion” as meaning:

“(a)	The date certified by the Superintendent in a Certificate of 	Practical Completion issued pursuant to clause 42.5, to be the 	date upon which Practical Completion was reached; or

(b) 	Where another date is determined in any arbitration or litigation 	as the date upon which Practical Completion was reached, that 	other date”.

# “Practical Completion” itself was defined by cl.2 as constituted by the following:

“Practical Completion” is that stage in the execution of the work under the Contract when -

(a)	The Works are complete except for minor omissions and minor 	defects –

(i) 	Which do not prevent the Works from being reasonably 	capable of being used for their intended purposes; and

(ii) 	Which the Superintendent determines the Contractor has 	reasonable grounds for not promptly rectifying; and

(iii) 	Rectification of which will not prejudice the convenient 	use of the Works; and

(b)	Those tests which are required by the Contract to be carried out and passed before the Works reach Practical Completion have been carried out and passed;

(c)	Documents and other information required under the Contract which, in the opinion of the Superintendent are essential for the use, operation and maintenance of the Works have been supplied.”

# Clause 35 provided for extensions of time for practical completion. It provided that, where it became evident to the contractor or the principal, then each was obliged to notify the superintendent in writing of details of the possible delay. If the contractor was to be delayed in reaching practical completion and within 28 days after the delay occurred notified the superintendent in writing for a claim for an extension of time for practical completion, then the contractor would be entitled to an extension of time for practical completion. The contractor was only so entitled if a specified cause arose. The causes set out in cl.35.5 were events occurring beyond the contractor’s reasonable control, including industrial conditions and inclement weather; delays caused by the principal, the superintendent or the principal’s employees; actual quantities of work being greater than the quantities specified in the annexure to the contract; latent conditions; variations directed under cl.40; repudiation or abandonment by a nominated sub-contractor; changes in the law; directions by appropriate authorities; delays by specified authorities not caused by the contractor; claims referred with respect to damage to persons and property other than the works; any breach of the contract by the principal; and any other cause which is expressly stated in the contract to be a cause for extension of time for practical completion.

# The date of practical completion certified by the superintendent was 13 January 2000.

# Clause 35 further provided for liquidated damages for delay in reaching practical completion. Provision was made that, if the contractor failed to reach practical completion by the date for practical completion, then the contractor was indebted to the principal for liquidated damages at the rate stated in the annexure for every day after the date for practical completion. The annexure to the contract provided for liquidated damages at the rate of $1,100.00 per day. The amount of liquidated damages was unlimited.

# Clause 35 is set out in appendix H to the reasons.

DELAY OR DISRUPTION COSTS

# Clause 36 of the contract provided that, where the contractor was granted an extension of time under cl.35, the principal was obliged to pay to the contractor such extra costs as were necessarily incurred by reason of the delay. There was specific provision that nothing in cl.36 obliged the principal to pay extra costs for delay or disruption already included in the value of a variation or other payment under the contract, or limit the principal’s liability for damages for breach of contract.

# Clause 36 is set out in appendix I to these reasons.

VARIATIONS

# Clause 40 of the contract was concerned with variations. It provided that the superintendent may direct the contractor to increase, decrease or omit any part of the work under the contract, change it, execute additional work, or demolish or remove material or works that are no longer required by the principal. The contractor was precluded from varying the work, except as directed by the superintendent. Clause 40 provided, further, that the contractor was bound only to execute a variation which was within the general scope of the contract. Upon receipt of a notice from the superintendent advising the contractor of a proposed variation under cl.40, the contractor was required to advise the superintendent whether the proposed variation could be effected and, if so, to advise the superintendent of the effect on the construction program and the time for practical completion and an estimate of the cost, including delay costs of the proposed variation. There was provision that the principal would reimburse the contractor for the reasonable costs of complying with the requirements of cl.40.2. In the absence of agreement between the superintendent and the contractor, the variation was to be valued under cl.40.5 of the contract which  specified the particular valuation methods to be used.

# Clause 40 of the contract is reproduced in appendix J to the reasons.

CERTIFICATES AND PAYMENTS

# Clause 42 set out the regime for payment claims, certificates, calculations and time for payment. It also provided for a certificate of practical completion and a final payment claim. Broadly, cl.42.1 provided a structure whereby the contractor was to deliver claims for payment referred to as “payment claims”. Within 14 days after receipt of a payment claim, the superintendent was obliged to issue to the principal and to the contractor a payment certificate stating the amount of the payment which, in the opinion of the superintendent, was to be made by the principal to the contractor. The superintendent was required to set out in the certificate the calculations employed to arrive at that amount.

# Clause 42 further provided that, if the contractor failed to make a payment claim, then the superintendent could nevertheless issue a payment certificate. The clause further provided that if, within 28 days after receipt by the superintendent of a claim for payment, or within 14 days of issue by the superintendent of a payment certificate (whichever was the earlier), the principal was bound to pay to the contractor an amount not less than the amount shown in the certificate as due to the contractor. If no payment certificate had been issued, the principal was bound to pay the amount of the contractor’s claim. Clause 42 further provided that a payment made pursuant to cl.42.1 did not prejudice the right of either party to dispute the amount under cl.47, the dispute resolution clause of the contract.

# Clause 42.5 also provided for the certificate of practical completion. It required the contractor to give the superintendent at least 14 days notice of the date on which the contractor anticipated that practical completion would be reached. It further provided that, within 28 days after the expiration of the defects liability period, the contractor was to lodge with the superintendent a final claim endorsed “Final Payment Claim”. Clause 42 made provision for interest on overdue payments. It provided that if any moneys due remained unpaid after the expiration of the date for payment, then interest was to be paid at the rate of 5 per cent above the National Bank of Australia’s 90 day bill rate. Clause 42.10 provided for set-offs by the principal, namely, the deduction of moneys due to the contractor where owed to the principal. Clause 42.10 also provided that the principals, subject to cl.5.5, may have recourse to retention moneys and, if they are insufficient, then to security under the contract.

# Clause 42 is set out in appendix K to the reasons.

DEFAULT

# Clause 44 set out the applicable provisions in the event of default. It provided that if the contractor committed a substantial breach of contract and damages was not an adequate remedy, then the principal may give the contractor a written notice to show cause. Substantial breaches were defined to include (but were not limited to) suspension of work, failing to proceed with due expedition and without delay, failing to lodge security, failing to use the materials or standards of workmanship required by the contract, failing to comply with a direction of the superintendent, failing to provide evidence of  insurance, and other related matters. Clause 44 entitled the principal to serve a show cause notice and specifically provided that such notice must:

(a)	state that it was a notice under clause 44;

(b) 	specify the alleged substantial breach:

(c)	require the contractor to show cause in writing;

(d) 	specify the time and date by which the contractor must show 	cause, but not less than seven days after the notice is provided; 	and

(e)	specify the place at which cause must be shown.

# If the contractor failed to show cause then the principal was entitled to give notice in writing to the contractor to take out of the hands of the contractor the whole or part of the work remaining to be completed, or to terminate the contract. Upon giving such notice, the principal may suspend payments to the contractor until the date on which the contractor showed reasonable cause, the principal took action under cl.44, or the date which is seven days after the last day for showing cause. If the principal exercised a right under cl.44, then the contractor was not entitled to any further payment in respect of the work taken out of its hands unless a payment became due to the contractor as otherwise provided under clause 44. Where the principal took the work out of the hands of the contractor pursuant to cl.44, then the principal was obliged to complete the work and, as reasonably required, facilitate completion of the works. If the principal took such possession, then it was obliged to maintain plant and other equipment on-site owned by the contractor, and on completion, return it to the contractor.

# Clause 44 further provided that, where work was taken out of the hands of the contractor and completed, the superintendent was obliged to ascertain the cost incurred by the principal in completing that work and issue a certificate to the principal and the contractor specifying the amount of the cost. If the amount of the cost incurred by the principal was greater than the amount that would have been paid to the contractor if the work had been completed by it, then the difference became a debt due from the contractor to the principal. If the cost was, in fact, less than the amount that would have been paid to the contractor, then the difference became a debt due from the principal to the contractor.

# Clause 44 also made provision with respect to a default of the principal. It provided that, if the principal committed a substantial breach of contract and the contractor considered that damages was not an adequate remedy, then the contractor may give the principal a written notice to show cause. Substantial breaches were defined to include (but were not limited to) –

(a)	failing to make a payment;

(b)	failure by the superintendent to either issue a certificate of 	practical completion or give the contractor, in writing, reasons 	for not issuing the certificate;

(c)	failing to produce evidence of insurance;

(d) 	failing to give the contractor possession of sufficient of the site;

(e)	failing to lodge security in breach of clause 5.

Where the contractor served a show cause notice under cl.44.8, it was required to include in the notice:

(a)	a statement that it was a notice under cl.44;

(b)	specify the alleged substantial breach;

(c)	require the principal to show cause;

(d)	specify the time and date by which the principal must show 	cause;

(e) 	specify the place at which cause must be shown.

In the event of the contractor exercising its rights and the principal failing to show cause, the contractor, by notice in writing to the principal, was entitled to suspend the whole or any part of the work under the contract. The contractor was entitled to recover from the principal any damages incurred by it arising from the suspension. In the event of the contract being terminated pursuant to cl.44, then the rights of the parties were stipulated under the contract, as they would have been at common law, had the defaulting party repudiated the contract and the other party elected to treat the contract as at an end and recover damages.

# Clause 44 is set out in appendix L to these reasons.

WAIVER

# Clause 48 of the contract provided that, except as provided at law or in equity or in the contract, none of the terms of the contract were to be varied, waived, discharged or released, except with the prior consent in writing of the principal in each instance.

SUMMARIES OF WITNESSES’ EVIDENCE

# The evidence in the trial was substantial, complex and technical. A series of witnesses were called on both sides, mostly technical and expert. All witnesses provided witness statements, some of which ran to hundreds of pages. The witnesses were subject, in most instances, to extensive cross-examination and re-examination. Much of the viva voce evidence involved cross-referencing to multiple specifications, plans, shop drawings and drawings. The documentary evidence consisted of 72 court book volumes, over 100 volumes of lever arch folders and numerous sets of plans and specifications. The documents before the court and the transcript ran to thousands of pages. The trial ran for just over 10 weeks. Without the benefit of witnesses’ statements and the requirement of written submissions, both opening and closing, the duration of the trial would have been many many months. Given the magnitude of the evidence and submissions, and in light of the observations of the Court of Appeal in Fletcher Construction Australia Ltd v Lines MacFarlane & Marshall Pty Ltd (No. 2), I have considered that evidence and the submissions in considerable and intensive detail. I have borne in mind all the evidence in reaching my findings. Where I do not specifically refer to or recite the evidence of an individual witness, or the detail of a particular document, I have not disregarded or overlooked that matter. Ultimately, in a substantial and technical matter of this type, being a long and hard fought building case, the summary of evidence and submissions and the analysis of the evidence must necessarily be limited.

PLAINTIFF’S EVIDENCE

# The main witnesses called for the plaintiff were:

(1) Tivendale

# the project manager: his evidence was principally concerned with extension of time claims, termination of contract, the role of the superintendent, the set-out and structural steel issues, defective works and rectification works and issues relating to Kane’s quantum meruit claim.

(2) Forster

# the chairman of directors of the plaintiff company: his evidence was concerned with the contract itself, termination, the role of the superintendent, extension of time claims and various other matters.

(3) Lucas

# the finance director of the plaintiff: his evidence was concerned with termination and other various matters.

(4) Isaacson

# the construction director of the plaintiff: his evidence was concerned with the contract, termination, and the role of the superintendent.

(5) Skarajew

# the site foreman of the plaintiff: his evidence was concerned with termination, the role of the superintendent, the set-out and structural steel issues, the extension of time claims, the variations and the deduction variations.

(6) Williamson

# another site foreman: his evidence was concerned with termination, the role of the superintendent, the set-out and structural steel, the extension of time claims, the variations and other various matters.

(7) Omond

# another site foreman of the plaintiff: he was concerned with termination, the role of the superintendent, the set-out and structural steel, extension of time claims, variations and other matters.

(8) Swarbrick

# the façade foreman: he was concerned with matters relating to the contract, the role of the superintendent, the variations and the deduction variations.

(9) Qi Shao

# the draftsperson employed by the plaintiff to prepare the shop drawings: her evidence was concerned with the shop drawings.

(10) Dordevic

# the steel engineer engaged by the plaintiff: his evidence was concerned with the shop drawings and set-out.

(11) Thomas

# the quantity surveyor engaged as an expert by the plaintiff to give evidence about the quantum meruit assessment: his evidence was principally concerned with the contract, termination, the role of the superintendent and the extension of time claims.

(12) Lynas

# an expert engaged by the plaintiff for the purposes of the trial: his evidence was concerned with the extension of time claims.

(13) Lee

# an expert engaged by the plaintiff concerned with variations.

(14) Gilfillan

# a further expert engaged by the plaintiff: his evidence was concerned with the variations, the deduction variations and aspects of the Domestic Building Contracts Act.

# There were “pair” expert witnesses in most instances. The expert witness opposed to Lynas was Degenhardt; the expert witness opposed to Lee was Goodwin; and the expert witness called by the defendants to deal with the evidence of Gilfillan was Permewan.

DEFENDANTS’ EVIDENCE

# The principal witnesses called by the defendants were:

(1) Sopov

# the owner of the site: his evidence was concerned with virtually all matters.

(2) Jeffery

# the superintendent of the site engaged by the defendants: his evidence was concerned with most aspects of the claim.

(3) Brown

# a mechanical consultant retained by the defendants in relation to the set-out and structural steel issues.

(4) Long

# a structural engineer retained by the defendants who gave evidence with respect to the set-out and structural steel.

(5) Pandov

# who made a video recording of the site which was relevant with respect to the topic of termination.

(6) Degenhardt

# an expert witness called by the defendants with respect to the superintendent’s role, extension of time claims and the set-out and structural claim issues.

(7) Goodwin

# an expert called by the defendants in relation to the deduction variations.

(8) Permewan

# an expert called by the defendants in relation to the variations.

# In light of the breadth and technical nature of the much of the witnesses’ evidence, it is appropriate to set out in summary the evidence given by each of the main witnesses.

PLAINTIFF’S EVIDENCE

(1) TIVENDALE

# Tivendale’s Role as Project Manager

# In his original witness statement dated June 2003, Gary Charles Tivendale stated that he commenced working as a contractor with the plaintiff, Kane Constructions (“Kane”), in the capacity of contract administrator in 1994 and became a project manager in 1995. He is a graduate of the University of Melbourne, obtaining his Bachelor of Building degree in 1983.

# In May 1999, when construction commenced on-site, Tivendale commenced work on the Boilerhouse project as Kane’s project manager. From that time until August 1999, he was involved in contract negotiations with Mr Jonathan Forster, the Executive Chairman of Kane.

# Although project manager for the duration of the works, Tivendale’s presence on-site was not constant throughout the project. From May 1999 to February 2000, he was on-site approximately two or three times per week, for about an estimated two to four hours each time. After February 2000, when he commenced working on the Boilerhouse project full-time, Tivendale attended the site on a daily basis, spending approximately 15 to 20 hours per week on-site.

# According to his original witness statement, Tivendale’s primary functions and responsibilities in the project were as follows. He assisted Kane personnel in communicating and handling daily communications with the principals, superintendent and sub-contractors; he prepared and submitted extension of time (“EOT”) claims to the superintendent; he supervised the letting of the sub-contracts; he assisted the contract administrators, first Mr Short with progress claim 1 and secondly, Le Hy Ta, with respect to progress claims 2- 15. He was responsible for project planning and wrote Boilerhouse programs 1 through to 11, which set out the sequence of the works to be done and anticipated the date of practical completion. Other tasks involved general project management.

# In performing his duties, Tivendale was in regular communication with the superintendent; Le Hy Ta (Kane’s contract administrator for the majority of the project); the principal (Mr Cole Sopov); Williamson, Omond & Skarajew (Kane’s on-site managers); and Swarbrick (façade foreman).

# For the period May 1999 through to December 1999, Tivendale said in evidence that he kept a paper diary recording site progress. Tivendale said that this diary has since been lost by him. For the period January 2000 through to December 2000, Tivendale used a palm pilot to record attendances at meetings and other details in relation to the project, which presumably he also used in the preparation of evidence. Tivendale also retained and used three files in relation to the Boilerhouse project, some or all of which were used in the preparation of his three witness statements. These included file number 75, documents and handwritten notes in relation to the sub-contractor’s works; file number 76, which contained information on-site meetings, general information and handwritten notes made at the site meetings; and file number 77, which included copies of requests for further information (“RFI”s), drawings and handwritten notes.

# During cross-examination, Tivendale’s abilities as project manager, particularly with respect to the programming task, were called into question. For instance, counsel for the defendants, Mr Magee, suggested to Tivendale that he had consulted Williamson (the façade foreman) about drawing up programs for the project because he himself “hadn’t sufficient experience to draw the Boilerhouse Program 1 without consulting him”. Tivendale flatly rejected the suggestion that his programming was somehow “faulty”, however he said that he had requested Williamson’s involvement because he desired his input as the construction manager.

# During re-examination, Tivendale outlined his extensive previous experience in performing similar tasks on other sites. He also pointed out that the lack of feedback on the time extensions made it extremely difficult to program the project as contemplated under the contract. In particular, he said that it put him in an uncertain position as to when the date for practical completion would be.

# Tivendale’s relationship and behaviour with the superintendent and the principal during the project was also questioned. At trial, it was put to him that he demonstrated a distinct inability to follow clear instructions, with one example put forward being his failure to construct a beam in accordance with the plans. During cross-examination, counsel for the defendants also asserted that it was Tivendale’s practice to “go behind the superintendent and Mr Sopov’s back, to try and get calculations from the engineer to justify [his] conduct”. Whether or not one accepts the suggestions of the defendants in this respect, what is clear is that at some stage of the project, perhaps around the beginning of 2000, relations between the project manager and the superintendent, and between the project manager and the principals, had deteriorated to a point where there was apparently little effective communication between the parties.

# The Superintendent

# During Tivendale’s evidence, the work performed by the superintendent, Mr Trevor Jeffery, came under intense scrutiny. In essence, it was Kane’s position that it was the responsibility of the defendants to appoint a competent supervisor, which Kane claimed did not occur. Tivendale, during both cross-examination and re-examination, asserted numerous times that the delays to the project were not to be attributed to himself or to Kane; rather, they stemmed from two particular sources. First, the claimed deficiencies in the contract documents, and second, the alleged incompetency of the superintendent in that role. Moreover, Kane held the superintendent responsible for the claimed discrepancies in the contract drawings and documents since they were in fact issued by him.

# Tivendale gave evidence that construction problems often arose as a consequence of works being performed according to the contract drawings which were later found to be “unworkable”. He said that many of the construction problems encountered were as a result of what he believed to be discrepancies or “deficiencies” in the contract drawings that resulted in some extension of time claims being issued. Kane contended that the difficulties with the contract drawings and documents had a disastrous flow-on effect.

# For instance, the situation was compounded by the refusal of the superintendent to respond or allow Kane’s EOT claims, which Tivendale said made the programming task on the Boilerhouse project considerably more difficult. He stated that the consequence of the EOT’s not being answered in a timely fashion was that he had to assume that the EOT’s submitted would be approved, since he had not received feedback and therefore did not have any other date to work from. He stated that this put Kane in an “invidious position”, preventing them from programming the works in light of a properly determined date for practical completion. As proof of their claims with respect to the response times for the EOT’s, counsel for the plaintiff tendered a document, prepared by the witness, which was a table showing the dates of EOT submissions and assessment dates.

# Tivendale also noted that there were numerous occasions when Kane did not receive timely or accurate responses to RFIs, despite the fact that it was important to the efficiency of the project that RFIs be promptly responded to by the superintendent. As evidence of this, Tivendale pointed to several occasions where Kane apparently submitted RFIs to the superintendent without receiving a response for several weeks. According to Kane, slow response times to both EOTs and RFIs held up progress on the project works.

# According to Tivendale, Jeffery also lagged in his response times to claimed variations, which along with the RFIs and EOTs not responded to, helped to create unpleasant relations between the contractor and sub-contractors on-site. When questioned by Kane’s counsel about the causes of the discord which apparently existed on-site between Kane and the sub-contractors, Tivendale stated that one of the reasons for this was that “[w]e had the electricians, the plumbers, the plasterers and other sub-contractors whose variations were not being looked at, not being approved, not being answered, and it does cause a lot of grief to a sub-contractor who doesn’t know what he is going to get paid for.” Tivendale went on to say that the sub-contractor often did not differentiate between whether the lack of response was due to Kane or the superintendent. Tivendale said that the anxiety and concern over whether the sub-contractors were going to get paid for extra works was aimed at Kane who had hired them and who had the most contact with them.

# For their part, the defendants claimed that the nature of the relationship between the parties on-site had little to do with the superintendent or the owners; rather, Kane as the main contractor was responsible for creating a harmonious and productive atmosphere which had nothing to do with them.

# Progress Claims Procedure

# Tivendale stated that Le Hy Ta was primarily responsible for the preparation of progress claims 2-15, the first one having been prepared by Short. It was Tivendale’s responsibility however to check each claim before submission to the superintendent. Tivendale stated that this would occur on or about the 28th day of each month of the project, where Tivendale would discuss the contents of each claim prepared by Le Hy Ta, meaning that Tivendale was intimately aware of all the details claimed by Kane for each claim submitted.

# Following the issuing of each progress certificate, Jeffery requested Kane to sign a statutory declaration certifying that all sub-contractors had been paid. Tivendale signed and dated most of them, since payment from the superintendent was apparently “contingent” upon signing. The few not signed by Tivendale were signed by Le Hy Ta in his absence.

# Tivendale also asserted in his original witness statement that at no time did he indicate to Jeffery that he would agree to a varied payment or claims procedure, as alleged by the defendants in their amended defence and counterclaim. Tivendale flatly rejected this suggestion, stating that he “did not engage in any discussions with Jeffery in relation to that matter”.

# Progress Claim 14

# Le Hy Ta submitted progress claim 14 on or about 1 August 2000 following Tivendale’s review of it. For progress claim 14, Kane claimed the sum of $1,216,546.64. Certificate 14, issued by the superintendent on 23 August 2000 in response, certified $340,562 (together with GST) in Kane’s favour. The same day, Tivendale stated that he signed the statutory declaration certifying that the sub-contractors had been paid so that Kane could receive payment on the certificate; although according to him, this was not necessarily the case. By letter dated 28 August 2000, Kane was then informed that liquidated damages of $220,000 would be deducted from certificate 14, meaning that Kane would in fact receive only $120,562 as a result of the lodgement of the certificate. A revised certificate 14, advising Kane to that effect, was dated 6 October 2000.

# Progress Claim 15

# Progress claim 15 claimed the sum of $1,231,742.81. This sum did not appear to include the $340,562 which had been originally been certified in Kane’s favour in response to progress claim 14. Certificate 15, issued in response to progress claim 15 on 14 September 2000, certified $220,800 in Kane’s favour. This certificate apparently did not deduct or make any reference to the defendants’ entitlement to liquidated damages. The revised certificate 15, dated 6 October 2000, certified less than this amount; this time being $187,000 in Kane’s favour. Kane did not prepare a tax invoice with respect to certificate 15, nor did the contractor receive any payment in relation to it.

# In his evidence, Tivendale maintained that the superintendent often revised both progress claims 14 and 15 on the basis of what had been “physically done”, ie particularly with respect to the large amount claimed as a result of the sub-contract with the plastering firm, MTK (a company no longer in existence). During re-examination, Tivendale agreed that the superintendent undertook “the process of valuing what he thought the actual value and progress of the works on-site was, from month-to-month, by reference to what was physically going on and what materials were being delivered to the site”. However, Tivendale asserted that Jeffery’s method of breakdown in this respect was a mistake, stating that “[o]ften, these breakdowns don’t relate specifically to the contracts that we let, because there is some up and down in those figures. But at the end of the day we are paid the contract amount, so we proceed for our progress claims based upon an original break-up given at the time of tender”. Hence, the builder was unable to claim where the amounts exceeded breakdown amounts given at the time of tender.

# Delays and Delay Costs

# According to Tivendale, the delays experienced by the builder on the Boilerhouse site were a result of two basic and inter-related problems: firstly, what the witness variously called the “deficiencies” or the “discrepancies” in the contract drawings and documents. The second point concerned Tivendale’s view that delays often came about due to the incompetence of the superintendent hired by the defendants, whose responsibility it therefore was for the delays flowing from Jeffery’s asserted slow response times to EOT claims, RFIs and variation claims. Tivendale clearly thought that the superintendent (and through him ultimately the defendants) was responsible for the issuing of the flawed contract drawings and documents in the first place.

# On the other hand, during Tivendale’s evidence, counsel for the defendants, Mr Magee, suggested that the delays experienced during the project were at least partially the result of “poor co-ordination” of the tradespersons by Kane. It was inferred that it was at least partially for this reason that Kane suffered poor relations with the sub-contractors. Mr Magee extracted comments from a document written by representatives of Custom Chassis (who installed the handrails) as evidence of this. Tivendale rejected this evidence however, stating that they (Custom Chassis) were “not in a position to comment”. During re-examination, Tivendale clarified what he meant by this, namely that  Custom Chassis were not aware of the EOT claims and the other discrepancies and difficulties being experienced on-site.

# During cross-examination, Mr Magee also referred the witness to the sub-contractor, Australian Aluminium Shop Fitting Pty Ltd (“AAS”), and their complaints to Kane about their inability to access the site, inferring this indicated a lack of co-ordination on Kane’s behalf which led to delays (and therefore presumably costs claimed by Kane for the delays caused). However, during re-examination, Tivendale asserted that this access problem was “impossible to avoid” and, in any case, it occurred over only a short period of time and did not affect the progress of overall works on the critical path.

# According to Tivendale, the sub-contractors blamed Kane as their employer, when the “real” problems – which they were unable to see given their lack of contact with the superintendent or the principal – stemmed variously from the incompetence of the superintendent and the deficiencies in the contract drawings and documents.

# As for delay costs, the contract provided by Sopov (AS-2124-1992 to replace the former JCC-D) stated that the daily rate for delays was nil. Tivendale said that he made it clear to Sopov, at a meeting between the parties held on 30 June 1999, that Kane was not prepared to accept nil and that they would need to agree on a daily rate. At that time, Kane had already commenced on-site and had already encountered delays in early June 1999 (basement rock forming part of EOT claim no.1). Tivendale said that Sopov and Hampton had allegedly agreed to a margin of 10 per cent for delay costs incurred, which was now denied by the defendants. Tivendale, and it appears Kane, subsequently relied upon this discussion and not upon the Domestic Building Contracts Act.

# Extension of Time Claims

# As of 13 September 2000, the builder had amassed a claim for $660,135.00 in costs associated with EOTs. This equates to the original contract amount of day-to-day running costs of the project increasing in the order of 550 per cent. Nevertheless, the superintendent’s assessments of the EOTs – all of which were prepared and submitted by Tivendale – approved just $5,675.00 as acceptable costs, or in other words, less than 1 per cent of costs claimed.

# Extension of Time Claim 1

# For EOT 1, Kane claimed 12 days delay as a result of two major items or incidents. With regard to Item 1 of the claim, Tivendale said that Kane was delayed eight days when it encountered rock whilst excavating the lift-overrun pit. During cross-examination, Mr Magee noted that the pit was not “very big”, thereby inferring that the claim for eight days was excessive. Tivendale agreed that the pit was only about 11 metres of excavated material (under 2 metres square, about 1.5 - 2 metres deep), however he said that this event delayed Kane for the period stated. When an outside expert, Mr Degenhardt, was brought in to assess this item of the EOT claim, he stated his belief that it would take in fact only four days to remove the rock. At trial, it appears that the defendants adopted this assessment of four days, despite the superintendent’s certification of only three days in SA152.

# With regard to Item 1 of EOT 1, Tivendale was also cross-examined on Kane’s claim for delay with regard to the pumping arrangements which had to be made as a result of damage to a water service pipe during concrete cutting to the ground floor slab on 4 June 1999. Tivendale explained that the pit did not have to be tanked, therefore saving time, because they put forward an alternative to use as a waterproof additive, called Xypex, as added to the concrete that they were using for the base and sides of the lift and footings in the basement. However Tivendale stated that they were still required to pump water out of the pit from 4 June 1999 up until 22 June 1999, which was “not work required under the contract”. Tivendale claimed that all of this work was unforeseen extra work which impacted on Kane’s building progress overall.

# Kane also claimed that the removal of material from the ground floor entry, classified as Item 2 of EOT 1, caused a delay of four days to the critical path of the project. According to Tivendale, this was necessary so that the builder could establish the appropriate foundations for the ground floor entry. When cross-examined on why he thought the ground floor entry and the ramp were “critical” to the completion of the project (an assertion denied by the defendants), Tivendale responded that, as per the program, Boilerhouse 1, the sequence and structural modification required that “you work your way up through the building before you could put… the structure on top of it”. While the witness confirmed that the stair was not a part of the structural modifications, he stated that the excavation of the stair one footings was; notwithstanding that Mr Magee suggested to Tivendale that the superintendent and (the defendants’ expert) Degenhardt claimed that the excavation of the stair one footings was not in fact critical to the progress works.

# During Tivendale’s evidence, much of the witness’ cross-examination on the subject of EOT’s 1 to 18 centred around the topic of what each party considered was or was not on the “critical path”. With regard to EOT 1 particularly, perhaps because it was the first EOT under cross-examination, Mr Magee queried the witness repeatedly in relation to the “critical path”.

# In relation to EOT 1, Kane asserted one day concurrent delay with regard to the ramp (included as a part of Item 2 of that claim). Tivendale maintained that the ramp was critical because, as with the removal of material from the stair footings, there was a sequence to be followed in order to keep the concretor on-site. Mr Magee asked the witness why he said that the ramp was critical when it was not critical to the progress of the building at that point, putting it to the witness as follows: “You are saying that it is critical because of some arrangement with the sub-contractor. Is that what you are saying?” Tivendale replied in the affirmative, saying that: “It was the sequence of work that we carried out on-site”. When asked who had the ultimate call in determining the sequence, Tivendale responded that it was a joint decision between himself and the engineer. During re-examination, Tivendale confirmed that if the concretors were prevented from doing their job at that time, then it could be difficult to get them back on-site to do the job as required, and further delay would result.

# In short, Tivendale considered items to be critical because that was what the sequence on the contract documents and drawings dictated; not because it actually had to be physically “done” at that particular point. This set the tone for Kane’s apparent attitude generally in relation to delays and the “critical path” for the duration of the case.

# Extension of Time Claim 2

# For EOT 2, Kane claimed two days as a result of industrial action. The claim for two days was accepted by the superintendent, however not by the defendants. The two days in contention are 7 July 1999 and 14 July 1999. The defendants refused to allow the days for the reason that, according to them, the works were not affected by strike action on 7 July 1999 and that three hours work was done on-site on 14 July 1999.

# At trial, both parties agreed that the only dispute with regard to industrial action was how it was to be treated under the contract. In this way, it was left to the court to determine the issue based on the contract.

# Extension of Time Claim 3

# For EOT 3, Kane claimed three days and two hours. There were two items categorised by Tivendale in attachment 1 of his original witness statement that comprised the claim. The first item was also with respect to industrial action. As noted above in relation to EOT 2, that point was not argued in court and it was agreed between the parties at trial that the only dispute with regard to industrial action was how it was to be treated under the contract.

# With regard to the second item of EOT 3, Tivendale stated that the superintendent directed them to cut the level 2 slab pursuant to the superintendent’s direction SA21. This in turn, he claimed, delayed structural alterations to the chimney face and office stair void, and delayed the scaffolding from being moved down. This claim was wholly rejected by the defendants.

# Extension of Time Claim 4

# For EOT 4, Kane claimed 47 days when it was submitted; however, Tivendale, in attachment 1 of his original witness statement, made reference to two days less than this, namely, 45 days. Counsel for the defendants spent a great deal of time cross-examining the witness on this particular EOT, as this claim was by far the largest of the 18 extension of time claims. Delay costs claimed by Kane for EOT 4 and submitted on 8 October 1999 (the same day the Boilerhouse 3 Program was issued by Tivendale) amounted to $144,000. The claim was mainly in relation to the structural steel and set-out.

# In evidence, and to assist in analysis of Kane’s claim, Tivendale produced a structural steel shop drawing registry (the “shop drawing registry”) and EOT 4 Delay and As Built program (the “As Built”). The shop drawing registry was produced by Tivendale from notations made on the workshop drawings provided by DVP Engineering Pty Ltd (“DVP”), including handwritten notes advising when specific shop drawings were provided for manufacture and notes on when the steel fabrication was completed. The “As Built” was designed to demonstrate the impact of structural steel events on the contract program, drawn from DVP workshop drawings, shop drawings, site diaries of Kane’s foremen and the shop drawing registry.

# Tivendale asserted that the causes of the delays in relation to the completion of the structural steel were due to changes made by the superintendent and the defendants, as arising from one or more of the following sets of circumstances: lack of detail in the design drawings and inconsistencies in these drawings; design changes made after the shop drawings had been approved; and/or design changes made during and after steelwork had been erected on-site.

# So that the court might better understand Kane’s claimed delay costs for EOT 4, in his first witness statement, Tivendale divided the critical path of the structural steel works into the following stages:

  - Stage 1 (or “Item 1”): Commencement of drafting (12 days);

  - Stage 2 (or “Item 2”): Gallery façade steel work (dictating the set-out for southern level 2 columns, southern level 3 floor beams and southern level 3 roof columns and beams) (8.5 days);

  - Stage 3 (or “Item 3”): Level 2 and Level 3 floor beams, including level 3 balconies and the Level 2 mansard roof connections to these beams and columns (33 days); and

  - Stage 4 (or “Item 4”): Level 3 roof columns and roof beams and the fascia trusses and plant platform (4 days).

  - Stage 1 – Stage 4 Structural Delays = 57.5 days in total.

# The original sub-contract value of the structural steel package was $230,000, and the Boilerhouse 1 Program allowed for a period of 61 working days for the completion of shop drawings and off-site fabrication, plus 10 working days for on-site erection (totalling 71 planned working days for all structural steel works). However, in reality, the process had an excess of 95 working days for the shop drawing process and an excess of 54 days for on-site erection (excess of 149 days = 220 days taken for the entire structural works to be completed). Kane claimed 57.5 days of the excess 149 days in delay costs.

# Stage 1 (or “Item 1”) of EOT 4: Commencement of Drafting

# Tivendale contended that there were six critical issues in the matter of the set-out which delayed Stage 1, i.e., delays to all shop drawings from being completed between 24 June 1999 and 9 July 1999:

  - position of the main entry gallery façade steel;

  - difficulties with protruding nib walls on the north-west corner;

  - existing grid lines had to line up with existing columns – but the existing steel

column capitals were much larger than the new steel columns;

  - original design deficiencies with respect to the line of the east façade;

  - distance from the existing grid E & F to the existing brickwork; and

  - the Alucobond columns to level 2 to the north and west façades had to line up

with existing external pilasters.

# In his evidence, Tivendale admitted that there was no provision in the Boilerhouse 3 Program (also written by him) for the shop drawings, or for what time people should commence shop drawings. Tivendale stated, however, that the shop drawing and steel manufacturers should be able to “tell” by the program what day the steel was required on-site.

# Tivendale was cross-examined on the following assertion made in his original witness statement: “Changes and lack of details caused shop drawing preparation and the approval process to be delayed which in turn delayed fabrication, and, ultimately, delayed on-site erection”. Counsel for the defendants, Mr Magee, put it to the witness that, as S & D Design and Drafting Pty Ltd (“S & D”), sub-contracted by DVP, was the only party producing the shop drawings, they were the “only party which could cause itself delay”. Tivendale agreed with that statement, but he noted the flow-on effect of delays, from the drawing stage, to manufacture and to installation. Counsel for the defendants also put it to the witness that Kane’s claimed delay for Stage 1 (12 days) could hardly be attributed to the defendants if the problems experienced by S & D at the time of drafting (particularly from 24 June 1999 until 9 July 1999) were not communicated to the superintendent or the principals. The inference was that the Stage 1 delay was therefore Kane’s own dilemma to deal with.

# Stage 2 (or “Item 2”) of EOT 4: Gallery Façade Steel Work

# Tivendale asserted that the critical issues with respect to delays for Stage 2 were as follows: (i) lack of information on how the terrace gutters were to be constructed allowing for falls and downpipes; (ii) alterations made pursuant to superintendent’s direction SA21, deletion of the architectural columns; (iii) alteration to beam LT1 and the addition of beam HB1 to the Level 2 slab edge; and (iv) alterations necessary to the main set-out dimensions. Tivendale asserted that all these delays were caused by either scarcity of information or incorrect details on the contract documents or drawings, a situation which was, according to Tivendale and Kane, compounded by the superintendent’s asserted slow response times to queries.

# (i) Lack of information on how the terrace gutters were to be constructed

# During his evidence, Tivendale was questioned on his assertion that the gallery façade steel was structural and therefore on the “critical path”. He stated that the gallery façade was structural because “[i]t holds up the floor beams and it holds up the roof”; and also that the gallery façade steelwork dictated the set-out of the Level 2 columns.

# Counsel for the defendants also challenged Tivendale’s assertion in his original witness statement that the lack of detail on the original contract drawings for the terrace gutter beam caused a five day delay to Stage 2. Mr Magee put it to the witness that the terrace gutters “delayed absolutely nothing” because they were not structural at all. Tivendale responded that they were on the structural steel drawings (and therefore presumably had to be done). When asked whether the gutters had feasibly been installed as an “appendage” and not as part of the structural steel process, Tivendale replied that the builder could have done so, but “only if the details were shown”. Kane submitted that the details were indeed not shown.

# Also on the issue of the terrace gutter beam, counsel for the defendants questioned Tivendale’s assertion that the five day delay claimed for this event was caused by Jeffery’s “incapable” response to RFI 42. Mr Magee pointed out during cross-examination that the five day delay could not be claimed by Kane as S & D could be getting on with the shop drawings in other critical areas. Tivendale agreed there were other critical areas that S & D could have been getting on with at that point, for instance the set-out.

# (ii) Deletion of the architectural columns

# In relation to the deletion of the architectural columns, Tivendale essayed the same argument that he had used with regard to the terrace gutter, namely that although the building would not literally fall down if they were not deleted at the given point where the delay of two days was claimed (and therefore they were not in the strictest sense of the word “structural”), they were on the critical path because they were part of the sequence on the structural drawings and were in any case an integral part of the gallery façade.

# (iii) Alteration to beam LT1 and addition of beam HB1 to Level 2 slab edge

# Regarding the alteration of the beam LT1 on Level 2, Tivendale asserted that it was altered because it was fixed to the gutter beam in the area. HB1 was an entirely new beam which had to be added to the terrace area of apartment no. 10, subsequent to the alteration of beam LT1, as this situation was apparently not allowed for in the structural steel drawings. In his original witness statement, Tivendale claimed that the draftsmen were delayed by one day while the approved drawings were revised and the other drawings “were put to one side”. During cross-examination, Tivendale admitted that his claim for one day was based upon the extra time it took to alter the drawings; it was not based upon a delay because the shop drawings could not proceed. He said: “It was not specifically at that time… [b]ut at some stage these drawings had to be revised”. It appears, therefore, that Tivendale’s statement that “this delayed the draftsmen by 1 day whilst these approved drawings were revised…” is not correct. There is no specific delay which can be pointed to.

# (iv) Alteration to main set-out dimensions

# With regard to the alteration of the main set-out dimensions, Tivendale asserted that Sopov gave him verbal instructions to cut the concrete edge of the level two slab 1550mm from Grid Line 2, thus altering the set-out dimensions for the gallery face steel. He asserted that it was later altered again by the superintendent’s direction SA07 dated 6 August 1999. During cross-examination, Tivendale confirmed that Sopov’s instruction could not be found in writing, Sopov had denied giving the instruction. Mr Magee put it to Tivendale that, in any case, the concrete cutting did not cause a delay to practical completion. Tivendale said that it did because the structural draftspeople had to make changes which in turn impacted on the manufacturing, therefore causing delays in installation. The question here is whether these alterations stopped work on-site, and caused delays to the critical works?

# In the Boilerhouse 1 program, Tivendale asserted that the gallery façade steel was not originally a “critical” item. However he claimed that this item became critical because it was not installed in time and therefore “fell into the critical path”. Tivendale said that the gallery façade steel should have been included from the beginning as a critical item because it “held up the roof”. Degenhardt and Jeffery both said that the five day delay could not be claimed because it was not on the program, and was not considered “critical path” at this stage (about August 1999). Tivendale’s approach in relation to the gallery façade steelwork can be contrasted with his earlier assertions where he stated that the only items which were on the critical path were those which were stated in the drawings, i.e. those which were in the “sequence”. In my opinion, the project manager was clearly taking conflicting positions on what was or was not on the “critical path”.

# Stage 3 (or “Item 3”) of EOT 4: Level 3 roof columns and roof beams and the fascia trusses and plant platform

# Tivendale asserted that the critical issues with respect to the delays for Stage 3 were in summary as follows: (i) delays to set-down drawings; (ii) alteration to set-down drawings; (iii) mansard roof connection details; (iv) delay due to reversal of beams; (v) extra columns to beams 97A and 99A; and (vi) the removal and replacement of beam 3B2.  According to Tivendale, Kane claimed a delay of 33 days overall for this particular stage.

# (i) - (iii) Delays and Alterations to the set-down drawings including revision of mansard roof connection details

# For these three details of Stage 3 of EOT 4, Tivendale said that Kane claimed a total delay of 10 days (33 days claimed overall for Stage 3 of EOT 4). During cross-examination, Tivendale was questioned on his claim that the constant changing of instructions emerging from the superintendent and Keith Long from Keith Long & Associates (“KLA”) regarding the step-downs to the level 3 balconies frustrated the draftsperson (and subsequently construction work), for a period of eight days (an additional two days was claimed for revision of the drawings for the mansard roof connection details on level 2). The defendants, on the other hand, claimed that the instructions were in fact on the contract documents and drawings, and that if there was any delay, that Kane should shoulder the responsibility for that and all the other delays claimed for this third stage of EOT 4. This was the essence of the argument between the two parties on these points. For instance, Mr Magee put it to the witness that: “… this whole episode of 33 days was commenced, maintained and finished by your complete inability to read drawings”. Mr Magee put it to the witness that he simply had not read the drawings correctly and that all the relevant information was before him. The witness denied the allegation.

# (iv) – (vi) Delay due to reversal of beams, extra columns and removal and replacement of beams

# The points relevant to the actual installation and construction work performed on the project that Tivendale categorised as Stage 3 of EOT 4 centred around changes to the contract drawings which delayed on-site work on the one hand (as contended by the plaintiff) and the argument that delays on-site had to do with the builder’s own ineffective co-ordination of the sub-contractors on the other (as contended by the defendants). According to Tivendale, Kane claimed 33 days delay overall for Stage 3 of EOT 4, of which approximately 23 days of the claimed delay is relevant to these points.

# In fact, it appears the defendants were suggesting that Kane had invented much of their claim in relation to EOT 4 (and not just Stage 3 of EOT 4) in order to cover costs due to poor programming by Kane and difficulties with their sub-contractors. Particular reference was made to Kane’s problems with the sub-contractor DVP, which lagged in bringing the steel, and whose staff apparently “didn’t show” at crucial points. During cross-examination, Tivendale was taken to a document dated 17 November 1999 wherein Skarajew requested from DVP “a program for completion of the structural steel of this project. This is required immediately to enable us to coordinate other trades around your work.” Tivendale explained this as reflecting Skarajew’s difficult position, stating that he was “stuck in the middle of all these delays and… all the EOTs we are claiming”.

# Nevertheless, Skarajew made some strong complaints about DVP Engineering, Pty Ltd. Tivendale was also taken to a document, dated 4 December 1999, in which Skarajew wrote to DVP – “none of your workers [are] on-site and they are required urgently” and “your lack of labour today is totally unacceptable and we require you to force back today to carry out the above work immediately.” Rather than being the cause of delays in shop drawings (as contended by the plaintiff), Mr Magee inferred that the delays were the result of DVP having “a very full order book around …the last quarter of 1999, and they didn’t have enough men to service their jobs”. Tivendale acknowledged that DVP was working on Fitzroy Town Hall at this time, as well as other Kane projects and projects with other builders.

# In response to the defendants’ claims that the delays were really the result of Kane’s poor co-ordination of the trades as well as problems with its sub-contractors, Tivendale stated, during re-examination, that the days DVP were not on-site – such as 15 December 1999 and 21 December 1999 – were not “critical” points in time as the defendants suggested. Rather, he stated that they were days on which the overall progress of the builder’s work was not affected by their absence and not the subject of EOT claims made by Kane.

# Stage 4 (or “Item 4”) of EOT 4

# According to Tivendale, the critical issues in relation to the delays to Stage 4 (Level 3 roof columns and roof beams) were discrepancies in the brick parapet; and a query about whether the parapet was too low. The plaintiff essentially argued (once more) that there were discrepancies in the contract drawings and that this delayed them from the critical path of the project works. Once again also, the defendants argued that the reasons for delay were not the major changes to the shop drawings ordered by Sopov or the superintendent; rather, the delays were “made up” by Tivendale to cover costs lost as a result of poor planning. For instance, during cross-examination, Tivendale admitted to the fact that the Alucobond sub-contractor, AAS, had not agreed to the Boilerhouse 1 program. The Boilerhouse 1 program had submitted that 40 days would be required to install the Alucobond, however, AAS had made a point of disagreeing with Tivendale’s estimation and had instead strongly recommended 60 days. Tivendale apparently disregarded the advice and AAS’ job was programed in at 40 days, leaving a shortfall of at least 20 days, since the installation of Alucobond in reality took longer than this. Tivendale maintained, however, that his program did not go to plan because of other reasons – not his or Kane’s incompetence in planning.

# During re-examination, Tivendale attempted to explain again that the 40 days were not as ambitious as AAS and the defendants were making out, saying that he tried to give AAS “more areas” on-site to work on so that they had more capacity and therefore would be able to do their job a lot more quickly. However, during cross-examination, Tivendale admitted that he was “wrong” in his estimate. Mr Magee suggested to Tivendale that, at that time, “the delays that were occurring… had nothing to do with shop drawings. They were just made up by you to cover the fact that AAS… had not accepted the purchase order, and had not agreed to the program.” Tivendale denied the suggestion.

# It is apparent, however, that there were problems with respect to the programming and planning of the works. Another sub-contractor, MTK, made similar complaints to the effect that Kane had not allowed sufficient time in the programming for each trade. For its part, the plaintiff maintained that delays claimed were the result of contractual discrepancies which had flow-on effects for the rest of the project.

# Extension of Time Claim 5

# EOT Claim 5 was not the subject of argument between the parties - 2.5 days allowed by the defendants before the commencement of trial.

# Extension of Time Claim 6

# EOT Claim 6, however, was a different matter. There were six items claimed by Kane for which the defendants accepted no responsibility, though Tivendale asserted that Kane claimed a total of 14 days and two hours. The superintendent approved two days and six hours of the claim.

# With regard to item 1 of the claim, Kane claimed that weather delayed the critical path of the works for two days and six hours on a number of days in November and December 1999. The superintendent approved two days and two hours, with one day concurrent with industrial action. The defendants, however, approved nil.

# With regard to the second item of EOT 6, Kane claimed five days. One day was for a state-wide strike; four days for a “union-enforced” shutdown on 23 December 1999 and 5 - 7 January 2000. The superintendent allowed one day, concurrent with one day delay as a result of the weather, however, he rejected the further claim for four days from 23 December 1999, saying that these days were "non-working" (holiday) days and therefore no delay costs could be claimed. The defendants, in their amended defence and counterclaim, denied all five days, including 15 December 1999, the date of the state-wide strike.

# At trial, both Mr Magee for the defendants and Mr Digby for the plaintiff agreed that the only dispute with respect to industrial action is how it was to be treated under the contract.

# For Item 3 of EOT 6, Tivendale claimed that Beam 3B26 had to be removed on 19 November 1999 and worked on off-site, and subsequently returned on 23 November 1999. Kane claimed that the critical path was delayed between these two dates since it was a critical path item. The superintendent rejected the claim in SA155, dated 8 May 2000, on the basis that the critical path at the time was with regard to the fascia trusses and other off-site activities. However, as Tivendale pointed out in his original witness statement, the fascia trusses were in fact supported by structural steel and was therefore a critical path item. Nevertheless, the question still remains as to whether Kane was necessarily delayed from the critical path by two days, or any time at all, as a result of the removal and reinstallation of Beam 3B26.

# Item 4 of EOT 6 was in relation to the installation of extra purlins and cleats. Kane claimed delay for these as apparently they were necessary and were not shown on the structural drawings. According to Tivendale, the extra work resulted in a delay to the “critical path” as the roofing sub-contractors were prevented from commencing work until these tasks were done. Kane claimed one day and four hours for Item 4. However, for the same reasons given in Item 3, the superintendent rejected them, on the basis that the critical path was the fascia trusses and other off-site activities.

# With regard to item 5 of EOT 6, according to Tivendale, Kane noted that the roof plant platform in the contract drawings was not large enough and had to be subsequently re-designed and re-drawn. The contractor claimed four hours for the extra time taken to install the platform as the newly drawn version was twice the size as previously. Tivendale arrived at the figure of four hours by estimating the excess amount of time it would have taken to install the original platform. However, Jeffery rejected Item 5 of EOT 6 for the same reason that he did for Items 3 and 4, namely, that the critical path was at that time stated to be in relation to the fascia trusses and other off-site activities.

# According to Tivendale, Kane claimed five days for the sixth item in EOT 6. Between 1 and 21 December 1999, Tivendale stated that Kane delayed five days to install ply, as instructed to do by SA23, since there was a discrepancy in the documents. Tivendale said that the Boilerhouse 3 program stated that the level 3 flooring was critical path, so the delay was therefore a valid one. The superintendent denied the claim in SA157 on the ground that these were contract works. During the witness’ cross-examination, Mr Magee suggested there was another reason why EOT 6 could not be granted, namely, because there were “concurrent delays”.

# Extension of Time Claim 7

# Tivendale stated that Kane claimed seven days and one hour for EOT 7. The entire claim was denied by the superintendent and the defendants. Item 1 of EOT 7 was with regard to the floor wastes in the laundry areas, later the subject of a claim that the wastes were less than the required Australian standard. Tivendale claimed that the Clements Consulting Group, under instructions from the defendants to provide advice on the hydraulics aspects of the project, initially advised them not to install the wastes as they were not required. Tivendale gave evidence that the superintendent subsequently reversed this decision and instructed them, in SA158 dated 12 January 2000, to install the wastes. Kane therefore issued a notice of delay six days later advising that Kane would be submitting an EOT claim.

# During cross-examination, Mr Magee suggested that Kane knew all along that they had to install the wastes, pursuant to the Building Code of Australia – but that Clements Consulting Group told them they “might be able to get [a]round” not installing them. This was denied by Tivendale.

# In my opinion, it is fairly clear that Kane was initially advised, by expert hydraulics consultants, that floor wastes were simply not required – and it was for this reason that they were not factored into the original schedule or program.

# With regard to Item 2 of EOT 7, Kane was required to install plywood backing to level 3 areas (this is to be distinguished from Item 6 of EOT6 which required ply backing to the quietel) as installation of plywood backing was not in the original contract drawings. Kane claimed an extension of 18 hours for delays encountered to the critical path, namely to cement and floor sheeting to the third floor. The superintendent, in SA155, refused the claim on the grounds that these were “contract works”.

# Item 3 of EOT 7 was relevant to the mechanical penetrations. Kane claimed that completion of the penetrations to level 2 delayed completion of the ceiling rough works, which were required before the ceiling and internal walls could be installed. Kane claimed four hours; but the superintendent rejected the claim on the basis that these were contract works.

# Counsel for the defendants suggested that Kane always knew it had to install the ducts, therefore they should have factored this in, even if they were not shown on the mechanical drawings. Tivendale rejected this suggestion, saying, if it was not shown, then it was not factored in.

# Extension of Time Claim 8

# According to Tivendale, Kane claimed 15 days and three hours for EOT 8. This extension of time claim is comprised of seven items, four of which are relevant to industrial action claims and “inclement weather”.

# Item 2 of EOT 8 is a claim by Kane for alterations made to the steel, pursuant to the superintendent’s direction SA52. Kane claims that the alterations delayed the installation of the ceiling and internal walls. The superintendent rejected this claim on the ground that the work performed was contract works.

# Item 3 of EOT 8 was linked to Item 1 of EOT 7, the floor wastes. Kane claimed it was delayed because it had to remove the already installed structure board and replace it with CFC board, as this was necessary to construct the fall required, pursuant to SA68. Kane therefore contended that it was prevented from completing the ceiling in time and that other trades could also not work at the same time due to the risk involved, thus causing further delay.

# Extension of Time Claim 9

# Tivendale stated that Kane claimed 16 days and 3.5 hours for EOT 9. Items 1 to 3 of EOT 9 were concerned with claims made by Kane for delays to the critical path as a result of weather conditions, industrial action taken by the workers on-site, as well as “consequential time” resulting from industrial action.

# For Item 4 of EOT 9, Kane claimed 12 days, with three of those days concurrent with the other three items (hence, nine days in total). Tivendale contended that the delay occurred as a result of the manufacture and installation of fire-rated boxes for down lights to the level 2 ceiling. Tivendale stated that the standard method of installation outlined in the contract documents for the recessed lights would have destroyed the fire rating, hence the downlights being manufactured and installed in fireboxes between 22 February and 8 March 2000, in accordance with SA080. Tivendale also stated that other works had to be stopped until the boxes were manufactured and installed. During cross-examination, Mr Magee said that Sopov’s position on the issue was that it was not the principals’ fault that the sprinklers were deleted from the contract documents which led to the delays in relation to the fire-proofing of the lights.

# Extension of Time Claim 10

# For EOT 10, Kane claimed four days and 4.8 hours. Both items were relevant to industrial action.

# Extension of Time Claim 11

# Kane claimed 12 days for EOT 11. Items 1 and 2 were with reference to weather conditions and industrial action. For item 3 of EOT 11, Tivendale claimed nine days delay to on-site work as a result of having to carry out extra works to install P50/P60, a type of ceiling edge pursuant to the superintendent’s Direction SA127 dated 14 April 2000. The direction apparently instructed that a fire-rated caulking be placed behind the P50/P60 to maintain the integrity of the fire-rated ceiling. Tivendale maintained that “this work was not required by the original drawings”.

# However, Mr Magee put it to Tivendale during cross-examination that this work was “always” required to be done by the builder under the contract. However Tivendale rejected this suggestion, stating that “[t]here was no detail provided of how these items were to be installed, and it was extra works”. Moreover, according to Tivendale, the installation of P60, as opposed to P50, proved to be “very difficult and time consuming”,  extending between 14 April 2000 and 31 May 2000. Tivendale asserted that the builder had to complete plasterboard works to level 2 ceilings and walls before other trades could follow, thereby preventing them from commencing other works on time.

Extension of Time Claim 12

# According to Tivendale, Kane claimed 13 days for this EOT. Items 1 and 2 related to Kane’s claim for “extra” time to install the P50/P60 and also extra works to design and fabricate support details for pivot doors. In relation to the pivot doors, Kane contended that numerous RFIs were issued requesting consideration of alternative details regarding the method of installation for the pivot floor boxes. However, in his original witness statement, Tivendale stated that the superintendent “failed to adequately respond” to these RFIs or provide workable instructions to allow Kane to continue with the works. The problem according to Tivendale was this: there was no design detail provided to Kane in relation to this work and detail should have been either provided in the contract documents or, failing that, by the architect upon request. Tivendale maintained that the defendants had not done either of these things.

# Item 3 was a claim for delay caused by the weather. The superintendent rejected this on the basis that all critical path activities were, at that point, “off-site”.

# Items 4 and 5 had to do with claims for delay as a result of industrial action.

Extension of Time Claim 13

# The builder claimed nine days and four hours delay for EOT 13. For item 1, Tivendale gave evidence that the delay resulted from extra works in designing and fabricating support details for the pivot doors, already referred to in item 1 of EOT 12 (levels 2 and 3). Kane claimed that further extensions were needed due to additional delays for these works, on various days between 1 June and 7 July 2000 (EOT 12 referred only to delays claimed for May 2000).

# Item 2 was a claim for delay of eight hours (or one day) caused by weather conditions. The superintendent rejected the claim on the basis that all critical path activities at that point were “off-site”.

# Items 3 and 4 had to do with claims for delay as a result of industrial action.

Extension of Time Claim 14

# Kane claimed five days and four hours for EOT 14. For item 1, Tivendale explained that further delays occurred in relation to the design and fabrication of the support details for the pivot doors (levels 2 and 3). This item is relevant to items 1 of both EOTs 12 and 13. They were rejected by the superintendent on the basis that they were "contract works" (SA215).

# As for Item 2 of EOT 14, Tivendale stated that the delay was caused by weather conditions. The superintendent rejected this claim in SA215 on the basis that all critical path activities at that point were “off-site” at the time.

# Item 3 of EOT 14 concerned Kane’s claim for a burst water main in Stanley Street. Tivendale stated that this delayed works on 7 July 2000 as the “site could not be occupied due to the absence of amenities”. Jeffery rejected that claim on the basis that all critical path activities at that point were “off-site”.

Extension of Time Claim 15

# The builder claimed five days and four hours delay for EOT 15. For the first item, Tivendale stated his opinion that delay occurred by reason of additional work performed to make and install a roof template, to ensure that the Level 3 Alucobond soffits were in one section. The contract drawings indicated the cladding would be installed in two sections, however Tivendale alleged they were subsequently instructed to investigate the installation in one section. Task 5 of Boilerhouse (external) 3 program indicated that the installation of the Alucobond to the gallery face was a critical path item. The installation of the template stalled AAS' fitting of the Alucobond to the gallery for the duration of the investigative works. However, the superintendent rejected the claim on the basis that these were "contract works" and that the works should not have impacted on the date for practical completion.

# Item 2 concerned claims for delay as a result of weather. Pursuant to the superintendent’s direction CAMC 16, dated 25 August 2000, this claim was rejected on the basis that the works were occurring outside the date for practical completion.

Extension of Time Claim 16

# The builder claimed five days and five hours for EOT 16. Item 1 was relevant to claims for delay as a result of industrial action. Item 2 of EOT 16 referred to the extra work necessary to install Alucobond soffits (level 3). This item is relevant to item 1 of EOT 15. Tivendale arrived at the figure of two days by estimating the difference in time if the Alucobond had been installed in two pieces as opposed to a single piece. It is therefore not a specific delay. Again, the superintendent rejected the claim on the basis that these were “contract works”. Moreover, Jeffery stated his opinion that the approved shop drawings required the soffit to be installed in two pieces instead of one, which was more efficient and would not have resulted in the delay claim.

Extension of Time Claim 17

# Kane claimed six days and four hours delay for EOT 17. The first item was relevant to industrial action. Item 2 of EOT 17 referred to delay caused by the weather. However, Jeffery rejected this claim on the ground that the works were occurring outside the date of completion, as extended.

Extension of Time Claim 18

# For the last EOT, Kane claimed 10 days. There was only one item in this EOT and it related to the suspension of works. According to Tivendale, the calendar showed that Kane was to undertake works between 18 September and 2 October 2000. However, the principals took the work out of Kane's hands. Kane claimed that this affected the installation of the Alucobond to the gallery face, a critical path activity. The notice was also not submitted to the defendants, since Kane was no longer working on the project.

Variations

# In his original witness statement, Tivendale stated that the contract administrator, Le Hy Ta, was primarily responsible for the preparation and submission of variation claims. However, in most instances, Tivendale reviewed and checked the claim prior to submission of variation claims to the superintendent. In this way, Tivendale was aware of and familiar with each variation claim submitted by Kane.

# The method used by Kane to calculate variations included the use of “builder’s standard rates” and “prices from sub-contractors”. An overheads and profit allowance of 10 per cent was claimed by Kane, since Tivendale thought that this was the margin agreed pursuant to the contractual negotiations held between the parties in June 1999. According to Tivendale, the architect Tony Hampton stated that he was prepared to pay Kane a margin of 10 per cent and that Sopov did not disagree or correct this statement. The defendants denied that they agreed to a variations margin of 10 per cent.

# It should be noted that for much of the time that Tivendale gave evidence, the parties were negotiating for settlement outside court on the issue of 164 separate variations. The parties finally agreed to a figure which was equivalent to 82 per cent of the plaintiff’s claim in relation to variations, not including interest or legal costs. Variations were also a matter referred to by counsel as more relevant to the examination of Le Hy Ta.

The Contract

# Tivendale was not involved in the tender process, however he was actively involved in negotiating the contract for Kane from approximately May 1999 until 20 August 1999. The claim for the amounts owed under the progress claims (under the contract) and the quantum meruit claim are, for obvious reasons, related.

# Show Cause Notices and Suspension of Works

# A notice to show cause was issued on 8 September 2000. The defendants purported to show cause by a second letter dated 11 September 2000, denying breach of contract and stating that payment for progress claim 14 was correct and that liquidated damages were deducted pursuant to cl.35.6 of the contract because “Kane Construction failed to achieve Practical Completion by 13th January 2000, the date that the Superintendent had granted extension of time for Practical Completion”.

# Following this, Kane suspended the works under the contract following the issuance of a notice to the defendants dated 18 September 2000. In response, the defendants issued another notice, “Principals Notice to Show Cause”, on 21 September 2000. The document alleged that Kane had in fact committed a breach by suspending the works and had failed to proceed with “due expedition and without delay” in breach of cl.33.1 of the contract. The plaintiff denied a contractual breach on their part, confirming the defendants’ breach (for failing to make payment in accordance with progress claim and for deducting liquidated damages from the certified amount) by letter on 28 September 2000.

Termination

# Tivendale stated that he was informed that the defendants had made recourse to Kane’s bank guarantees on the morning of 6 October 2000. He was also aware at that time of the letter sent by Kane’s solicitors, Deacons, to the defendants’ solicitor on 6 October, whereby Kane terminated the contract and alleged “repudiatory conduct” by the defendants.

# In the claim for breach of contract, the plaintiff alleged that, as the defendants had not dealt with the extension of time claims in a timely and “reasonable” manner, they were entitled to damages. The plaintiff repeatedly pointed out that the contract contained an express obligation to deal with the claims in a reasonable manner.

Deduction Variations

# The issue of deduction variations was comprehensively set out in the evidence of Le Hy Ta. The variation claims with which Tivendale had specific involvement are listed in his second reply witness statement (Tivendale’s third witness statement in this matter). Briefly, they are as follows:

  - Item 1.2, Hazardous Material Report

  - Item 1.4, Project Signboard

  - Item 1.5, Omission of Licensed Surveyor

  - Item 6.2, Steel Stud Framing

  - Item 9.13, Sadler Tiles over Particle Board

  - Item 13.1, Alucobond shop drawings

  - Item 14.1, Hardie Panel not factory sprayed

  - Item 16.6, Deletion of Window W/G12

  - Item 19.1, Plastering

  - Item 20.11, Tiles in the Gallery

  - Item 20.12, Waterproof membrane over existing concrete slab

  - Item 21.6, Polythene pipe in lieu of copper pipe in Apartments 1,2 and 3

  - Item 21.8, Remote Water Meters

  - Item 26.1, Building Size

# For each one of the deduction variations in this above list, Tivendale rejected the defendants’ claims (that Kane was not entitled to the variations) by using either one of the following two explanations: namely that either Kane had merely followed the instructions of the principal, his representatives or other authorities; or that at the time that the work was performed, no relevant complaint had been made to Kane explaining that the work was unsatisfactory.

Quantum Meruit Claim

# Kane claimed some $2.45 million for work performed, which remains unpaid. Further and alternatively, the plaintiff claimed the value and benefit that it said it had created for the defendants by reason of its performance. On the other hand, the defendants stated that the claim was based on a provision of the agreement as varied by the Act, and was invalid and/or of no effect in that it sought to increase the contract price.

# The defendants also alleged that Kane’s quantum meruit claim included claims for payment for defective work, rectification of defective work, rectification of work damaged by water ingress, and for costs incurred in relation to alleged set-out errors. The plaintiff rejected this submission in evidence. Partly in support of the plaintiff on this point, Tivendale made a third statement, his second reply witness statement in this matter.

Defective Works and Rectification Works

# Tivendale stated that, between March and September 2000, Kane attended to the rectification of defects by notifying the relevant sub-contractor and ensuring defective work was rectified in a “timely manner”. The defects list, composed by Glenn Skarajew and maintained from about March 2000, showed 86 reported defects items. Of the 86 reported defects listed on the 12 September 2000 defects list summary, Tivendale claimed that only eight were outstanding. This is in stark contrast to Jeffery’s witness statement which identified three categories of defects, equalling a total value of $617,200.

Rectification works Forming Part of Kane’s Quantum Meruit Claim

# During cross-examination, Mr Magee referred to the construction of the laundries without the floor wastes, which were also the subject of a claim made by the defendants that they were less than the required Australian Standard. Mr Magee suggested to Tivendale that Kane were taking shortcuts and that they were attempting to “get around” putting them in. This was rejected by Tivendale, however, who noted that at the time, Kane was under instructions from expert advisors, Clements Consulting Group (a hydraulics firm contracted by Sopov), not to install the floor wastes. In Tivendale’s opinion, therefore, the associated costs should have been borne by the defendants.

Rectification of the Stud Framing

# The wall rectification/studs issue formed part of the quantum meruit claim because, according to Kane, the original contract drawings did not provide for studs that were strong enough. Extra work had to be done, namely, ensuring that the studs were removed and then reinstalled with treated pine and weatherproof ply to prevent maintenance issues with the tiling.

# Counsel for Kane, Mr Digby, noted that Mr Magee had put it to Tivendale, or at least had made the comment during cross-examination, that the removal of the studs was the plaintiff’s responsibility or fault (namely, that Kane had inserted the “wrong” studs in the walls and that in fact Sopov had warned Kane about this very early on). However, Mr Digby noted that, despite the defendants’ emphasis on the point, this work was not the subject of any charge or claim made of the builder by the defendants. Tivendale stated that he provided a credit to Kane’s quantum meruit claim for the instances where the plumbing and electrical fixtures had to be removed to enable the noggins to be installed.

Rectification Work For Items Damaged by Water Ingress

# According to the defendants, rectification work for items damaged by water ingress, such as the removal and reinstallation of the plasterboard, was factored into Kane’s quantum meruit claim. However, during his evidence, Tivendale was given the opportunity to emphasise that the cost associated with this rectification work in fact did not form part of the quantum meruit claim. He noted that he himself had applied a credit for this against the quantum meruit claim.

Deductions/Credits Made to the Quantum Meruit Claim by Kane

# Tivendale stated that he had personally checked all of the components of Kane’s quantum meruit claim, including variations works, to identify the existence of other costs claimed by Kane which should be deducted from Kane’s quantum meruit claim, either because they were caused by Kane, or if for some other reason they may not be claimed. According to Tivendale’s calculations, the total deduction to Kane’s quantum meruit claim should be $70,065.

Deductions to the Quantum Meruit Claim Relevant to MTK

# Kane claimed the amounts which it paid directly to the plastering firm, MTK, the materials supplied to MTK, and the superannuation paid for MTK workers, as originally brought under the contract (under the progress claims). Failing this, Kane claimed that these amounts would fall under a quantum meruit claim. The original primary contract between Kane and MTK was for about $420,000. This increased to approximately $560,000 in value, which Kane claimed as part of the quantum meruit claim (representing the “cash out” payments made to MTK). Kane claimed that it has not been paid for the MTK works.

# During cross-examination and re-examination, Tivendale made it clear that payments for MTK materials were made by Kane because the sub-contractor was experiencing financial difficulties (and is now apparently no longer in existence). This was a purely financial decision by Kane as it would have cost the builder more to hire out another sub-contractor to complete the MTK works. Also, Tivendale asserted that replacing MTK with another plasterer would have caused an “out and out” one week delay to the project.

# The materials bought for MTK and the superannuation paid for MTK workers falling under the quantum meruit claim is as follows:

  - $31,000 (C+BUS Superannuation)

  - $176,000 (Boral)

  - $25,000 (the Atkar materials)

  - $12,000 (SJ Plastering)

  - $25,000 (Commercial Interiors)

  - $1,200 (Gisborne Plaster)

Other Deductions/Credits Applied

# Kane applied a credit against the quantum meruit claim for the removal of material in front of the steps near the office area. As well, in a letter dated 19 July 2000, MTK complained to Kane about replacing the fire-rated ceilings as a result of water damage. This was not charged to the principal and a credit was accordingly provided under the quantum meruit claim.

(2) FORSTER

Background

# The second witness for the plaintiff was William Jonathan Forster. Forster appeared in his capacity as the Executive Chairman of Kane. Forster said that he had been the Managing Director of Kane from 1973 until November 2001. Forster stated that Kane was a “medium sized/second tier commercial construction company engaged in a variety of work including commercial, institutional and residential work” of which Forster gave several examples including 4 Treasury Place, Melbourne ($14,000,000) and Raheen, Kew ($23,000,000).

Tender

# Forster said that Kane became aware of the Boilerhouse project on or about 10 March 1999 when Stacks Properties sent Kane a written invitation to tender. Kane subsequently submitted a tender on 8 April 1999 in the sum of $3,624,700; and on 17 May 1999, a revised tender was submitted in the sum of $3,474,000. Forster said that the revised sum reflected the negotiations between Sopov and Kane’s chief estimator at the time, Peter Cusack. Forster said that, by letter dated 20 May 1999, the defendants advised Kane that they had been successful in winning the tender.

Project

# Forster stated that he was familiar with the Boilerhouse project but did not have direct on-site involvement. He said that he received information through Kane’s monthly meetings of directors and, from time to time, from discussions with the project manager, Tivendale. Forster further stated that his “main direct involvement with the project relates to the pre-contractual negotiations from June 1999, the issuing of a notice of dispute by Kane in January 2000, and the period immediately prior to and subsequent to the termination of the contract”. Forster said that the Boilerhouse project was a “construct only project” wherein Kane had “no design functions or obligations”. Forster stated that he believed that the original Boilerhouse project program of 130 days was achievable.

Form of Contract and Role of the Superintendent and Architect

# Forster stated that the form of contract originally put forward by the principal was a JCC-D 1994 contract which “assumes that an architect will perform the role of Superintendent”. Forster said that Tivendale told him in a conversation in late May 1999 that Sopov wished to change the contract to an AS 2124 1992 contract and that Tivendale had told Sopov that Kane had no objection “provided that the commercial conditions were the same as those upon which Kane had tendered”. Forster said that Stacks forwarded the AS 2124 form of contract to Kane for signing by letter of 4 June 1999.

# Forster stated that, during May and June of 1999, he was advised by Tivendale and Cusack that negotiations with Sopov were progressing slowly and that he decided to become “more directly involved” in order to expedite the execution of the contract. Forster said that Kane received an unconditional acceptance of its tender on 20 May 1999 and, in about June 1999, established on the site in Collingwood.

# Forster said that, in about July 1999, Tivendale informed him that “he was finding it difficult to resolve the outstanding contractual issues with Sopov” and that there were issues about variations and delay cost provisions. Forster said that his concerns had been highlighted when he received a facsimile from Stacks on 19 July 1999 copying a letter from Slattery wherein they proposed their appointment as superintendent, and a subsequent facsimile on 20 July 1999 wherein Stacks informed Kane that Hampton had resigned as superintendent and that Slattery had been appointed effective from that date. Forster said that he spoke to Peter Slattery, the principal of Slattery, on about 21 July 1999, and expressed concern about the contract not being finalised, and further, that since Slattery was a “Construction Cost Consultant and Quantity Surveying organization” that he “did not think it likely [they could] adequately fulfil the role of design consultant”.

# Forster stated that Kane’s subsequent letter of 21 July 1999 set out their concerns about the proposed change in the form of contract and stated that they required an annexure to the contract to “reflect the conditions set out in the tender documents and the need for an experienced architect to be appointed to supervise the work”. Forster said that, further to Kane’s letter of 21 July 1999, a meeting was held at Slattery’s office on 23 July 1999 and attended by himself, Tivendale, Sopov and Jeffery. Forster stated that, at that meeting, he had said that “an architect needed to be involved in the project and in administering the contract” and that “Kane required the extension of time costs to mirror the provisions of JCC-D (without amendment), as this was part of the basis for [their] tender sum”. Forster further stated that, at the meeting, Jeffery indicated that “the arbitration provisions of the contract would require amendment to reflect the Domestic Building Contracts Act.”

# Forster stated that Kane received a letter from Slattery, dated 26 July 2000, wherein Jeffery set out the proposed dispute resolution process and suggested the amount in respect of delay costs; but that these were rejected by Kane by reply letter of the same date. Forster said that, on 5 August 1999, Jeffery requested particulars of Kane’s requirements with respect to the annexure to the AS 2124 form of contract “in relation to the appointment of an architect as Superintendent’s Representative” and that these were subsequently forwarded by letter dated 6 August 1999. Forster said that this letter stated that contracts must be exchanged by 11 August 1999, otherwise, Kane would cease work. Forster stated that, by faxed memo of 6 August 1999, Slattery confirmed acceptance of the annexure and that the contract was subsequently signed by Kane and the principal on 20 August 1999.

Compliance with the Domestic Building Contracts Act 1995

# Forster stated that he was aware that the Domestic Building Contracts Act 1995 would apply to the Boilerhouse project and he cited various Kane and Stacks’ communications referring to that fact. Forster stated that he “relied on the Principal and the Principal’s consultants who proposed and provided the Contracts to include all necessary amendments to ensure compliance with the Act”. Forster said that he had a “general awareness” of the Domestic Building Contracts Act, but no “detailed knowledge” about it, and that no-one at Kane had the responsibility of informing themselves about the Act.

# Forster said that he understood that if Kane did extra work on the project because of a variation, and/or if Kane was delayed in a way that entitled it to an extension of time, then “it would be paid the fair and reasonable cost of that extra work, and would be paid for compensable delay costs”. Forster further said that, if that was not the case, he would not “have allowed Kane to continue to undertake extra works on the project or go on with the works when Kane were being delayed, if [he] had been aware that the Principal did not intend to pay for extra work done by Kane in the nature of variations and/or did not intend to pay for compensable delay costs incurred by Kane”.

Progress of the Works

# Forster said that, following the execution of the contract, he was not involved in the day to day works on-site; but that Tivendale reported that the works were progressing slowly and that “Sopov was on the job continuously whereas the Superintendent was an infrequent visitor to the site”. Forster said that, following the resignation of Hampton, a replacement architect was not appointed until November 1999 and that he considered this was “in breach of clause 24 of the Contract”.

# Forster further stated that, based on Tivendale’s reports to him, he understood that “Sopov’s general response to any requests for information or clarifications or an extension of time was to seek suggestions from Kane and adopt a “sort it out yourself at no cost” approach rather than to give instructions”. Forster said that, between November 1999 and April 2000, the project experienced delays associated with industrial action that were “beyond the control of Kane”, and that it was not possible to complete the project by 10 December 1999. Forster said that this action affected all of Kane’s projects.

# During cross-examination, Forster conceded that at one point in early 2000 he had ordered a lock-out of workers and that this delay was therefore within Kane’s control. Forster also said that Kane had claimed for the delays associated with the lock-out and that he believed that they were claimable under the contract.

# Forster stated that, in January 2000, he was informed by Tivendale that there were numerous variations that had not been approved by the superintendent. Forster said that Tivendale informed him that in many cases there had been no response from the superintendent and that this situation became intolerable, leading to Kane eventually issuing a notice of dispute to the principals on 21 January 2000. Forster said that this notice set out “the disputes between Kane and the Principals including in respect of the valuation of variations, extensions of time to the Date for Practical Completion and delay costs”. Forster stated that these disputes were not resolved and that Kane subsequently commenced proceedings in the Victorian Civil and Administrative Tribunal (“VCAT”), with the points of claim being filed on or about 4 July 2000.

Principal’s Repudiation

# Forster stated that, on or about 1 August 2000, Kane’s contract administrator, Le Hy Ta, informed him that Kane had submitted progress claim number 14, totalling $1,216,546.64, to the superintendent. Forster said that, of that sum, only $132,618 (namely $120,000 plus GST) was paid to Kane on 28 August 2000. Forster further stated that certificate number 14, dated 23 August 2000, certified the amount of $340,562 as payable by the principals to Kane, and that subsequently, Kane issued a tax invoice for that sum (plus GST), namely $374,618.20, on 24 August 2000. Forster noted that cl.42.1 of the contract stated that a certificate must be issued within 14 days of the progress claim being submitted to the superintendent.

# Forster summarised the ambit of Kane’s dispute with the principals as being, firstly, a claim by Kane for variation claims NPV 1 to NPV 108 for $396,268, of which $94,268 had been approved by the superintendent; and extension of time claims for 139.13 days and claimed delay costs of $590,795.50, of which 11.75 days and $5,675 had been approved by the superintendent.

# Forster stated that, by letter dated 28 August 2000, Kane was informed by the principals that they were deducting liquidated damages of $220,000 from the certified sum of $340,562. Forster said that he regarded the principals’ actions as indicative of them not abiding by the contract; however he said that he was not sure if Kane would have lifted the subsequent suspension if the principals had paid the amount of liquidated damages deducted from progress claim 14.

# Forster said that, on or about 1 September 2000, Kane submitted progress claim 15 to the superintendent seeking $1,231,742.91. Forster said that he was “the person within Kane who was making the decision in relation to what step Kane took under its Contract”, and that subsequently Kane issued a notice to the principals, dated 8 September 2000, requiring them under cl.44 of the contract to show cause why Kane should not exercise its rights under cl.44.9.

# Forster said that the principals responded, by letter of 11 September 2000, that stated, among other things, that the payment of $132,618 for progress claim 14 was “the correct sum under clause 42.1, and clause 35.6 of the AS 2124 contract agreement”. Forster said that Kane responded to the principals’ letter, by way of letter dated 13 September 2000, that stated that Kane maintained its allegation that “the principals have committed a breach of contract”.

# Forster said that the superintendent issued certificate 15 on 14 September 2000, certifying that the sum of $220,800.00 was payable by the principals to Kane; and that this amount had not been paid despite a request for payment as conveyed by way of letter dated 5 October 2000 from Kane’s solicitors to the principals’ solicitors at the time. Forster said that certificate 15 included no deduction for liquidated damages and that it also stated that the sum of $2,989,350.00 had previously been certified (including the sum of $340,562.00 as certified under certificate 14).

# Forster said that the principals responded by way of letter on 15 September 2000. However, Forster said that he did not believe that the response adequately responded to Kane’s notice to show cause and that, subsequently, Kane issued a notice of suspension and suspended the whole of the work under the contract on 18 September 2000. Forster said that the principals wrote to Kane, by way of letter dated 21 September 2000, alleging, among other things, that Kane was in breach of contract; and that Kane responded, by way of letter dated 28 September 2000, stating that it had validly suspended the work but that it remained willing to continue if the principals “observe[d] their payment obligations”.

# Forster said that he was concerned about the security of Kane’s plant, equipment and material that remained on-site, and that, on or about 29 and 30 September 2000, Kane commenced removing it and advised the principals accordingly by way of letter dated 5 October 2000. Forster said that Kane had received a letter dated 2 October 2000 from the principals’ solicitors stating that this removal was effected without the consent required by cl.29.2 of the contract.

# In cross-examination, it was suggested to Forster, by counsel for the defendants, that Kane removed the plant, equipment and material in anticipation of the principals exercising their rights under cl.44.4 of the contract; however Forster did not concede that point. Forster also rejected the suggestion put by counsel for the defendants that “this whole removal and the way it was done was done in a way to cause maximum financial loss [to the defendants]”.

# Counsel for the defendants further suggested to Forster that Kane had made up its mind to get out of the contract and had asked its lawyers how best to do that. Forster rejected that suggestion and said that his view was that “Sopov was trying to get out of the contract, take our $5 million-worth of work and keep it for $2.7 million”. Forster said that he believed that the contract was still on foot at 28 September 2000, albeit a “shaky foot”. Forster stated that while, by early October 2000, Kane had completed approximately 95 per cent of the works, it had only been paid for less than 60 per cent.

# Forster said that, around 11:40am on 6 October 2000, Kane received two revised certificates 14 and 15 from the superintendent wherein liquidated damages were deducted, hence making Forster suspicious about the possibility of the principals exercising “undue and improper influence [on Jeffery]” to issue the revised certificates. Forster said that, in about January 2000, Jeffery had told him that he “was not prepared, and would not make, any decisions concerning [the] contract, without the approval of Mr Sopov”; and that this discussion was in the context of the “failure to make decisions in relation to our time claims and our variation claims”. In cross-examination by counsel for the defendants, Forster said that it had not been his intention, for the purpose of litigation, to prejudice Mr Jeffery as someone not prepared to be independent; rather it simply recorded his view at the time.

# Forster further said that, at about 11:45am on 6 October 2000, he was informed by Mr Peter Rice of the National Australia Bank that the principals’ solicitor had “called upon and cashed the bank guarantees in the sum of $173,700 that were provided by Kane under the Contract”. In cross-examination by counsel for the defendants, Forster conceded that he had phoned Rice, but that Rice had told him that “My hands are tied”. However, Forster denied counsel’s suggestion that this telephone conversation was deliberately omitted from Forster’s witness statement, as was the attempt by Kane’s solicitors to seek an injunction against the bank guarantees being cashed. In his testimony, Forster also conceded that Rice had rang before the guarantees were cashed, and that, hence, his witness statement could be perceived as contradictory.

# Forster said that the principals did not give Kane any notice that they intended to cash the bank guarantees as required by cl.5 of the contract. Forster further set out his understanding of the bank guarantees, wherein he stated that the principals had no recourse to take the action they did. Forster said that he considered the principals’ actions to be “aggressive and unlawful” and that this consequently “left [him] in no doubt that Kane’s only practical and sensible course of action at that stage was to accept the principals’ repudiation of the contract”, which Kane subsequently did by way of letter dated 6 October 2000 terminating the contract.

Changes to the Contract Price and Payment for Work Done

# Forster said that Kane would not have entered into the contract if it was not to be paid for extra works in the nature of variations and if it thought that the principals would rely on the Domestic Building Contracts Act to avoid payment. Forster further stated that at no time prior to the execution of the contract, or during the works, did the principals inform Kane that such payments would not be made or refer to any rights they might have under ss.16 or 33 of the Domestic Building Contracts Act.

# Forster said that the completed value of the Boilerhouse project (“as valued on behalf of the Principals by PBB Valuations in July 2000”) was $7,740,000, and that “the Principals had derived a benefit from the works done by Kane”. Forster further said that, given this value resulting for the principals, he thought that it was “most unfair for Kane not to retain and recover its costs of performing the works and to be prejudiced or restricted by virtue of section 16, 33 or any other section of the Act”.

Quantum Meruit Claim

# Forster said that the unpaid portion of the costs incurred by Kane was $2,452,253.01, and that the recording and derivation of those costs was set out in the statements of Lucas and Le Hy Ta. Forster further said that Kane’s claim of an overhead and profit component of 10 per cent in the sum of $474,691.18 was “a reasonable margin” and consistent with their industry practice.

Contractual Claim

# Forster said that Kane claimed $1,736,728 as the sum owing to it under the contract as at 6 October 2000. Forster further stated that Kane claimed approximately $440,661.16 as variation costs (as set out in the statement of Le Hy Ta and independently verified by Mr Laurie Thomas of WT Partnership (“WTP”)); and delay costs of approximately $768,000 (as set out in the statement of Tivendale).

(3) LUCAS

Background

# The third witness for the plaintiff was Sidney Robert Stephen Lucas who appeared in his capacity as the Finance Director of Kane. His responsibility was to ensure that appropriate and accurate records were maintained that showed Kane’s financial position and the results of Kane’s operations for the period reported on. He was also responsible for all accounting services. In his witness statement, Lucas explained that “commitment cost accounting” figures were used for forecasting and monitoring job performance for management purposes.

# Lucas was called by the plaintiff as a witness to prove the fair and reasonable cost of the job undertaken by Kane, in particular, by highlighting that the financial records of the plaintiff’s money claims were valid. Use of the Jobpac computer cost recording system was central to this process.

Jobpac

# Lucas said that Kane had used an integrated computerised software system called “Jobpac” since 1994. Lucas said that it was specifically designed for use by a construction business in that it enabled the user to establish the revenue and costs that relate to specific projects and record them on a job-by-job basis. With Jobpac, the overall financial position of Kane was readily apparent and ascertainable at any particular time or for any particular period. It recorded all direct costs incurred by Kane (liabilities, all payments made including wages, the raising of amounts receivable and the processing of receipts) but not indirect expenses.

# Lucas said that “liabilities incurred” were recorded under three categories: capital expenditure, indirect expenses and direct expenses. Lucas described how suppliers’ invoices were forwarded to the contract administrator for verification and approval (which at times involved consultation with the project/site manager). If approved, the contract administrator entered the relevant details of the invoice onto Jobpac. Similarly, Lucas stated that the sub-contractors’ claims had to be approved by the contract administrator and that the amount was then entered onto Jobpac via an “authorisation for payment form”. Lucas did not appear to address the question of what happened when invoices or sub-contractors’ claims were not approved.

# Lucas asserted that all information provided in the Jobpac reports identified all costs incurred and payments made by Kane on the Boilerhouse project and was the basis upon which claims in these proceedings had been made. Further, Lucas said that the information was of the kind that was regularly entered and made available in the ordinary course of activities. Lucas said that, to the best of his knowledge, the Jobpac system at Kane operated properly throughout the entire period in question (1 May 1999 – 30 April 2003).

# Lucas said that it was the practice of Kane that project costs and payments be reviewed on a quarterly basis by project managers and/or contract administrators. In this case, Tivendale and Le Hy Ta informed Lucas that they carried out such reviews in relation to the Boilerhouse project, ascertaining costs incurred and payments made by Kane. Lucas said that an independent audit was carried out annually.

Payment

# Lucas stated that payments by Kane were usually made by cheque. Sometimes payment was made by credit card or electronic funds transfer. All payments were recorded in Jobpac, the latter two as “dummy cheques”. Lucas said that approved invoices were accessed and paid according to the credit terms of the supplier/sub-contractor. Sometimes a single cheque was issued to cover a number of invoices or claims across a range of projects. All direct expenses were itemised on the Accounts Payable Enquiry Transaction Report printed on 29 April 2003.

Indirect Expenses and Profit

# Lucas said that the indirect expenses and profit, for which Kane claimed 10 per cent, were itemised in his witness statement. Lucas said that these expenses were not recorded on a project specific basis, as the expenses didn’t relate to specific jobs. He said that they were entered onto the Jobpac system under “General Ledger”, and were set out in Kane’s financial reports as “Administration and Marketing Expenses”. Indirect expenses were charged to the job within the “on-costs” of the direct labour costs, and, in the case of the Boilerhouse project, these amounted to approximately 30 per cent of Kane’s direct labour charge for the duration of that project.

# Lucas provided a summary of Kane’s trading and profit and loss accounts for the 1998/99, 1999/00 and 2000/01 financial years. The average net profit and indirect expenses, as a percentage of total income, was 13 per cent. Lucas said that the 10 per cent claimed by Kane in this proceeding was fair and reasonable, as it was lower than the average percentage achieved by Kane over the stated period.

Structural Steel Works

# The cross-examination of Lucas was focussed around a Kane document itemising variations approved for structural steel works. Lucas agreed that Jobpac recorded the variations which DVP had requested, including those that had been approved and those awaiting approval. Lucas further agreed that Jobpac did, and should, record all the transactions between DVP and Kane in relation to this project.

Demolished Roof

# Lucas said that he was not aware of the fact that Mr Dordevic was recompensed for demolishing a roof by an off-set of steel. He stated that it was possible that such an ad hoc transaction could appear in the Jobpac system (if a financial value was placed on the steel), but in this case he was not aware of the arrangement having been recorded. Lucas denied that this reflected an inaccurate record of Boilerhouse transactions as long as the net effect remained the same, that is, if in the present case the transaction had been recorded as a credit for the steel, and the steel had then been brought in as a positive variation against the sub-contract. In that case, Lucas said that the records on Jobpac would remain identical.

Variations

# Lucas agreed that, in so far as such transactions amounted to a “barter”, they did not show up on the Jobpac system if they were not recorded. Instead, one could expect to find the transaction recorded as a variation (under “details”) issued to that sub-contractor for the particular item. By way of example, Lucas pointed to the variations in crane hire, which in some cases would have been additional crane hire that Kane had agreed to pay for on credit, for which the sub-contractor would then be charged. Lucas was only able to point to two negative variations on the record for structural steel works.

(4) ISAACSON

Background

# Antony Peter Grant Isaacson was the fourth witness for the plaintiff. Isaacson’s statement was essentially made with regard to paragraphs 63 and 64 of Sopov’s statement and paragraphs 19, 20 and 21 of Jeffery’s statement. Isaacson stated that he had been a director of Kane since 1999 and that he was appointed Managing Director of Kane on 15 May 2001. Prior to his appointment as Managing Director, Isaacson said that he had been the Construction Director for Kane. Isaacson stated that he had been involved in the property, building and construction industry for approximately 24 years.

Contract Documentation, EOT Claims and Variation Claims

# Isaacson stated that, in about mid February 2000, he received a call from Sopov requesting a discussion about the progress of the Boilerhouse project, and that a meeting subsequently occurred in Kane’s office on 14 February 2000. Isaacson said that he was “kept informed generally about the progress of the Boilerhouse project” and that he shared the concerns of Kane personnel that “the project was not well documented [and] that there was a detrimentally high degree of involvement from the principal that impeded Kane in completing the works”; and that furthermore, “there had been a large scale rejection of what Kane considered were justifiable claims for extensions of time (and delays costs) and variations claims”.

# Isaacson said that Tivendale had reported his “serious concerns about the adequacy of the contract documentation” and that “Kane was continually getting bogged down by the necessity of having to submit RFIs … in an endeavour to ascertain the precise nature of work required”. Isaacson said that both Tivendale and Le Hy Ta both reported to him about Kane’s submission of EOT claims and variations claims that had not been approved.

Dissatisfaction of Sopov with Kane Personnel and Performance

# Isaacson stated that there was a meeting on 14 February 2000 attended by him, Sopov and Jeffery, and for a short time, Tivendale. Isaacson stated that, at this meeting, Sopov voiced concerns about “the quality of Kane personnel and their performance on-site”. Isaacson said that he recalled a discussion about Kane’s plastering and about the Alucobond shop drawings, and that these matters were subsequently followed up with Spencer Wilson, a representative of AAS. However, Isaacson said that he did not recall any other specific issues being raised or discussed at the meeting.

# Isaacson said that he rejected Sopov’s concerns about Kane’s personnel and performance and that he voiced his own concerns about Sopov’s over-involvement in the project. Isaacson further stated that he told Sopov that he would “continue to maintain an interest in the project”.

Skarajew’s Experience

# Isaacson also said that, at the meeting on 14 February 2000, he did not say that Skarajew was inexperienced. Rather, Isaacson said that he was aware of Skarajew’s significant experience (including in multi-unit residential construction) when first hiring him.

Extra Resources Provided by Kane

# Isaacson said that, following the 14 February 2000 meeting, he had decided that “Kane should commit additional staff to the project in an endeavour to improve the progress of the works” and he said that a further meeting was attended by him, Sopov, Jeffery and Tivendale on 29 February 2000.

# Isaacson said that, in about March 2000, Kane appointed “Roger Swarbrick to be the foreman responsible for the façade” and for “Alexei Simm to replace Tivendale while he was on leave and to assist him upon his return”. Isaacson said that John Chambers later filled the role of assisting Tivendale, and that “David Crews was appointed as leading hand/carpenter from March 2000”.

# Isaacson said that Kane “committed additional resources to the project in about late February or early March 2000” and that he was aware that “Kane and [its] sub-contractors worked significant week-day overtime” and that there “were only ten Saturdays between June 1999 and September 2000 when there was no work on-site”.

EOT Claims

# Isaacson said that, by the end of February 2000, Kane had lodged EOT claims 1, 2, 3 and 4 which claimed in excess of 50 days of time extensions for delays Kane considered it had not caused.

Criticism of Kane’s Approach, Personnel or Progress by Jeffery

# Isaacson stated that he rejected Jeffery’s assertion that, prior to the meetings on 14 and 29 February 2000, Kane’s approach consisted of “a lack of progress, coordination, cooperation and communication ultimately leading to the builder abandoning the site in October 2000”. Isaacson said that he attended the site approximately once per month from March 2000 “until Kane suspended work on 18 September 2000” and that Tivendale “continued to report to [him] about the progress of the works on-site at least on a weekly basis”. Isaacson said that he did “not recall Jeffery making any adverse statements about Kane personnel or progress at the 14 or 29 February 2000 meetings” and that to the “best of [his] recollection Jeffery did not state to [him], after 29 February 2000, that he was dissatisfied with the manner in which Kane was performing the works at the Boilerhouse project”.

(5) SKARAJEW

Background

# Mr Glenn Skarajew was not called as a witness. Counsel agreed to rely on his witness statement and reply witness statement. In his statement, Skarajew said that he was employed as site foreman on the Boilerhouse project by Kane from October 1999 to December 2000. During this time, Skarajew said that he was on-site daily for at least eight hours. Prior to this, Skarajew stated that his experience extended to two commercial/residential development projects in Abbotsford and Cairns (worth $10million and $5million respectively). In his reply witness statement, Skarajew rejected the suggestion by Sopov that he was inexperienced when he worked as site foreman on the Boilerhouse project. Skarajew said that he considered that his prior experience in the building industry was extensive.

Skarajew’s Role

# Skarajew described his role in the Boilerhouse project as comprising communication, co-ordination, management of day-to-day activities, handling/forwarding labour time sheets, informing Kane of site activities (regular contact with Le Hy Ta and Tivendale) and attending site meetings. Skarajew said that he was also responsible for maintaining a record of site activities through Kane’s foreman’s diary and maintaining time sheets for the project. Skarajew said that he worked in close proximity with Tivendale who attended the site on a regular basis (two to three times per week from October 1999 to March 2000 and daily from March 2000). Skarajew said that he was responsible for reporting to Tivendale on delays and potential costs. He said that he also reported communications that he had with Sopov, Jeffery or Irving.

# In his reply witness statement, Skarajew rejected Sopov’s statement that there was “poor co-ordination of sub-contractors and the excessive use of day labour”. Skarajew said that he was unable to respond to any specific allegation, since no details or examples were provided. Skarajew said that, generally, his on-site contractors were efficiently coordinated, and that he exercised judgement as to when Kane engaged day labour.

# In his statement, Skarajew further rejected Sopov’s statement that there was an inadequate handover between Omond and Skarajew. Skarajew said that, prior to commencing as site foreman on 1 October 1999, he had looked through the entire set of contract drawings and specifications. Skarajew said that, on 1 October 1999, he spent the working day on-site with Omond. He said that for part of the day, Tivendale was present to explain the project in general terms. Skarajew said that by that stage Kane had been on-site for approximately four and a half months.

# Skarajew said that at no stage during the course of the Boilerhouse project did Sopov or Jeffery question his competence as site foreman; or raise in his presence any suggestion that work was poorly coordinated, or that Kane was using too much day labour. Moreover, Skarajew said that he had a very detailed knowledge and appreciation of the contract drawings and specifications. Skarajew said that the contract documentation was deficient, including ambiguities and/or discrepancies between drawings and specifications and insufficient information on contract drawings. Skarajew said that these deficiencies resulted in the high number of RFIs and general delay. Skarajew said that he considered the responses to the RFIs by Jeffery to be inadequate.

Delay

# Skarajew stated that Sopov was on-site frequently. He suggested that the regular conversations that he had with Sopov in relation to design and construction issues impacted on his work because it detracted from the time he could be spending supervising site issues. Skarajew stated that he spent one to two hours per day with Sopov discussing the progress of works. This was unusual and unnecessary, given that the common practice was to have the principals attend site meetings once per fortnight.

# During re-examination, Tivendale described Skarajew’s role as determining the priority of what was done on any given day. This was determined according to need and a general approach of “first in best dressed”. This could cause delay if, for example, the crane was being used for one thing while sub-contractors waited for it to be used for their own purpose.

Skarajew’s Communications with Sopov and others

# In his statement, Skarajew provided examples of the conversations he had with Sopov, Jeffery and Irving in relation to the design and construction issues that often gave rise to a delay. These were generally later conveyed to Tivendale and Le Hy Ta. For example, with regard to Sopov, Skarajew made the following allegations:

- location of power boards – this should have been decided by an 	electrical consultant;

- vanity units – he was told by Sopov to proceed as per the relevant 	drawings;

- floor wastes – they were not specified in the drawings. Skarajew 	suggested they were advisable and Sopov instructed Skarjew to 	provide them;

- vanity benches – Sopov instructed Skarajew that the height should be 	900mm;

- toilet pans – Sopov did not agree with Skarajew that the drawings were 	unclear;

- Irving – Sopov was “furious” about instructions issued in relation to 	the flashing to the east façade without prior consultation;

- relocation of sewer pipe – Skarajew indicated that this would be part of 	Kane’s variation claim;

- industrial conditions on-site (lock-outs) – Sopov stated that if a lock-out 	occurred he would sue Kane for interest and damages;

- wall expansion joints – Sopov sought advice from Skarajew as to the 	appropriateness of their location. Sopov did not want to involve Irving 	or Jeffery as this would entail a cost;

- variation claims – Skarajew spent two hours with Sopov explaining 	construction issues. Sopov stated that he was not issuing instructions to 	Kane because this would provide the basis for a variation claim;

- general construction issues – Skarajew said “a couple of hours” were 	spent in discussion with Sopov during time that could have been spent 	managing site activities;

- design issues – one hour on 3 April 2000 was spent discussing this with 	Sopov;

- discrepancy between units 10 and 13 – Sopov said that he had been 	forced to reverse verbal instructions issued by him to Kane because he 	believed Kane was trying to “rip him off”. Skarajew could not recall the 	instructions Sopov was referring to;

- instructions to bricklayer – Sopov was overriding Kane and instructing 	the bricklayer directly;

- legal dispute – Sopov told Skarajew not to sign any legal documents 	regarding the dispute between Kane and the principals.

With regard to conversations that Skarajew said that he had with Irving, Skarajew cited the following alleged examples:

- Kane’s requests and confirmations – Irving told Skarajew over the 	phone that these should be submitted to the principals or Jeffery “for 	legal and political reasons”;

- visiting the site – Irving told Skarajew that he had been instructed by 	Jeffery not to visit the site unless an RFI had been issued by Kane.

In relation to the RFIs, Skarajew suggested that Jeffery’s inadequate responses to RFIs created considerable delays in works.

# When Sopov was cross-examined by counsel for the plaintiff, he stated that, rather than actively giving instructions on construction issues with Kane site personnel, Skarajew would respond to greetings or grant a favour or accept changes when they were put to him. Therefore, as a consequence of this tendency, Sopov stated that he believed Skarajew was an ineffective foreman/manager.

Termination

# After Kane suspended the works on-site, Skarajew said that he went to the site to begin cleaning work. He said that he was instructed (by whom he cannot recall) to remove Kane’s plant, equipment and some material from the site so that those things could be secured. Skarajew said that removal took place from between 28 September 2000 and 2 October 2000. Skarajew stated that some material belonging to the principals was also removed from the site by PN Electrics, while other items which were left in Kane’s sheds (e.g. tile samples, display boards, keys) were removed in error. Skarajew said that he did not intentionally remove any item belonging to the principals, nor was he instructed to do so. Skarejew said that the property of the principals was returned on or about 1 March 2001 to Sopov.

# Skarajew stated that on or about 2 October, as he was cleaning the site, Sopov arrived and asked what was going on. Skarajew said that Sopov informed him that Kane was not supposed to remove anything for 28 days. Skarajew said that Sopov told him to stop removing items from the site as he was taking possession of the site and had already taken photos. Skarajew said that he did not understand what Sopov meant by this. Skarajew said that he did not hand over Kane’s keys on request by Irving as he said he did not have any instruction from Kane management to do so. Later on the same day, Skarajew said that Brendan Archer attended the site and introduced himself to Skarajew as Sopov’s lawyer. Skarejew said thatArcher asked him if Kane had removed anything apart from items belonging to Kane. Skarajew said that he told Archer they had not and that Kane left the site at around 4pm.

RFIs

# Skarajew stated that he had a very detailed knowledge and appreciation of the contract drawings and specifications. He said that the contract documentation was deficient, including ambiguities and discrepancies between drawings and specifications, and insufficient information on contract drawings. These deficiencies resulted in the high number of RFIs and the general delay. Skarajew said that after the RFI was submitted to Jeffery, there were numerous occasions where Kane either received no response at all, or received a delayed or inadequate response.

EOT Claims

# Skarajew stated that Tivendale was responsible for the preparation of EOT claims on behalf of Kane, but that he had relied on Skarajew for information about site activities (such as inclement weather and industrial conditions) which would affect the outcome of the claim.

Variations

# Skarajew said that he reported to Tivendale about events which he considered could cause Kane to incur costs such as variations or delays to the works. He stated that he would also report to Le Hy Ta when information was required for variation claims or progress claims. Skarajew said that, in a discussion on-site with Sopov, Sopov stated that he was not issuing instructions to Kane because this would provide the basis for a variation claim.

(6) WILLIAMSON

Background

# The sixth witness for the plaintiff was Charles Trevor Williamson. In his witness statement, Williamson stated that during the Boilerhouse project he was employed by Kane as an acting site foreman from 31 May to 19 June 1999 (during the first three weeks of the project). During this period, Williamson said that he was on-site every working day for approximately eight hours. Williamson said that his role included:

- assisting Kane personnel in communicating with Sopov, Hampton, 	sub-contractors and design consultants;

- attending fortnightly site meetings (he said that he attended two 	meetings during the relevant period);

- keeping a record of site activities in a diary;

- managing day-to-day activities;

- forwarding time sheets to Kane head office; and

- informing Kane personnel (particularly Tivendale) of site activities.

# Williamson said that there were four days when Peter Omond (another site foreman) and Williamson were both on-site together, namely, 21-24 June 1999.

Construction Supervisor

# Williamson described how he had been appointed by Kane as a construction supervisor and plant manager in 2000. In his role as construction supervisor, Williamson stated that he would attend the site weekly or fortnightly, or as needed, to discuss with the foremen manpower, safety issues, scaffolding requirements and construction issues/procedures.

# In his reply witness statement, Williamson rejected the suggestion by Sopov that he was inexperienced or otherwise unable to perform his role as site foreman. Williamson said that at no time did Sopov suggest as much during his time as site foreman. Williamson emphasised his belief that the four days that he and Omond spent on-site during the hand-over period in June were sufficient. Williamson said that Kane had only been on-site at this stage for three weeks, so it was a straightforward task to explain the work completed to that stage.

Delay

# In relation to the issue of delay, Williamson said that he spoke to Tivendale specifically about the ruptured water pipe and the rock in the lift overrun pit in the basement and ground floor entry ramp as (potential) sources of delay.

Termination

# In his role as construction supervisor, Williamson said that he arranged manpower and transport to remove the sheds, plant and equipment in late September 2000. Williamson said that he recalled that he was requested to assist in that process by Tivendale.

Set-Out and Structural Steel

# In closing submissions, counsel for the plaintiff, Mr Digby, stated that there were no difficulties relating to the builder’s performance of the work by reason of any deficiencies in set-out. It was submitted that Williamson did this work and he was not called for cross-examination, which he should or would have been if the matter had been relevant to the defendants’ case. In short, the defence suggested that there was a very specific problem with the set-out, but the allegation was not substantiated by evidence.

# EOT Claims

# In relation to EOT claims, Williamson stated that, prior to preparing EOT claims, Tivendale would ask Williamson for information about site activities and they would discuss the proposed claim together. The discussions encompassed the causes of the delay, the effect of it on overall progress, and the actual period of the delay.

Variations

# During the relevant period, Williamson stated that he recalled Tivendale attending the site two or three times and spending several hours on-site during each visit. Williamson recalled discussing with Tivendale the progress of the works and events impacting on the progress, including variations and delays.

(7) OMOND

Background

# Peter James Omond, the seventh witness for the plaintiff made a reply witness statement in which he stated that he was a registered building practitioner. His statement was essentially made with regard to paragraphs 38 and 66 of Sopov’s statement and paragraphs 17, 18 and 106 of Jeffery’s statement.

# Omond rejected Sopov’s suggestion that Omond was “inexperienced in supervising and executing works of [the] complexity [of the Boilerhouse project]”. Omond highlighted his experience in large scale developments and further stated that, by 1999, he had “13 years experience as a Site Foreman with Kane”.

# Omond stated that he no longer worked for Kane; but that while he did work on the Boilerhouse project, he “was on-site almost every working day for approximately 8 hours per day”. Omond further stated that at no time did Sopov or Jeffery “question [his] experience or competence”.

# Omond stated that his role in the Boilerhouse project included assisting Kane personnel in communicating with Sopov, Hampton, Jeffery, Martin, the sub-contractors and the design consultants; attending site meetings; keeping a record of site activities in a diary; managing day-to-day site activities; forwarding Kane’s time sheets; and informing Kane personnel of site activities. In particular, Omond said that he discussed the progress of work on-site and any particular problems or issues arising with them with Short, Tivendale and Le Hy Ta.

# Omond stated that he attended fortnightly site meetings at the Boilerhouse and attended all meetings between 21 June and 1 October 1999, except for the meeting held on 13 July 1999. Omond stated that he maintained a record of site activities in Kane’s foreman’s diary and recorded in the diary the names of sub-contractors on-site, the works being undertaken, meetings that took place with Sopov, Martin, Jeffery, Hampton and Long and others. Omond said that he maintained Kane’s time sheets on the Boilerhouse project that recorded the number of days and hours worked by Kane’s labourers and that he knew each of Kane’s labourers personally.

# Omond stated that, while he was site foreman, “Tivendale attended the site at least 2 to 3 times per week, spending up to several hours on-site during each visit”. Omond said that, during those visits, Omond discussed the progress of the works with Tivendale and that he “also spoke with Tivendale nearly every day by telephone where [they] discussed the progress of the works on-site and any particular issues that arose”.

Delays and Variations

# Omond stated that, in his discussions with Tivendale, Omond informed Tivendale of all delays encountered by Kane and all circumstances where the costs might increase “either by variations or delays”. Omond further said that he reported these matters to Tivendale “within a day or so of becoming aware of the information [himself]”.

# Omond said that he was aware that Tivendale prepared Kane’s extension of time claims and that Omond informed Tivendale “on each occasion” and discussed what he knew about “the cause of the delay [and] the effect of the delay on the critical path or progress of work on-site and the period of the delay”. Omond said that “to the best of [his] recollection”, Short and Le Hy Ta were on-site each day for the duration of the project and that he “regularly informed” them of the knowledge he had in relation to the work performed by Kane as variations and the stage of work completed by Kane at the time their progress reports were prepared. Omond stated that, when he had relevant conversations with either Sopov, Jeffery, Martin or Hampton, he informed Tivendale and Short, or Le Hy Ta, as to the general nature of those discussions.

Extension of Time Issue

# Omond stated that, in “about mid September 1999”, he had a discussion with Tivendale about the completion date of 10 December 1999, since he was aware that Kane was “encountering significant problems with the structural steel works”. Omond said that he told Tivendale that the completion date of 10 December 1999 was not realistic and that, while he cannot recall telling this exactly to Jeffery, he did tell Jeffery that he was “frustrated in attempting to convince Tivendale that the completion date was not achievable”. Omond said that he did “not believe [that he] stated to Jeffery that it was frustrating working on a project with an unrealistic completion date”.

Handover from Williamson to Omond

# Omond rejected Sopov’s suggestion that “there was no smooth handover” with Williamson. Omond said that he reviewed all of the appropriate documentation and that, “considering the early stage of works that Kane was at”, he “was well informed about the project generally and the stage of works that Kane had reached by 21 June 2000”. Omond rejected any suggestion that his replacing of the previous site foreman, Williamson, in any way “affected or slowed Kane’s work”.

# Relocation of downpipes

# Omond said that he rejected the suggestion by Jeffery that he said, in about August 1999, that the relocation of two downpipes would cost a maximum of $500. Omond stated that he just quoted that as a “ballpark figure”.

(8) SWARBRICK

# Roger David Swarbrick, the eighth witness for the plaintiff,  was employed by Kane in the capacity of façade foreman on the Boilerhouse project from 4 March to 18 July 2000. He was not called as a witness and his evidence is based upon two witness statements.

# Swarbrick stated that he was on-site at the Boilerhouse Project almost every working day for nine hours at a time. As façade foreman, Swarbrick assisted Kane personnel in communicating with the principals (mainly Sopov), Jeffery, the superintendent’s representative (initially Mark Irving), the various sub-contractors, and also the design consultants. Swarbrick stated that it was his practice to inform Tivendale and/or Le Hy Ta of the details of discussions held with Sopov, Irving or Jeffery on or about the same day that he had the relevant conversation.

# Swarbrick said that he attended site meetings and kept a record by way of making entries of site activities in Kane’s foreman’s diary for the period from 8 May to 17 July 2000. This included a record of conversations held with Sopov, Jeffery, Irving or Le Hy Ta. As well, in the diary, Swarbrick said that he particularly noted events in relation to the façade works, the movements of sub-contractors on-site, industrial and weather conditions, and health and safety issues.

# Other tasks performed in Swarbrick’s capacity as façade foreman included management of daily site activities relating to the façade, such as assisting in the coordination of the various trades on-site, deliveries to the site and monitoring the progress of façade works. Swarbrick stated that he regularly spoke with other Kane employees, namely, Tivendale, Le Hy Ta and Skarajew, in relation to the façade work activities. Swarbrick said that he attended most of the site meetings (he was absent at five) while foreman, which were held on a fortnightly basis.

# With regard to delays and the EOT claims, Swarbrick said that he reported to Tivendale, either by telephone or in person, about any delays being encountered or anticipated, for example, inclement weather. Tivendale, who was responsible for preparing EOT claims, would also discuss proposed EOT claims with Swarbrick, including the actual period of delay and the effect on overall work progress.

# Swarbrick said that on occasion he had discussions with Le Hy Ta, particularly when he required information relating to variation or progress claims that Le Hy Ta was preparing.  Swarbrick said that Le Hy Ta was on-site for every working day for the duration of project (from the time Swarbrick began work on the project).

# Swarbrick also said that Sopov was on-site regularly and was generally interested in the set-out dimensions, the visual balance of the Alucobond and Rheinzinc, and the external façade in general. Swarbrick said that he spent a great deal of time with Sopov discussing issues such as balance, symmetry and the joins of various materials for the façade. Swarbrick said that Sopov often told him that he was happy with the visual effect.

# Swarbrick stated that he could specifically recall discussions with Sopov regarding the Alucobond to the level 3 gallery face soffit and the installation of the face in one piece. Swarbrick noted that the approved shop drawing and elevations showed a joint, but that the section drawings did not. According to Swarbrick, the Manager of AAS, Mr Spencer Wilson, informed him that it would be very difficult to install the face in one piece and that there should be a joint to facilitate installation. However, Swarbrick said that Sopov told him that he did not want a joint. Swarbrick was in this way made aware that a face template was to be manufactured if possible for installation in one piece.

# In relation to the pivot doors which were inspected and approved by Irving and Sopov on or about 10 July 2000, Swarbrick said that Sopov was happy with them and had no complaints.

# Swarbrick further maintained, in his reply witness statement, that issues with the façade shop drawings prepared by Kane and the relevant sub-contractors did not directly delay works under his supervision.

(9) QI SHAO

Background

# Qi Shao, the plaintiff’s ninth witness,  was a director of S & D Design and Drafting Pty Ltd (“S & D”). S & D became involved in the Boilerhouse project some time in June 1999 when DVP Engineering Pty Ltd (“DVP”), one of Kane’s main sub-contractors, in turn engaged S & D to carry out the drafting component of the structural steel. Shao’s evidence was drawn largely from her reply witness statement dated 8 August 2003 and also from evidence provided at trial.

# Ms Shao’s background was as follows. She stated that she obtained a Bachelor of Civil Engineering from Tongji University in Shanghai, China (although she did not specify which year). She said that she was qualified as a civil engineer in Australia and that she had undertaken such work for the past 16 years.

# Shao described S & D as a structural steel drafting company of approximately 12 years standing. She said that the company had worked on projects both larger and smaller in size than the Boilerhouse project, describing the project itself as “medium”sized. According to Shao, S & D derived much of its work through DVP.

# At the time of the Boilerhouse project, Shao stated that S & D employed two people in a full-time capacity, including herself, to work on the project. The other full-time worker was described as a casual employee. A third person, one Danny Gu, was also a director of the company and worked on a part-time basis. All three worked on the Boilerhouse project. Shao’s role specifically included providing architectural and structural drawings for the fabricator; the drafting of marking plans (which indicated the location of the structural steel); and provision of parts and shop drawings. Occasionally, but not often, she would be involved in discussing and resolving difficulties which arose.

# In June 1999, S & D were provided with the architectural and engineering (structural) drawings for the project for the commencement of drafting works. Qi Shao stated that the drawings were inadequately detailed and contained inconsistencies which delayed the commencement of detailed shop drawings for steel fabrication. S & D sent two letters to Kane on 23 and 25 June 1999. These letters outlined S & D’s problems and also requested further necessary information.

Drafting Problems

# In her witness statement, Shao listed the problems encountered during the drafting process. They are, briefly, as follows:

# “inconsistencies” in details provided in the contract drawings;

# details provided that, according to Qi Shao, “did not work”;

# apparent absence of details in contract drawings;

# need for additional shop drawings as a result of changes in the structural steel 	requirements; and

# late changes/rejection of approved shop drawings which further complicated 	the process.

# Shao expanded on and gave examples of these drafting problems in her witness statement. She estimated that 40 per cent of the shop drawings were revised. According to Shao, therefore, all of this caused significant overall delay to the progress of works. She suggested that had the documentation been adequate and no revisions been made, the project could have been completed in four to six weeks. Instead, the task went for a period of approximately four months.

# Shao stated that, in her opinion, Sopov did not appear to appreciate or understand what was involved in revising the shop drawings. For example, the fact that a small change resulting in the revision of a drawing affected other drawings and connections.

# Shao acknowledged that some revisions were the result of drafting mistakes, but she estimated that over 70 per cent of the revisions on the project resulted from changes having to be made due to deficiencies in the contractual documentation (including, for example, four revisions to drawing 27 (beam 3B26) and drawing 29 (beam 3B11)).

# Shao stated that, owing to the numerous major changes resulting from inadequate contract documentation, many meetings had to be held to discuss the problems. At least three of these meetings were with the engineer. Further, the meetings went for a minimum of half a day, causing more delays to the drafting process. Shao said she usually attended on-site or had meetings elsewhere once or twice a week. While Shao recognised her contractual need to visit the site during the course of such a project, this ordinarily did not extend to meetings. At one of these meetings with Sopov and Tivendale, which related to the steelwork for the level three balcony of apartment 11, Shao stated by way of example that Sopov had advised of revised details which would result in the alteration of 13 shop drawings that had already been approved some time earlier and provided to DVP for fabrication.

# Shao said that she could not recall how long individual shop drawings took to be approved but that there were often long delays. There were significant periods of time when S & D were unable to undertake any drafting because it was awaiting further instructions or information. However, Shao also stated that during the period from July to October 1999, S & D devoted all of its time to the Boilerhouse project, working weekends on numerous occasions and on at least one occasion working through the night to complete the shop drawings relating to the balcony set-downs. As a result, the company could not undertake any other work.

# In cross-examination, in which she gave evidence through an interpreter, Qi Shao provided other examples of her drafting problems. She said that two or three days after a meeting held with Tivendale, Sopov, the engineer and several others on 29 June 1999, she received part of the information required and began the shop drawings on the column of the ground floor of the gallery façade.

# Shao said that there were particular difficulties with the holding plans 1 to 3 (HP 1 to HP3) and the marking plans, which formed the basis for the shop drawings. For instance, Shao stated in relation to HP2 (dated 21 June 1999) that she required information on the length of a particular beam and details with respect to the canopy. She would not agree that the canopy could have been done at any time on the basis that it simply had to be bolted on underneath the existing concrete, as its connection point was the column.

# During cross-examination, it was put to Qi Shao that Tivendale had earlier given evidence to the effect that, following a further meeting with S & D on 9 July 1999, the set-out issues based on the site dimensions were finally resolved. Shao was not able to respond completely. She agreed that shop drawings 1,2 and 3 were dated 9 July 1999 and that no other shop drawings were produced until shop drawings 4 and 5 on 23 July 1999. Shao did, however, explain that while her query in relation to holding plan 1 (HP1) had been answered by Tivendale, she had to wait for answers to HP2 and HP3, which prevented shop drawings being produced for the gallery façade. Shao agreed that she had never directly asked Sopov for information when information was required. She stated that DVP had directed her to contact Tivendale, the project manager for Kane, where necessary.

# Counsel for the defendants put it to Shao during cross-examination that there was nothing in HP1, 2 and 3 which prevented her from preparing the shop drawings to the gallery façade if that was the place she thought she had to start. However Shao stated that the dimensions and arch location had to be approved by the engineer and architect for that part before she could start and the information had to be complete. Nevertheless, Shao agreed with the proposition that structural engineers only ever approve holding down plans for shop drawings for structural integrity and they never approve dimensions.

# During re-examination, Shao gave evidence that the information she required in the June/July 1999 period included (i) set-down information which was not marked on the original drawing and could only be supplied by the engineer, and (ii) design information such as column location which she said needed to be provided by an architect.

# As to the need for site measurement, attention was drawn to plan AO1 A-A which Shao recognised as one of the plans Dordevic, a Director of DVP, had given her in the middle of June 1999. Notes on the right hand side read: “the contractor is to verify the existing column grid spacing and all set-out dimensions prior to commencing the work”; with respect to which Shao gave evidence that it was not her job to interpret what the notes on the plan required.

# It was put to Shao that she requested site measurements between 16 June and 7 or 8 July 1999 on a piecemeal basis. Attention was drawn to the fact that a number of documents were eventually provided setting out the dimensions rather than, as should have occurred, the site measurements being provided before beginning drafting work.

(10) DORDEVIC

Background and Role of DVP in the Boilerhouse Project

# Vlastimir Dordevic, as the tenth witness for the plaintiff, gave evidence for the plaintiff in his capacity as a director of DVP Engineering Pty Ltd (“DVP”). Dordevic stated that DVP was an engineering and fabrication firm which entered into a sub-contract with Kane on 8 June 1999 for the drafting of shop drawings and the fabrication and erection of the structural steel for the Boilerhouse project. Dordevic said that DVP had been providing structural steel engineering works for 27 years in projects both larger and smaller than the Boilerhouse project. Dordevic said that, for over 10 years, DVP had obtained a significant amount of work through Kane. Dordevic stated that his role in the Boilerhouse project encompassed managing workshop operations and overseeing the shop drawing process and contract administration. Dordevic said that he had approximately 30 years experience as a structural steel fabricator.

# Dordevic said that programs usually have to allow for more time in relation to a refurbishment project as a result of the complexities associated with ensuring that the structural steel complements the existing structure. He said that approximately 20-30 per cent of DVP’s work over 26 years had involved structural steel refurbishment projects, many of these similar to the Boilerhouse project. Dordevic further said that, according to his professional experience, the structural steel component (drafting, fabrication and erection process) of the Boilerhouse project should have taken eight to nine weeks, inclusive of approximately four weeks at the beginning of the project for the resolution of any queries in relation to contract drawings and the drafting and approval of shop drawings; two to three weeks for fabrication; and 10 days for the erection of the resulting structural steel.

# Dordevic stated that the tender drawings S1 to S11, A1 to A11-A, A16-A to A17-A and A21-A were provided to DVP in late March or early April 1999 and that DVP provided its quote to Kane by document dated 8 April 1999. Prior to being awarded the contract on 8 June 1999, Dordevic said that he had discussed the requirements with Tivendale, including the time required for the drafting, fabrication and erection. Dordevic further said that he was aware that Kane had programd the structural steel to be erected on-site in early August 1999 and that DVP could have met that deadline. Dordevic alluded to the Kane program provided by Tivendale in early August 1999 which allocated 61 days for the structural steel. Dordevic said that, given the relatively small size of the project, six weeks with 10 days for critical structural steel erection was a “realistic and feasible program”.

# During cross-examination by counsel for the defendants, Dordevic said that he was not provided with a program when awarded the sub-contract, but that he was told of an approximate timeframe for the fabrication and erection of steel. Dordevic said that the production of drawings could be staggered so that fabrication could commence before all the shop drawings were complete, i.e., a certain amount of the drawings (from 60-90 per cent over the first four weeks) could be sent for approval and fabrication and could start, while the remaining drawings could be finalised over the next two weeks. As to the steel itself, Dordevic said that it was ordered and could be delivered in one day, whereupon fabrication could be done straight away, or it could take up to one week depending on the amount of work DVP had at the time.

# In his witness statement, Dordevic outlined the processes involved in drafting, fabrication and erection as being the obtaining of a full set of structural and architectural drawings from the builder; the engagement of a drafting company to provide a set of competence drawings in order to fabricate the structural steel; the resolution by the draftsperson of any queries which may arise (generally these are few) from the drawings directly with the architect, builder and owner; the preparation of shop drawings in sections so that fabrication can commence while drafting of other sections continues; the seeking of approval by DVP from the builder, upon completion of the shop drawings (noting that sometimes the draftsperson will provide the drawings directly to the builder or architect and that these are in the main approved by the architect and returned, although sometimes with markings which indicate any changes to be made); upon approval, the commencement of fabrication by DVP, frequently on the same day the drawings are approved and typically within one day of approval; and finally, the erection of the structural steel on-site.

# In cross-examination, Dordevic said that DVP’s drafting sub-contractor, S & D, was not provided with a program, nor did Dordevic give S & D any directions as to what sections of the shop drawings should be started first, since there was enough time to do the job – “if the documentation had been right” – and therefore they did not need to begin with the critical area.

# Dordevic said that he reviewed the shop drawing registry which indicated the number of revisions made to the shop drawings during drafting (and produced by Tivendale) and believed that it was an accurate record of the details in the shop drawing. Dordevic said that the register indicated approximately 70 changes to the approved shop drawings which is excessive and atypical, and that they were also having to “deal directly with the Principal to get information”. Dordevic said that this was a “very unusual situation” and that he could not recall DVP having worked on a similar project without an architect. Dordevic further stated that, in his experience, approved shop drawings were final, and in the absence of significant error, the structural steel would be produced and any revisions were usually minimal (with approximately one or two revisions for every 20 drawings).

# Dordevic’s witness statement highlighted the following issues in relation to the submission of shop drawings over a five month period: the tender drawings lacked sufficient detail to enable the production of shop drawings and were not revised (according to Tivendale) so as to avoid problems as is typical; an excessive number of changes made by the superintendent and principals during drafting, fabrication and installation were caused by inconsistencies in the contract drawings of which Dordevic was informed by S & D and Tivendale (additional members were then required to be shop drawn, fabricated and erected as a result); changes made by the superintendent and/or principals after shop drawings had been approved and changes to the structural steel requirements after it had been erected on-site; and the absence of an architect familiar with the project who could resolve any issues that arose quickly.

Competency of S & D

# Dordevic said that the standard practice was for the fabricator to appoint a draftsperson, as opposed to the builder. Dordevic said that DVP had dealt with S & D on a regular basis for approximately 8-10 years and was content with the standard of their workmanship. Dordevic said that S & D was retained, without written contract, because of the small size of the project, within one week of DVP being awarded the structural steel contract. Dordevic said that in mid-June 1999, shortly after the drawings were provided to S & D, Qi Shao, a director of S & D, informed Dordevic by telephone that the drawings did not contain sufficient detail to begin producing shop drawings. Dordevic said that DVP passed on the complaints to Tivendale and that this resulted in several meetings being held between S & D, Kane and the principal.

# In cross-examination, Dordevic said that when Qi Shao complained to him about the insufficient detail and many discrepancies (although she did not go into detail about these), Dordevic told her to speak to Tivendale. Dordevic further said that within a day (or not more than two days), Dordevic himself spoke to Tivendale about Qi Shao not being able to begin the shop drawings. Dordevic said that Tivendale told him that he would deal with it, and Dordevic said that he believed that there would have to had been a conversation between Qi Shao and Tivendale as a result.

# Dordevic said that during the shop drawing process he was frequently informed by Qi Shao of difficulties caused by the lack of detail, and/or where detail was stipulated, it was often unworkable. Dordevic said that, on 16 November 1999, Danny Gu, a director of S & D, wrote to Dordevic outlining the difficulties and additional work required as a result of inadequate contract drawings and changes made by the principals. Dordevic said that, in his opinion, the drafting process should have taken four weeks, but instead took from June 1999 until 15 November 1999 and that this resulted in a delay to fabrication and the erection of structural steel.

# Dordevic said that, on occasion, S & D provided DVP with shop drawings – simultaneously with the provision of these drawings to the engineer for approval – in order that fabrication of the structural steel commenced (namely, prior to the approval of the principals and the superintendent) and that delays were thereby minimised. Dordevic said that the fabrication of the structural steel should have taken two weeks but instead took from 15 September 1999 until 22 November 1999 due to deficiencies in the structural steel documentation.

# During cross-examination, Dordevic said that there were problems with the structural steel drawings, but that these were much less than the problems with the architectural drawings which included set-out, measurements, and how each member connected to gutters, concrete and similar things. Dordevic said, however, that he had never checked the architectural drawings in detail, nor had he conducted an analysis of the delay to the structural steel fabrication as a result of the delay to shop drawings. Dordevic said that he had, to a certain extent, made an analysis of the delays to the structural steel shop drawings caused by the deficiencies in the plans by noting the timing of where members were pulled out and changed. Dordevic said that in doing this, considerable time was wasted on the job. Dordevic said that changes were required to the shop drawings and structural steel and that the builder also required changes to the structural steel. However Dordevic said that the only the record of the alterations required by the builder were to be found on the invoices that he provided to the builder.

# Dordevic said that the fabrication delays were also caused by the infrequent and irregular manner of obtaining the approval of shop drawings. Dordevic said that DVP received the approved shop drawings for connecting beams or components at different times. Dordevic further said that the erection of the structural steel, which should have occurred over 10 consecutive days, instead took 12 weeks, from 21 September 1999 until to 13 December 1999. He said that this was caused by the delays in the drafting and fabrication processes and the increased number of structural steel components and by the late changes to the approved shop drawings which were made after the beams were installed. Dordevic said that, for instance, beam 3B26 was revised four times, with the beam having to be removed, the altered beam fabricated and then re-erected.

# Dordevic said that the installation of the structural steel was programd to be completed by 24 September 1999 and that the program allowed for 10 days. Dordevic said that, had it not been for inadequate contractual documentation and substantial changes made during shop drawing, fabrication and erection processes, this timeline would have been achievable. Dordevic said that he had read Tivendale’s witness statement which stated that the original program allowed 61 working days for shop drawings and off-site fabrication and 10 working days for on-site erection; however Dordevic said that the shop drawing process occurred from mid-June to late October 1999 which was a period of time in excess of 95 working days. Dordevic said that the on-site erection which was programd to begin on 18 August 1999 did not begin until 18 September 1999 and that it proceeded through to early December 1999, that being a period in excess of 54 days. Dordevic said that these delays could not have been reasonably anticipated on the structural steel documentation prior to entering the contract and were caused by the excessive number of changes made by Sopov to the structural steel requirements.

Specific Delays

# Dordevic said that DVP were provided with the approved shop drawings with respect to the gallery face on 13 August 1999, by superintendent’s instruction of 5 August 1999 and with annotations that indicated the principals’ approval. Dordevic said that the approved shop drawings included handrails and the ARC columns. Dordevic further stated that DVP were informed, on or about 8 September 1999, that the ARC columns were to be deleted and, as a result, shop drawings 11B and 13B were produced and provided in mid-September 1999 for fabrication. Dordevic stated that these changes involved the deletion of six columns, 12 connection points to the ARC columns on six beams, and the re-location of the bolt holes in these beams for the altered handrail layout. Dordevic said that, at the time that he was notified of the changes, shop drawings 11 O and 13 O had been received for fabrication, but Qi Shao advised him that these beams were to be altered and had not been fabricated.

# Dordevic further said that he was also advised, by way of instruction SA21 dated 8 September 1999, that the cutting of the level 2 slab adjacent to the 2nd floor terrace on the south of the chimney required the alteration of the length of the main beam LT1 and an additional beam HB1. Dordevic said that shop drawing 14 O was provided to DVP for fabrication on 10 September 1999 and the steel was subsequently fabricated on 23 September 1999. Dordevic said that, as required by SA21, the beam was then altered in length and the end plate connections were added.

# Dordevic stated that DVP had experienced many delays and difficulties with respect to the Level 2 columns and level 3 beams and balconies. Dordevic said that on 14 September 1999, Qi Shao informed him that the connection steel to the columns and beams at the north-west corner had been omitted from the architectural plans and approved shop drawings but were later required. Dordevic said that some of the columns and beams to which these connections related had already been manufactured in DVP’s workshop while others were in the process of being fabricated. During re-examination, Dordevic said that the shop drawings provide the record of the fabrication date of the members.

# Dordevic further said that, on or about 22 September 1999, Tivendale and Qi Shao advised Dordevic that Sopov had instructed revisions to be made to the balcony in apartment 11 and that these revisions affected 13 drawings that had been fabricated in accordance with the approved shop drawings of 3 September 1999. Dordevic said that the fabrication of six of these drawings (17C, 23C, 25AB, 27A, 29A and 35A) had already been undertaken. Dordevic said that revised shop drawings were provided on or about 24 September 1999 or 27 September 1999, but that Dordevic then received instruction from Tivendale on or about 30 September 1999 that Sopov wanted to revert to the original structural steel design and so a hold was placed on fabrication. Dordevic said that the revised approved shop drawings were provided to DVP on 5 October 1999, but that DVP were instructed not to begin fabrication until approved by the engineer and that this approval occurred on 6 October 1999. Dordevic said that the altered steel was delivered to the site on 14 October 1999 and that the removal of the beams which had been installed in accordance with the earlier shop drawings delayed the project for nine days.

# In cross-examination by counsel for the defendants, Dordevic said that he had not carried out an investigation to establish whether or not the whole project was delayed due to the structural steel, but he believed that, as a natural “flow-on effect”, delays with the structural steel would mean that the progress of other trades would also be halted. Dordevic said that the main problems were that S & D were delayed in producing the shop drawings and that the erection of the structural steel was still occurring between 30 September 1999 and 14 October 1999 while there were still problems with the documentation. Dordevic said that DVP should have finished their work by 2 September 1999, but that it was taking longer because the erection of the structural steel was being done in “bits and pieces”.

# In cross-examination, Dordevic said that the demolition of the roof which preceded the structural steel work did not delay in any way the structural steel work itself. Dordevic further said that he could not recall the exact date when demolition began, but estimated that it was in late July 1999 or early August 1999. Counsel for the defendants suggested to Dordevic that demolition of the roof did not begin until after 18 August 1999, but Dordevic said that he believed that it had occurred before that date. Dordevic also said that the gallery façade steel was attached to the roof and could not have been left alone completely or put on months after the main structure was built.

# Dordevic also said that there were problems with the gutters and that alterations had to be made due to the deletion of some holes and therefore the documentation had to be changed. In re-examination, Dordevic said that the problems were indicated on engineering drawing S6 between grids 1 and 2; on drawing S5; and on drawing S8,which apparently did not indicate where the holes had to be drilled in relation to fixing the balustrade. Dordevic said that the area of guttering was part of the gallery façade steel which Dordevic considered an integral part of the structural steel work.

# In re-examination Dordevic said that he went to the structural engineering drawings to identify the problems arising from time to time which included a mansard roof which was never shown in structural drawings and the alteration in the size of the plant platform on the roof.

# Dordevic stated that, on 5 November 1999, beam 3B26 was again revised (after it was installed) from it being a straight to a cranked beam. Dordevic said that this meant that the beam had to be removed, altered and re-installed. Dordevic said that DVP did not keep a record of beams that had been installed. However Dordevic said that, based on a discussion he had with the door manufacturer, he knew that one of the beams had to be returned for alteration around the end of October 1999. Dordevic said that these instructions again changed on 12 November 1999 and that the final revision occurred on 13 November 1999, with work undertaken between 19 November 1999 and 23 November 1999, meaning that the project was delayed by 2.5 days.

# Dordevic said that difficulties also arose from the insufficient height of the reinforced core filled blockwork pier supporting beams 97A and 99A. It appears that this particular problem was not discovered until DVP had commenced installing the beams on 29 September 1999. This meant that three extra columns had to be fabricated by DVP to support the beams. Dordevic said that this caused a delay to on-site erection between 30 September 1999 and 14 October 1999, a period of nine working days.

# Dordevic said that he believed that Kane’s claim was justified for a delay of 45 days between 27 September 1999 and 2 December 1999. Dordevic said that, given the difficulties and delays to structural steel, he believed that Kane’s claim of 45 days was “conservative”.

(11) THOMAS

General

# Lawrence Maxwell Thomas was a quantity surveyor by profession with almost 30 years of experience in his field. He first became involved in the Boilerhouse project when the WT Partnership (“WTP”), of which he was a Director, was engaged by the plaintiff’s solicitors to provide an expert opinion on whether the costs of $5,221,603 incurred by Kane were fair and reasonable.

Quantum Meruit Report

Background/Methodology

# Thomas’ Order 44 statement included a report of the quantum meruit claims made by Kane, as assessed by Thomas. Thomas said that, to verify the accuracy of the quantum meruit claims, WTP audited a selection of representative items. These were detailed in Table 1 of his witness statement. Purchase orders were chosen on a criteria of value and possible contention and included 22 entries. Table 2 of Thomas’ witness statement used a selection of contract final accounts, selected on the basis of their significant increase in end value in relation to the initial value (i.e. variations and possible EOTs). The sample included six sub-contracts.

# Findings of Thomas

# Thomas’ findings were that records were well kept with clear and logical sequence and annotation. Contract administration was held to be of a high standard. While not all records were perfect (for example, pages were missing from the foreman’s diary), WTP considered that the claim of costs incurred was accurately reflected. As to Kane’s claim for a 10 per cent mark-up on costs to recover overheads etc, WTP found it to be a fair and reasonable charge on a quantum meruit basis, based on previous average costs of administration (13.44 per cent).

# Notwithstanding the above findings, WTP reported some items which, by industry standards, were arguably higher than expected. Thomas identified these items as relevant to “the amount and value of Kane’s direct labour”. By “direct labour”, I take the expert to mean that this was the cost to Kane for employing their own workers and payment for sub-contractors’ employees where necessary to complete works. Nevertheless, according to Thomas, the higher costs were justified as labour was on-site and expenses were incurred as a result of one or more of the following situations: poor coordination of documentation supplied by the proprietor, giving rise to the need for variations which the trade sub-contractors were not willing to undertake; use of Kane’s own scaffolding crews, employed to minimise industrial and safety issues; delays caused by unproductive use of direct labour; and the MTK liquidation, for which Kane entered into a scheme of arrangement ensuring that works could be completed using day labour and with Kane paying MTK employees at agreed rates.

# Thomas found that the claim by Kane on the quantum meruit basis of an outstanding amount of $2,452,253 truly reflected the actual costs.

# Thomas summarised his statement by concluding that the increase in actual costs incurred over the original contract sum could be explained by a combination of factors including: (i) prolongation costs associated with the extended duration of the project; (ii) significant cost increases in the construction industry as a result of booming activity and the impact of the Enterprise Bargaining Agreements introduced at that time (1999); and (iii) variations “necessarily incurred in a project of this nature”, where, for example, complex construction matters have not been not reflected in tender documents.

# During cross-examination, Thomas said that he visited Kane’s offices three times. He met only Tivendale and Lucas at their offices.

# Thomas accepted that he took 22 entries (relating to costs) worth 69 per cent of the value of the job and divided the information into two tables. He explained that, through the audit, WTP were trying to identify the areas that would be most contentious and of the highest value. First they searched for any records that appeared “untoward or incorrect”. On finding nothing in this regard, they looked for costs that were higher than expected. Day labour was one such area, and so WTP interrogated Kane about it.

# It was inferred by counsel for the defendants during cross-examination that Thomas could not have come to an accurate or fair conclusion about the records of costs incurred because an assumption was made about the accuracy of what Kane told him.

# During re-examination, Thomas was given the opportunity to explain why he concluded that the increase in the day labour figure was plausible. His response was that Kane used their own labour (which in other circumstances could have been a trade contract). They also had two leading hands on the project because of the complexity of the issue of construction as well as extra labour on-site.

# All of this resulted in extra delays. The longer duration of the project, caused by the fact that works had been extended by up to a year longer than expected, meant that labour (paid by time not by task) produced higher costs in wages.

# With regard to the quantum meruit claim, Thomas acknowledged that the sub-contract agreement sum for MTK work (plastering/stud work) was $420,000.00, whereas Kane’s quantum meruit claim with respect to the MTK work amounted to $565,553.00, representing an increase of approximately $145,000 from the contract price. Thomas said that he did not measure the amount of stud and plaster work installed on the Boilerhouse project as WTP was not requested to do so. Thomas was not able to say whether the scope of stud or plaster work increased from when the contract was first let. He observed that it was not his brief to determine changes in the scope.

(12) LYNAS

Background

# Gordon Lynas, the plaintiff’s twelfth witness, was a director of Tracey, Brunstrom & Hammond Pty Ltd (“TBH”). His Order 44 statement was prepared at the request of the plaintiff’s solicitors who asked TBH to review the EOT claims, numbered 1-18 inclusive, made by the builder in respect of the Boilerhouse project. The brief provided to TBH by the plaintiff’s solicitors indicated that these EOT claims could be found in schedule 3 of Kane’s Amended Points of Claim dated 16 November 2000; schedule 2 of Kane’s Points of Claim dated 3 July 2000; and Kane’s Further and Better Particulars of its Points of Claim dated 4 September 2000. Lynas stated that he was “an expert in project management processes and techniques with particular emphasis on time, cost, scope and risk management”.

Methodology

# Lynas described his methodology for quantifying the delays as involving several aspects. These were described as, firstly, reviewing the factual evidence to determine the circumstances of the delay and its chronology; then reviewing the contractor’s programs to identify the immediately preceding program; inspecting the relevant program to determine whether the delay affected any of the program’s critical paths at the time of the delay; and where the program showed more than one critical path, inspecting the “as built records” to determine if the path had actually been critical at the time of the delay. Lynas further stated that the critical delay to completion was defined as the period for which the progressive critical path was delayed and that the next occurring delay was treated on the same basis.

# In examination by counsel for the plaintiff (and despite the objections made by counsel for the defendants about Lynas’ mode of evidence), Lynas gave a PowerPoint presentation to illustrate how it was that he went about identifying activities of work in relation to the overall construction works undertaken by the builder, for the purpose of identifying what work was critical and what work was not critical on the project. Lynas further stated that, even if, hypothetically, his assessment of the critical path was not accepted with respect to the EOTs, he believed that “in general terms, the delays [were] stand alone items”.

# Lynas stated that the time set for the project by the contract was from 31 May 1999 to 10 December 1999, i.e. 6.5 months, and that taking into account “normal construction practice”, the available number of work days in that contract period was 154 days. Lynas stated that, based on his understanding of “the statistical relationship between time and cost for construction projects”, a period of 154 days would require “performance from all parties to the works equivalent to or better than that achieved by the top 25 per cent of projects” and that such a timeframe could be considered to be “somewhat ambitious but not unachievable for a project of this type and value”.

Analysis of EOT Claims

# Based on his analysis, Lynas came to the following conclusions about Kane’s EOT claims:

| # EOT Claim Number | # Description | # Valid (√) or Invalid (x) Claim | # Number of Days # that can be Substantiated # by the Claim |
| --- | --- | --- | --- |
| # 1(a) | # Lift overrun pit | # √ | # 8 |
| # 1(b) | # Basement ramp, Ground floor entry | # √ | # 4 |
| # 2 | # Industrial action | # √ | # 2 |
| # 3(a) | # Industrial action | # √ | # 1.25 |
| # 3(b) | # Cut back slab at Level 2 | # √ | # 2 |
| # 4(a) | # Balcony stepdowns | # √ | # 4 |
| # 4(b) | # Redesign of structural steel to the 3rd floor north-west corner | # √ | # 14 |
| # 4(c) | # Height of the parapet | # √ | # 3 |
| # 4(d) | # Incorrect detailing for roof members | # √ | # 36 |
| # 5 | # Statewide strikes | # √ | # 2.5 |
| # 6(a) | # Removal, alteration and reinstallation of beam 3B 26 | # √ | # 2 |
| # 6(b),(c),(e),(i) and (j) | # Inclement weather | # √ | # 1.4375 |
| # 6(d) | # Installing larger plant platform | # √ | # 0.5 |
| # 6(f) | # Installation of purlins and cleats for gutter | # x | # 0 |
| # 6(g) | # Installation of gutter | # x | # 0 |
| # 6(h) | # Statewide strike | # x | # 0 |
| # 6(k) | # Installing plywood backing | # √ | # 5 |
| # 6(l) | # Enforced shutdown by union | # √ | # 4 |
| # 7(a) | # Install floor wastes | # x | # 0 |
| # 7(b) | # Install plywood backing | # √ | # 2.25 |
| # 8(a)-(e) | # Inclement weather | # √ | # 2.375 |
| # 8(f) | # Altering steel | # √ | # 5.375 |
| # 8(g) | # Pulling up structure board and installing CFC for floor wastes | # √ | # 1.75 |
| # 8(h)-(k) | # Industrial action | # √ | # 5.125 |
| # 9(a) | # Inclement weather | # √ | # 0.25 |
| # 9(b)-(c) | # Industrial action | # √ | # 6 |
| # 9(d) | # Manufacture of fire rated boxes | # √ | # 4 |
| # 9(e) | # Installation of fire rated boxes | # √ | # 6 |
| # 10(a) | # Industrial action | # √ | # 0.375 |
| # 10(b)-(d) | # Loss of productivity | # √ | # 1 |
| # 11(a)-(c) | # Inclement weather | # √ | # 1 |
| # 11(d)-(e) | # Industrial action | # x | # 0 |
| # 11(f) | # Installation of P50/P60 | # √ | # 1 |
| # 12(a) | # Design and fabricate support details for pivot doors | # x | # 0 |
| # 12(b) | # Installation of P60/P50 | # x | # 0 |
| # 12(c)-(d) | # Inclement weather | # √ | # 1.25 |
| # 12(e)-(j) | # Industrial action | # √ | # 5.875 |
| # 13(a) | # Design and fabricate support details for pivot doors | # √ | # 3 |
| # 13(b)-(e) | # Inclement weather | # √ | # 2.75 |
| # 13(f)-(h) | # Industrial action | # √ | # 2.125 |
| # 14(a) | # Design and fabricate support details for pivot doors | # x | # 0 |
| # 14(b) | # Inclement weather | # √ | # 0.5 |
| # 14(c) | # Burst water main | # √ | # 1 |
| # 15(a)-(l) | # Extra works | # x | # 0 |
| # 15(m)-(o) | # Inclement weather | # √ | # 1.5 |
| # 16(a) | # Industrial action | # x | # 0 |
| # 16(b)-(h) | # Extra works | # x | # 0 |
| # 16(i)-(o) | # Inclement weather | # √ | # 2 |
| # 16(p)-(r) | # CFC painting delay / inclement weather | # x | # 0 |
| # 17(a) | # Industrial action | # √ | # 0.375 |
| # 17(b)-(m) | # Inclement weather | # √ | # 3.8125 |
| # 17(n) | # CFC painting delay / inclement weather | # x | # 0 |
| # 18 | # Period from the contractor’s Notice of Suspending the Works to the date the Principal took control of the works | # √ | # 10 |

# In his analysis, as summarised above, Lynas noted that some of the delays were concurrent with others. Taking this factor into account, the total delay assessed by Lynas, on behalf of TBH, was 151 days. Lynas further stated that the superintendent had approved delays totalling 11.75 days. Lynas therefore concluded that additional non-concurrent work day delays totalling 139 days and two hours was justified.

# Lynas further stated that, in light of his analysis, the practical completion date should be extended from 10 December 1999 to  August 2000. After further taking into account inclement weather delays and what may or may not have been covered by the conditions of the contract, Lynas concluded that Kane was entitled to an extension of time of 147 days, and that the extended date for practical completion should be 4 August 2000.

# In cross-examination, Lynas conceded that what he had assessed as a construction program did not take into account “off-site activities”, and that there could have been “critical” off-site activities which affected the on-site program. However, in re-examination by counsel for the plaintiff, Lynas said that although the programs that the builder produced did not have programd activities such as procurement or the preparation of shop drawings, he did not believe that the absence of such activities rendered those programs “defective”; since Lynas thought that the time available from the beginning of the program until those items were required was still adequate.

(13) LEE

Background

# Norman John Lee was a quantity surveyor. He, like Thomas, was an employee of the WT Partnership (“WTP”). WTP prepared a report and Order 44 statement, as commissioned by the plaintiff’s solicitors, Deacons, in respect of both Deduction Variations and Costs to Complete.

Deduction Variations

# In his witness statement, Lee said that WTP reviewed the 19 deduction variations that had been claimed by the principal and set out in the annexures to the statements of Jeffery and Goodwin. Lee said that WTP concluded that the listed variations claimed by the principals were “not fair and reasonable”.

# Counsel for the defendants questioned Lee on his methodology. Lee said that he had seen Tivendale “half a dozen times” and that he had read Le Hy Ta’s witness statement. However Lee said that he had not spoken to the defendants; nor had he seen any documents showing how the superintendent had assessed the claims. Lee said that the documents that he had seen from the defendants’ side were the principals’ claim for the deduction variations, the Jeffery Report, the Construction and Asset Management Consultant (the “CAMC” Report) and the Goodwin Report.

# Lee summarized the competing assessment of the claims as follows:

Principals’ Claim			$185,183

Goodwin Assessment		$77,307

Jeffery Assessment			$75,625

WT Partnership assessment	$50,886

# A table comparing the competing assessments of each of the items was given by Lee as follows:

| Item | Description | Principal $ | Goodwin $ | Jeffery $ | WT Partnership $ |
| --- | --- | --- | --- | --- | --- |
| 1.1 | Reinstatement to Original Condition | 18,000 | 9,818 | - | 2,400 |
| 1.6 | Surveys | 10,200 | - | 10,200 | 2,880 |
| 4.7 | VSL Supervision | 7,000 | 7,700 | 7,000 | 1,800 |
| 4.10 | Car Park Entry Ramp | 7,423 | 7,328 | 7,423 | 1,840 |
| 5.2 | ARC Columns | 9,540 | 2,955 | 9,540 | 1,505 |
| 9.14 | Laminex Kitchen Bench Tops | 3,298 | 228 | - | 275 |
| 9.16 | Size of Granite Bench Tops | 5,891 | 220 | - | 333 |
| 9.17 | Width of Granite Island Benches are Narrower than Specified | 8,168 | - | - | Nil |
| 10.4 | Grand Master Keying System | 5,201 | 265 | 3,119 | 600 |
| 13.1 | Shop Drawings | 11,680 | - | 11,680 | 6,000 |
| 13.4 | Alucobond to Balcony Columns Installed in 4 Sections in Lieu of 3 | 6,128 | - | 900 | 1,500 |
| 14.2 | Balcony Ceilings | 16,800 | 4,643 | 12,390 | 3,350 |
| 16.14 | Opening Sashes | 6,610 | 832 | 1,200 | 1,500 |
| 17.2 | Rebated Meeting Stiles | 10,720 | 6,772 | 594 | 810 |
| 17.14 | Door Schedule Discrepancies | 5,804 | 933 | 5,254 | 810 |
| 17.16 | Flush Doors with Waterproof Ply | 22,140 | 19,058 | 6,325 | 11,450 |
| 19.3 | Fibre Cement Supports | 4,750 | - | - | 375 |
| 20.11 | Alternative Floor Finish to Gallery | 19,580 | 9,680 | - | 10,208 |
| 24.1 | Lift Door Jambs and Reveals Not Installed | 6,250 | 6,875 | - | 3,250 |
|  | TOTAL (excluding GST) | $185,183 | $77,307 | $75,625 | $50,886 |

# In cross-examination, counsel for the defendants questioned Lee about two deduction variations in particular: the car park entry ramp and the shop drawings.

# With regard to the car park entry ramp, Lee said that there was some “confusion” between the architectural and structural drawings. He said that Kane had constructed the car park entry in accordance with the structural design. Nevertheless, under cross-examination, Lee conceded that he was not a structural engineer (or an architect) nor had he read anything that the structural engineer, Keith Long, had said about the car park entry ramp. It is in this way difficult to see how Lee could have concluded that Kane had in fact constructed the car park entry in accordance with the structural designs.

# In his report, Lee stated his opinion that the shop drawings should not constitute a deduction variation. However, during cross-examination he acknowledged that this opinion was formed based on the information provided to WTP by Kane. Lee also admitted to making assumptions about the shop drawings without having seen them.

Costs to Complete

# Lee said that WTP were instructed by Kane to quantify the outstanding works for the following four trades (from 6 October 2000 onwards): the rendering works; the Alucobond cladding; fire spray and the shower screens.

# In Lee’s opinion, “a fair and reasonable cost to complete” the works was $40,645 (excluding GST). In contrast, the principal’s claim was for $95,247 (excluding GST). Lee considered, however, that the principal’s claim stood “well outside expected industry parameters”.

# In cross-examination, counsel for the defendants questioned Lee on the methodology he employed in calculating the costs to complete. Lee conceded that the four trades selected were given to him by Kane. He also agreed that he had not spoken to the defendants and that he relied upon the information provided by Kane to make his assessments. It appears that Lee obtained most documents directly either from Kane’s project manager, Tivendale or from the contract administrator, Le Hy Ta.

# Counsel for the defendants questioned Lee about each of the four trades forming the basis of his calculations for the costs to complete.

# With regard to the first trade, the rendering works, Lee assessed the costs to complete at $2,205. Counsel showed Lee photographs of rendering in certain areas; and Lee said that he was not aware of (and had not taken into account) such rendering that had apparently occurred subsequent to termination.

# As for the Alucobond cladding, Lee assessed the costs to complete to be $20,750. He said that he had assessed the supply and installation of Alucobond at $250 per square metre. He agreed that he was not shown any documents that would have made clear that the actual cost – as shown by invoices and actual prices paid – was in fact $295 per square metre (i.e. $45 per square metre more than that assessed by Lee).

# Lee assessed the costs to complete for the fire spraying to be $8,250 in total. He said that he was not shown RFI 83, which was a Kane document showing Jeffery what amount was allocated with respect to this trade (and which presumably may have assisted Lee in making his calculations).

# For the shower screens, Lee calculated the cost to complete to be $9,440. That is, 16 uninstalled screens valued at $590 each. The principal, however, claimed costs to complete of $13,806. Lee said that he had not seen the invoice dated 17 November 2000 (as produced by counsel for the defendants) from Premium Showers and Robes which stated that the remainder of works totalled $9,510 and that this amount had been invoiced to Stacks Properties. Nor had Lee seen the Kane document which showed the uncompleted work being that of 40 uninstalled mirrors from Expert Glass totalling $4165. Lee testified that the mirrors had been provided to WTP for assessment as a cost to complete that was part of the shower screen item.

# The assessment and analysis by Lee was of limited assistance as his views were principally based on information provided by the plaintiff.  This constrained the independence of Lee and is a factor I have taken into account.

(14) GILFILLAN

# The fourteenth witness for the plaintiff, Kenneth Struan Gilfillan, is a qualified architect. His Order 44 statement was prepared at the request of the plaintiff’s solicitors.

# Gilfillan was engaged to “provide an expert opinion on the variations claimed by Kane in respect of the Boilerhouse project”; however he was not instructed to assess the quantum of the variations and therefore “[made] no comment on the valuation of the variations assessed”.

# For the purpose of preparing his report, Gilfillan stated that he was provided with the contract dated 20 August 1999; the contract drawings and specification; folders of documents relating to variation claims including RFIs, superintendent’s directions, invoices, notices of price variations and variation approvals; and “relevant pleadings” provided by the plaintiff’s solicitors, Deacons.

# Gilfillan said that during his engagement he met with Tivendale on three occasions, both on-site and in Tivendale’s office, and that the duration of those meetings may have been “a day at a time”.

Variations

# Gilfillan said that he concentrated on the variations which “had not been approved by the Superintendent”.

# Gilfillan’s report concluded that the majority of the variations claimed by Kane “required additional labour and materials and were variations under the contract”.

# Gilfillan further stated that the builder was retained under a AS 2124 form of contract which was “not a design and construct contract” and he concluded that “a significant number of variations resulted from deficient, poorly coordinated and inconsistent contractual documentation”.

# During cross-examination, Gilfillan agreed that he had assessed the variations by considering what each “rival” side had said about them and coming to a conclusion. Gilfillan further agreed that this process that he had engaged in was similar to that which would have occurred had he been making a determination as an arbitrator at VCAT where he was a sessional member.

# Gilfillan’s assessment of the variations, as listed in Appendix 1 of his report, may be summarised as follows:

| Item | YES: A Variation | NO: Not a Variation | Other |
| --- | --- | --- | --- |
| 1. Repair to existing water service |  |  |  |
| 2. Excavation in Rock |  |  |  |
| 3. Break Out and Remove Concrete |  |  |  |
| 4. Extra for Galvanized Fire Service |  |  |  |
| 6. Car Park Concrete Beam |  |  |  |
| 8. Stormwater Drain Crossing |  |  |  |
| 9. Extra Ground Floor Slabs |  |  |  |
| 12. Agricultural Drain Lift Motor Room |  |  |  |
| 13. Window W3 – Stormwater Pipe |  |  |  |
| 14. Fire Proof Slabs & Brick Wall |  |  |  |
| 19R. Pilkington Evergreen Glazing |  |  |  |
| 20. Slab Penetration Infills |  |  |  |
| 21. Plywood Backing with Quietel |  |  |  |
| 22R. Fire Detection System |  | × |  |
| 23. Additional Walls |  |  |  |
| 26. Pressed Metal Door Frames |  |  | No claim for extra cost made by builder. |
| 29. Fire Rated Doors and Frames |  |  |  |
| 32. Extra to Conceal Columns to Second Floor Apartments |  |  |  |
| 33R. Suspended Slab-Stair 3 |  |  |  |
| 35. Terrace Gutters |  |  |  |
| 36. Extra Rheinzinc |  |  |  |
| 37. City West Water Fees |  |  |  |
| 38. Extra Fire Dampers and Collars |  |  |  |
| 39. Additional Ductwork and Grilles |  |  |  |
| 40. Changes to PMDF (Pressed metal door frame) |  | × |  |
| 41. Doors D7, D10.08 and D13.08 |  |  |  |
| 42. Eagle Light Fittings |  |  |  |
| 44. Cranked Beam 3B26 |  |  |  |
| 46R. Roof Plant Platform and Handrail |  |  |  |
| 47. Toilet Accessories |  |  | “I would regard a 10per cent overrun as the maximum overrun acceptable – i.e. $800” [variation acceptable]. |
| 48. Shower Screens |  |  | Says that a 10per cent overrun is the maximum overrun acceptable – i.e. $1,000 variation acceptable. |
| 49. Demolition of duct at chimney |  |  |  |
| 52. Royal Wall Hung Pans |  |  | Only two (rather than five) WC2s “can be supported as additional works under the contract”. |
| 53. Preseal to Sadler Tiles |  |  |  |
| 56. Staircase 7 – Apartment 8 |  | × |  |
| 57. Wardrobes PC Sum |  |  | Says that a 10 per cent overrun is the maximum overrun acceptable – i.e. $1,500 variation acceptable. |
| 60. Additional Wall in Office |  |  |  |
| 62. Gallery Entrance Gates |  |  |  |
| 63. Additional Brickwork / Parapet |  |  |  |
| 64. Cutting of Slab in Apartment 10 |  |  |  |
| 65. Lift Motor Room Ventilation System |  |  |  |
| 66. Laundry Floor / Wastes |  |  |  |
| 67. Adjacent Building Plumbing |  |  |  |
| 69R. Bluestone to Courtyard |  | × |  |
| 70. Additional for Water Tapping |  |  |  |
| 71. Penetration through Beams - Mechanical |  |  |  |
| 72. Add CFC for Laundries |  |  |  |
| 73R. Additional Track Lighting |  |  |  |
| 74. Additional Tiles to Second Floor |  |  |  |
| 76. Skirting Tiles to Ensuite Cupboards |  |  |  |
| 77. Change to Gallery Light Wiring |  |  |  |
| 78. Timber Flooring |  |  |  |
| 79. Add 36W Gallery Light |  |  |  |
| 80. Gas Cooktop GPO’s |  |  |  |
| 81. Charge floor waste in Unit 5 |  |  |  |
| 82. HWS to Gallery and Upper Tea Room |  |  | “This is a negative variation and the Principal is entitled to the applicable saving.” |
| 85. Clean off sign on West Elevation |  |  |  |
| 86. Integra Basin |  |  |  |
| 88. Isolator Switches |  |  |  |
| 92. Ductwork for Rangehood Exhaust |  |  |  |
| 93. Rheinzinc Dimension Alterations |  |  |  |
| 94. Structural beam at apartment 10 terrace |  |  |  |
| 95. Relocate bath, Apartment 9 |  |  |  |
| 96. Weatherproof Hopleys Trusses |  |  |  |
| 97. Alter Stair 2 at Level 3 Landing |  | × |  |
| 101. Detector Valve Booster |  |  |  |
| 102. Recessed Downlights |  |  |  |
| 103. Lift Shaft – Additional Inserts |  |  |  |
| 104. Additional Fire Rates Boxes in Ceiling Level 2 |  |  |  |
| 105. “Florida Pan” in Apartments 7 and 10 |  |  |  |
| 106. Rheinzinc at North East Elevation |  |  |  |
| 107. Additional Beam at Main Entry Gates |  |  |  |
| 108. Gallery Entry Steps |  |  | Works not proceeded with and no claim made. |
| 113. Alternative Recessed IDF Unit |  |  |  |
| 115. Wiring for Toilet exhaust fans air roof |  |  |  |
| 116. Windows WG13 and WG14 |  | × |  |
| 117. Pivot Doors Floor Springs |  |  |  |
| 118. Fire Rating to Soffits at Second Floor Terrace |  |  |  |
| 119. Install extra cable for Apartment Submains |  |  |  |
| 120. Alterations to Brick Pier for Fire Booster Assembly |  |  |  |
| 121. Gallery Entry Columns and Lintel Propping |  |  |  |
| 122. Alterations to basin to suit vanity heights |  |  |  |
| 123. Redirect Fire Services |  |  |  |
| 124. Gas Fees |  |  |  |
| 125. Pre-primed MDF Skirtings |  |  |  |
| 126. Additional Penetrations of Roof for Toilet Exhaust |  |  |  |
| 127. Existing Floor Levels surveys to apartments 1, 2 and 3 |  (“assuming the work is not already included in 78R”) |  |  |
| 128. Aluminium Screen Frames |  |  |  |
| 129. Additional Phone points in Units 5, 6 and 7 |  |  |  |
| 130. Floor Levelling to Laundry Areas |  |  |  |
| 131. Office Bulkhead Hydraulic and Mechanical Alterations |  | × | “only additional lengths of service pipe, ducts, supports can be supported as a variation together with adjustment of cost of light fittings involved” |
| 133. Relocation of Exit Light on Second Floor |  | × |  |
| 134. Plasterboard to Underside of Stair 2 |  |  |  |
| 135. Access Panel to Bathroom Hobs |  |  |  |
| 136. Chasing of Conduit on Chimney |  | × |  |
| 137. Additional Downlights in APT 12 and APT 11 Cable Modifications |  |  |  |
| 138. Office Entry Brick Nibs |  |  |  |
| 140. Brass Strips on Timber Floor Edges |  |  |  |
| 141. Relocate Electrical Conduit at Office Entry |  | × |  |
| 142. Pendent Light Cover Plates |  |  |  |
| 143. Relocation of External Lights at Apartments 4, 6 and 10 |  |  |  |
| 144. Support Studs for Alucobond Soffit on West Balcony |  |  |  |
| 145. P50 Shadowline for the FR Ceiling |  |  |  |
| 146. Alter Car Park Entry to Heritage Requirements |  |  |  |
| 147. Snibs for Clerestory Windows |  |  |  |
| 148. P50 to Lift Door Edge |  |  |  |
| 149. Levelling to Bedrooms Carpet |  |  |  |
| 150. Flashings at Base of Rheinzinc Area (North East) |  |  |  |
| 151. Ardit to Kitchen Areas |  |  |  |
| 152. Variation to Sanitary Tapware |  |  |  |
| 153. Install Hot Plates |  |  |  |
| 154. Addition for Rheinzinc areas due to Hopleys Joists |  |  |  |
| 155. Kitchen Baffle Lights |  |  |  |
| 159. Door Lock Tongues Changed |  |  |  |
| 160. Fire Collars (2) for AC Ducts to Fire Rated Shafts |  |  |  |
| 161. Fire Collars (3) for Third Floor Ducts |  |  |  |
| 162. Additional Drafting |  |  |  |
| 163. Additional Steelwork |  |  |  |
| 164. Ardit to Apartment 12 Balcony |  |  |  |

Domestic Building Contracts Act

# In cross-examination, counsel for the defendants questioned Gilfillan on variation 66 regarding the laundry and floor wastes. In response to this questioning, Gilfillan said that he didn’t think at the time that the Domestic Building Contracts Act applied to this item. However, he also said that he was aware of the Domestic Building Contracts Act and did consider it when he was assessing the variations.

DEFENDANTS’ EVIDENCE

(1) SOPOV

Background

# Cole Sopov, who is a sculptor by profession, was the first-named defendant in this proceeding. His wife, Norma Rose Walker, was the second-named defendant.  Both Sopov and Walker are directors of the third-named defendant, Stacks Properties. Collectively, these three defendants are referred to as the principals. Sopov stated that, prior to him becoming the registered joint proprietor of the Boilerhouse project on or about 22 March 1996, he was a lecturer in fine arts at Monash University from 1977 until 1995.

# Sopov stated that, in April 1997, he was introduced to Ross Carpenter who was to subsequently become the design architect for the Boilerhouse project. Sopov further stated that, given Sopov’s vision for the Boilerhouse project and his background and experience in art and design, he took “an active role in the design process”. Sopov stated that the design architect had costed the project by employing quantity surveyors, Slattery Australia Pty Ltd (“Slattery”). Sopov further stated that the design architect prepared all of the documentation for the tender.

The Tender Process

# Sopov said that he invited six building companies to tender for the Boilerhouse project and that Kane Constructions was one of three companies short-listed for interview. Sopov stated that he met with Peter Cusack, representing Kane, three times, namely, on 20 April 1999 and 10 May 1999 at Sopov’s office and once at the Bolierhouse on a date that Sopov said that he could not recall. Sopov said that at the first meeting there was “a discussion of the suitability of the use of the Australian Standards General Conditions of Contract AS 2124-1992 for the project”. Sopov further stated that he told Cusack that Kane would win the tender if they could “get their price down to $3.5 million”.

# Sopov said that, on 17 May 1999, Kane submitted an amended tender in the sum of $3,474,000, in which it was stated that the project would be constructed in 26 weeks (130 working days). Sopov said that he informed Kane on 20 May 1999 that theirs was the winning tender. In cross-examination, Sopov agreed that he “expected to get a fixed price on a fixed lump sum contract”.

# Sopov said that the principals appointed Tony Hampton of Tony Hampton Architects Pty Ltd as the project superintendent, with whom Sopov stated that they signed a Client and Architect Agreement on 28 May 1999 for Contract Administration Services of General Conditions of Contract AS 2124-1992 (Sopov said that the architect, Ross Carpenter was unable to be the superintendent because that was unacceptable to the bank). Sopov further stated that Keith Long & Associates were appointed for the structural works; Fryda Dorne for mechanical and electrical services; Clements Consulting Group for hydraulic services; and Duncan and McKenzie as building surveyors.

# Sopov said that works began on the site on 31 May 1999. Sopov further said that, on 3 June 1999, he attended the first site meeting on behalf of the principals and that site meetings were to be held fortnightly. Sopov stated that by the time that the builder had abandoned the site in October 2000, there had been 34 site meetings – all of which had been minuted – and all of which Sopov had attended on behalf of the principals.

The Contract

# Sopov stated that Stacks Properties, in conjunction with Slattery, had prepared the contract for the project and that it was to be signed by 7 June 1999, by which time the builder would provide a construction program. Sopov further stated that this program was not provided until 3 August 1999, despite the builder being reminded about it at the next four subsequent site meetings.

# Sopov said that the builder did not sign the contract by 7 June 1999 and instead sent Stacks Properties a letter on 17 June 1999 requesting a meeting to discuss various contractual issues. Sopov said that that meeting took place on 30 June 1999 at the builder’s offices and was attended by himself; Tivendale and Cusack of the builder; and Hampton, the superintendent.

# Sopov stated that the builder said that they would not sign the contract unless Sopov and his wife signed the contract as individuals. Sopov said that he was reluctant to acquiesce and that the builder’s demands made him angry; but he nevertheless agreed because he concluded that he had no other option at that stage of the project. Sopov stated that he subsequently confirmed the agreement, as requested by the builder, by way of letter on 1 July 1999, asking them to sign the contract.

# Sopov said that Hampton resigned as superintendent on 16 July 1999 and that Slattery was subsequently appointed to that role. Sopov said that he did not know why Hampton had resigned; although he conceded, in cross-examination by counsel for the plaintiff, that it involved a dispute over Hampton’s payment. Sopov said that Hampton subsequently sued him for unpaid fees.

# Sopov also said, in re-examination, that the builder had never raised any complaint about Slattery assessing the progress claims while Hampton was the superintendent.

# Sopov stated that he received a letter from the builder, dated 21 July 1999, that complained about both the contract and Slattery’s appointment as superintendent. Sopov said that he had no difficulty with a quantity surveying company like Slattery being the superintendent, as opposed to an architect as apparently preferred by the builder. Sopov said that, consequently, a meeting between Stacks Properties, Slattery and the builder was convened on 23 July 1999 in order to resolve the issues.

# Sopov said that Slattery sent a letter to the builder with a proposal from Stacks Properties to resolve the outstanding issues; however the builder insisted that the contract be amended to its requirements, otherwise it “threatened to walk out on the project”. Sopov further stated that the builder reiterated its demands in a letter to Slattery on 6 August 1999 and that, subsequently, Sopov stated that “considering that construction was by now in its third month and taking into account the ongoing tension between the parties [Sopov] decided to accept all of the Builder’s amendments”. Sopov stated that he, his wife and Stacks Properties signed the contract on 20 August 1999 and that it stated that “10 December 1999 was the Date for Practical Completion”.

Sopov’s Concerns about the Progress of the Project

# Sopov said that, in his opinion, the builder commenced work without any satisfactory program; lacked experienced staff allocated to the project; had an incorrect set-out of the works; failed to protect the works from damage during site activities and inclement weather; had poor coordination of sub-contractors and an excessive use of day labour; and had a large amount of defective works that needed to be rectified. Sopov said that he believed that these factors were the “principal reasons” why the builder had failed to meet the original date for practical completion. As to allegations by the plaintiff’s side that Sopov interfered too much in the day-to-day activity of the project on-site, Sopov conceded, in cross-examination by counsel for the plaintiff, that he was “regularly involved in … giving instructions to the builder’s on-site staff”; although he claimed that these “instructions” were more by way of “friendly discussion” rather than directions or decisions about the work.

# Sopov said that Jeffery suggested to him, on or about September 1999, that the date for practical completion be extended to 31 March 2000. Sopov said that he agreed in principle to the proposal so that the builder could complete the project without being concerned about the imposition of liquidated damages (to be calculated at the contract rate of $1,100 per calendar day); however upon receiving a revised construction program from the builder on 8 October 1999 wherein it demanded $144,835 for extension of time costs, Sopov stated that he withdrew his in-principle consent for the revised program.

# Sopov maintained his belief that all extension of time costs had been properly assessed by the superintendent and that Sopov had not interfered. Sopov further said that Slattery eventually suggested that an independent consultant assess decisions on extension of time costs and that, consequently, Degenhardt became involved. Sopov said that Degenhadt was employed, not because Slattery were incompetent to make the assessment (as suggested by counsel for the plaintiff), but because the builder (and Forster in particular) was difficult to deal with and being “negative to the whole process”.

The Events of August-October 2000

# Sopov said that, on 24 August 2000, he received a tax invoice from the builder for work completed in the sum of $340,562 (plus GST). Sopov further said that, on 28 August 2000, Stacks Properties paid the builder $132,618 (including GST), that amount being $340,562 on payment certificate for progress claim number 14 less a sum of $220,000 in liquidated damages that Stacks Properties imposed.

# Sopov stated that, on 8 September 2000, the builder served notice on him and his wife alleging that they were in breach of the agreement under cl.42.1 since the builder had not been paid $1,216,546, that being the amount of the contractor’s progress claim number 14. Sopov stated that, on 1 September 2000, the builder submitted progress claim number 15 for $1,572,304.91 and that the superintendent subsequently issued payment certificate number 15 for the sum of $220,800. Sopov further stated that, by way of letter dated 11 September 2000, the principals replied to the builder’s show cause letter of 8 September 2000; and that the builder responded by way of letter on 13 September, to which the principals again responded on 15 September 2000.

# Sopov said that, on 18 September 2000, following this exchange of letters, the builder gave the principals notice that it had suspended the whole of the work under the contract. Sopov stated that on 21 September 2000, the principals issued the builder with its own notice to show cause, alleging, among other things, that the builder had breached cl.33.1 of the contract by suspending the work and requiring the builder to show cause in writing by 4:00pm on 29 September 2000 as to why the principals should not exercise its rights under cl.44.4 of the contract. Sopov said that the builder subsequently replied, by way of letter of 28 September 2000, denying that the principals’ notice to show cause document had any “validity or effect”.

# Sopov stated that he attended the site at 9:15am on the morning of 26 September 2000 ready to participate in the fortnightly site meeting scheduled for 10:00am that day; but he found the site locked and no-one present. Sopov further stated that he then arranged for the state of the works at the site to be videotaped by his friend, Victor Pandov; and this videotaping also occurred the following day, 27 September 2000. Sopov rejected the suggestion, made by counsel for the plaintiff, that he had the works videotaped with a view to taking the work out of the builder’s hands or taking possession of the builder’s plant and equipment.

# Sopov said that when he visited the site on 26 and 27 September 2000, he noticed that, despite the absence of the builder’s personnel, “the Builder’s site sheds and all of its construction plant and equipment were on-site”. However, Sopov further stated that, when he again attended the site on 2 October 2000, all of the builder’s material (except for one site shed) had been removed, and that furthermore, all site records were removed; sewerage pipes and electricity were disconnected; five temporary powerboards had been removed from each floor; and electricity lines had been cut and terminated. Sopov said that the builder’s actions had a devastating effect on him. Sopov further stated that, at that time (on 2 October 2000), he did not engage in any discussion with the superintendent’s representative, Jeffery. However, in response to counsel for the plaintiff highlighting that Sopov’s pleadings indicated that a meeting with Jeffery took place on that day (together with his solicitor, Mr Archer), Sopov stated that he could not recollect the meeting and he further said that he had not deliberately lied earlier in his testimony about the meeting not having taken place.

# Sopov said that, on 2 October 2000, the principals gave notice to the builder under cl.44.4 of the contract, “taking the whole of the work remaining to be completed on the project out of the hands of the Builder”. Sopov further stated that the principals’ solicitor, Mr Archer, faxed the builder’s solicitors, Deacons, stating, among other things, that the builder’s removal of the construction plant and equipment was effected without the consent of the principals or the superintendent in accordance with cl.29.2 of the contract and therefore represented repudiatory conduct.

# Sopov said that the builder’s solicitors, Deacons, replied to Archer’s facsimile on 5 October 2000, stating, among other things, that “an obligation on the part of the Principals to pay the sum of $1,216,546.64 to the Contractor crystallised on 15 August when the Superintendent failed by that date to issue a certificate in respect of our client’s progress claim no. 14 dated 1 August 2000”.

# Sopov said that he attended his solicitor’s office on 6 October 2000 and that his solicitor advised him to draw down on the security held by the principals pursuant to the contract. Sopov said that he signed an authority allowing his solicitor to draw down the security; which his solicitor duly did. Sopov said that he did not think about any need to give the builder written notice of this action, and that instead, he simply acted according to his legal advice. Sopov stated that the drawing down of the security was regarded by the builder as repudiatory conduct on the part of the principals, as they indicated in Deacons’ letter to Archer sent later that day. Furthermore, Sopov stated that Deacons’ letter said that the builder had accepted the alleged repudiatory conduct by the principals.

# Sopov stated that, subsequent to this correspondence, he consulted John Pilley of John L. Pilley – Barristers and Solicitors, who, “in negotiation with Deacons … reinstated the bank guarantee to the Builder’s satisfaction”.

Completion of the Works after the Exit of Kane Constructions

# Sopov said that the project was substantially completed by 31 March 2002. He said that, together with the labour and contribution of his own family members, he used some of the builder’s sub-contractors, as well as other contractors, to complete the works. Sopov rejected suggestions by counsel for the plaintiff that he had delayed completing the project because he believed that the builder would be paying liquidated damages.

# Sopov stated that he believed that, at the time the works were taken out of the builder’s hands, there “were many defects that had to be rectified”. Sopov said that Jeffery compiled a list of these defects. Sopov stated that, on 30 August 2002, the superintendent issued a certificate certifying the amount of $1,181,548 as the cost incurred by the principals in completing the work. Sopov further stated that, on 28 April 2003, the superintendent issued a final certificate, pursuant to cl.42.8 of the contract, certifying that $1,515,199 was the amount due by the builder to the principals.

Deduction Variations

# Sopov said that there were components of the work undertaken by the builder that were not in the contract and that these were “either omitted or deleted from the work by the Builder, or constructed defectively”. Sopov said that this work had been “valued by the Superintendent as deduction variations in the sum of $617,200”.

# In cross-examination, Mr Digby for the plaintiff suggested to the Court that many of these deduction variations were indicative of the principals’ “pedantry”.  Mr Digby cited, as examples, alterations required to the Custom Chassis work in connection with metal balustrades; internal doors; and the lack of bins in the kitchen on slide-out drawers.

Variations Claimed by the Builder

# Sopov said that there were some variations claimed by the builder that the superintendent assessed but about which Sopov disagreed. Sopov further said that he regarded the process of approving variations to be one in which both the principals and the builder should be able to express a view; noting in particular that he wished to have the opportunity to object to variations if he disagreed with them. Sopov said that he was also concerned about the effect that the approval or otherwise of variations had on extension of time claims.

# In cross-examination, Mr Digby questioned Sopov in detail about numerous non-price variations (“NPV’s). These included, although not exclusively, NPV 13 (Stormwater Pipe); NPV 14 (Fire Proof Slabs and Brick Wall); NPV 20 (Slab Penetration Infills); NPV 34 (Relocation of Downpipe); NPV 35 (Terrace Gutters); NPV 36 (Extra Rheinzinc); NPV 44 (Cranked Beam); NPV 70 (Water Tapping); NPV 78 (Timber Flooring); NPV 80 (Provision of General Power Outlets); and NPV 123 (Redirection of Fire Services). While the plaintiff had argued that these were valid variations, Sopov contended that, in many cases they were not and that the work required should have been obvious to any competent builder.

# With respect to the quantum meruit claim made by the builder, Sopov stated that the claim incorrectly included “costs for defective work, the rectification of that defective work, rectification of works damaged by the weather for which the builder was responsible and all other costs incurred by it in correcting its own errors”.

Costs to Complete

# The costs to complete that Sopov claimed on behalf of the principals can be divided into the following five categories: bank expenses; loss of income on rent; additional consultants’ expenses; GST incurred on the sale of apartments; and other (miscellaneous) costs.

# In relation to bank expenses, Sopov stated that the principals had incurred additional bank expenses amounting to $620,408, as a result of the breaches of contract by the builder.

# On loss of income on rent, Sopov stated that the principals lost rental income, amounting to $396,600, as a result of the builder not completing the works on time.

# On the issue of additional consultants’ expenses, Sopov stated that the principals had incurred additional expenses on consultants in the sum of $168,487.10, as a result of the builder’s breaches of contract.

# In relation to GST incurred on the sale of apartments, Sopov stated that, since the principals had been unable to sell the apartments prior to the introduction of GST on 1 July 2000 as a result of the builder’s failure to complete the work on time, the principals had incurred an additional expense of $76,330.

# As to other costs, it was suggested in cross-examination that numerous items had been included by Sopov in the costs to complete that should not have been reasonably included and that they [the plaintiff] were “mystified as to how there could be any relation [of the amounts claimed] to the cost of completing the works”. For example, Sopov conceded that superannuation costs for his family amounting to about $170,000 in each of the years ending 30 June 2001 and 30 June 2002 had been included, as well as RACV membership and insurance on his wife’s motor vehicle. Sopov stated that he was unsure of the rationale for each of the items that had been submitted and unclear whether they had been submitted on his instruction or that of his accountant. In any case, Sopov argued that whatever was in the certificate, as accepted by Jeffery, should form the basis of the costs to complete.

(2) JEFFERY

Background

# Trevor Jeffery, the second defence witness, is a Quantity Surveyor. In his witness statement, he stated that he was an employee of Slattery Australia Pty Ltd (“Slattery”) from June 1998 until August 2000. Slattery was retained by Stacks Properties to carry out cost planning services on the Boilerhouse project. Slattery was also retained by the National Australia Bank to prepare the initial report and subsequent monthly reports on the progress of the Boilerhouse project.

# Jeffery said that he was commissioned to act as the superintendent’s representative on 20 July 1999. He said that, at that stage, the building contract had not been signed by either party. The builder initially objected to Slattery being appointed as superintendent. Jeffery stated that he commenced working in his own practice, Construction & Asset Management Consultants (“CAMC”) on 7 August 2000 and that, with the full agreement of Slattery, the principals retained CAMC and Jeffery to fulfil the role of superintendent.

# There were a number of important issues that arose in relation to this witness, and they were dealt with in cross-examination, namely:

# whether he was competent in his role as superintendent and properly 	understood his role;

# whether he faced a conflict of interest in his dual role as superintendent and 	bank auditor;

# whether he had breached his duty as an independent superintendent under 	cl.44.6 in “ascertaining” the costs incurred for completion and substantiating	costs included in the costs to complete;

# whether he had caused a breach of cll.35.5 and 23 of the agreement by not 	properly dealing with and determining the plaintiff’s extension of time 	(“EOT”) entitlements; and

# the ethical question of whether in his role as superintendent he had been 	dominated by the principal.

Problems with Builder’s Key Personnel

# According to Jeffery, the alleged over-involvement of Sopov in the project was a direct result of the builder’s delay in completion, the builder’s inability to ensure staff continuity, and its lack of experience in project administration.

# Jeffery cited as especially problematic the lack of continuity in site supervisors. For instance, Trevor Williamson (seven weeks) was followed by Peter Omond (14 weeks) who was finally replaced by Glenn Skarajew (approximately one year). Jeffery further stated that there was no handover between Omond and Skarajew.

# Jeffery also cited the absence of a project manager as difficult, stating that Tivendale was on leave during major wall rectification works. Jeffery stated that most internal walls were demolished and had to be rebuilt because of the builder’s incorrect construction.

# Jeffery said that certain critical shop drawings for the external façade were not provided which meant that the building could not be made waterproof. He also said that despite the fact that another project manager was provided in Tivendale’s absence, the shop drawings were still not supplied at the critical time.

# Jeffery stated that he attended a meeting with Isaacson and Sopov at the builder’s office in Richmond on 14 February 2000 so that the directors could be made aware of the problems being experienced on-site. Jeffery stated that the meeting discussed the status of the Alucobond shop drawings, the progress of works and the number of defects generally.

# Jeffery said that the builder acknowledged the problems and said that it was committed to change, with Isaacson affirming a commitment to “regrouping”, thereby taking a new “proactive, positive” approach to the project. However, Jeffery maintained that any change only lasted around a month, before standards dropped again.

Role of the Superintendent and Role of the Bank Reporter

# In cross-examination, Jeffery stated that he was aware of Kane’s concern as to Slattery’s dual role as both superintendent’s representative and reporter to the bank concerning the project’s progress. However, during re-examination, Jeffery said that, to his knowledge, Kane never actually went so far as to object to his dual role of bank reporter and superintendent.

# In the giving of his evidence, Jeffery produced a letter dated 26 July 1999 clarifying the ongoing role of consultants in the project. It was put to Jeffery that, in a letter written by Slattery, the roles of superintendent and bank reporter were to be taken by Jeffery and Fulton respectively in order to avoid a conflict of interest. However, in cross-examination, Jeffery conceded that the bank reports were largely completed by him and the usual practice was for Fulton to then read over and approve them, with occasional amendments. Jeffery said that this was part of Slattery’s quality assurance procedure.

# It is unclear whether Jeffery was aware that Slattery had told the bank that Fulton would not be involved with the role of superintendent. Jeffery said that he had just “followed the company procedures”.

# Jeffery denied that Mr Crawford Fulton, one of the associates of Slattery, had “no intimate conversance” with what was happening on the project, although he conceded that he did not take part in monthly site inspections. Jeffery said that he had “not really thought about drawing a distinction” between his role as the bank’s quantity surveyor and superintendent under the contract.

# Jeffery said that he was not aware of negotiations between Sopov and Slattery regarding the appointment of a superintendent until after Fulton had told him that Slattery had been appointed and that it was considering appointing Jeffery as its representative. Jeffery further stated that he had never before acted as certifier as well as superintendent under a construction contract.

# Jeffery said that he understood that his role in relation to the bank involved independently evaluating the cost of works being undertaken on the project; advising the bank about the progress of the project; and advising the bank about how the project was going financially, compared with the original Slattery projections.

# Jeffery said that he adopted a proposed budget already prepared by Slattery Australia, namely, “Construction Costs – Stage 1”, prepared by Mr Des Lynch.

# Jeffery further said that he provided an initial report dated 27 August 1999 detailing the proposed budget which referred to a realistic funding budget of $3.65 million. He said that he informed the bank that a more likely finishing date would be the end of January 2000 and allowed $176,000 contingency in relation to the construction cost.

Jeffery’s Alleged Lack of Independence

# In cross-examination, Jeffery conceded that many items in the cl.44.6 certificate were not certified independently by him in his capacity as superintendent. Nevertheless, Jeffery denied that he made an eleventh hour submission of revised progress certificates 14 and 15 (i.e. made just before the 12.00pm deadline on 6 October 2000) in order to place the principals in a better position in the argument that they were having with the builder. Jeffery said that neither Archer nor Sopov had ordered him to make the submissions at that time.

# Jeffery was cross-examined about the letter dated 21 January 2000 which was a notice of dispute from the builder, wherein it was alleged that Jeffery was not prepared to make independent determinations and was dependent on the whim of one of the principals, namely, Sopov.

# Jeffery said that he did not recall a conversation with Forster shortly before 21 January 2000 in which he allegedly said that he would not make any decisions concerning the contract without the approval of Sopov.

# Jeffery further said that he did not recall how or if the allegations made by Kane in the letter dated 21 January 2000 had made an impact on him. Jeffery said that his letter of reply dated 2 March 2000 came five weeks later. The delay was, according to Jeffery, in the hands of Slattery. He said that he did not respond personally, despite the personal nature of the allegations, as he felt bound by Slattery’s Quality Assurance Program.

# Jeffery further said that he also recalled long discussions with Fulton in which it was decided that they would wait until certain steps had been taken in relation to the notice of dispute before responding to the letter. Jeffery said that he did not agree that the reason for his delay was that he agreed with the allegations being made.

Time Extension Claims

# Jeffery stated that, from time to time, one or both of Stacks Properties and the builder did not accept Jeffery’s assessments of the EOT claims made by the builder. Jeffery further stated that the builder said that it would provide a construction program by 7 June 1999, however it did not provide one until 3 August 1999.

# With regard to the notice of delay issued by the builder on 17 September 1999, wherein the builder claimed that the principals were responsible for the delays in production of steel shop drawings, Jeffery said that he found no basis for a valid EOT. Jeffery said that he suggested to Sopov that the completion date should be extended without applying liquidated damages.

# On or about 8 October 1999, Jeffery apparently received a letter from the builder entitled “Construction Program”. Enclosed with that letter was a revised construction program and modified completion date for 31 March 2000. The new projected completion date included a total of 66 days EOT. According to Jeffery, the builder acknowledged that 15 of those days were the result of the builder’s own issues. Jeffery further stated that, in that letter, the builder requested the amount of $144,835 in delay costs, which amounted to $3,490 per day in delay costs; compared with $1,135 per day according to original tender costs, an increase in excess of 200 per cent.

# Jeffery said that, as at 13 September 2000, the builder had claimed 170 days in EOT claims. Jeffery, however, had only approved 11.75 days of this time – a similar number of days that the programming consultant verified as being an acceptable amount.

# In his witness statement, Jeffery claimed that “[a]t no time has the Builder acknowledged the effect that the huge amount of rectification of defective works … [has] had upon the construction program”. Jeffery said that the replacement of most of the internal walls was one such example of rectification works.

# On 21 January 2000, the builder issued a “Contractor’s Notice of Dispute” to the principals relating to EOT Claims 1 to 6. The notice claimed delays of 60 days and seven hours. Jeffery said that Stacks Properties objected to the notice and said that it would wait for his decision as superintendent.

# On 2 March 2000, Jeffery said that he issued a response to each item claimed by the builder in the notice of dispute. Jeffery said that he advised Sopov to engage the services of a programming consultant. Mr Bill Degenhardt of BILD Pty Ltd was subsequently contacted and carried out an evaluation of the EOT claims. Jeffery said that Degenhardt’s report confirmed that Slattery’s assessments were fair and reasonable. A copy of Degenhardt’s response was included in Slattery’s response to the builder’s notice of dispute.

# On 27 March 2000, the builder issued a letter to Stacks Properties voicing its disapproval with the superintendent’s determination. Jeffery then attended a meeting at Slattery’s offices on 6 April 2000 in an attempt to resolve the dispute. However it would appear that little, if anything, was in fact resolved at that meeting. On 14 April 2000, the builder again issued a letter to Stacks Properties, this time blaming the interference of Sopov as an overriding cause of problems. The builder also indicated its intention to take the matter to the Victorian Civil and Administrative Tribunal (“VCAT”).

# On 9 June 2000, Stacks Properties issued its own (principals’) notice of dispute. Jeffery said that this letter contained information to the effect that the extent of disputed delays was one day, and the costs associated with this delay was $547. Jeffery said that, to the best of his knowledge, the builder did not reply to this notice despite a written response being required within a 28-day period. On 21 July 2000, Jeffery said that he personally issued a response to each of the items listed in the principals’ notice of dispute. Following the notice of dispute as issued by Stacks Properties on 9 June 2000, the defendants did not issue any further notices of dispute relating to the EOT claim assessments. However on 25 July 2000, Stacks Properties issued a letter outlining its dissatisfaction with the superintendent’s determination and requesting a meeting to resolve the dispute. According to Jeffery, “the builder” – by which I take it to mean a representative of the builder – verbally stated that, in light of the pending VCAT hearing, there was “no point” in convening a meeting.

# Jeffery stated that, as of 13 September 2000, the builder had claimed $660,135 in costs associated with EOTs. Jeffery said that this equated to the original contract amount of day-to-day running costs of the project increasing in the order of 550 per cent. Jeffery further said that his assessments to that date had approved only $5,675 as acceptable costs, which was an amount less than 1 per cent of the costs claimed.

# In relation to the time lags between the lodgement of the EOT claims and the superintendent’s responses, Jeffery denied that he avoided making determinations. He did however concede that he was “uncomfortable about making an assessment … especially with Time Extension Claim 4, which was for such a large amount of time …”. Jeffery refuted the allegation that he did not feel comfortable and competent as the superintendent to make a determination in relation to these matters. Rather, he said it was a question of getting a “second opinion”, which he said he got from Degenhardt, “via Mr Sopov”, in mid-February 2000. Jeffery said that he provided Degenhardt with the analysis of his own assessments on EOT claims 1–7 as an attachment to a letter, dated 9 February 2000, from Slattery to Degenhardt.

# With respect to communications between the superintendent and the builder regarding the EOT claims, Jeffery admitted that he did not convey to the builder that he had made a determination of the EOTs as superintendent, nor did he send anything certifying what the builder was entitled to. Rather, he simply attached a report from Degenhardt, and thereby in effect, the builder had not received Jeffery’s decision (under cl.35.5 of the contract) on all of the outstanding EOT claims, most significantly EOT 4.

# With respect to EOT Claim 4, Jeffery admitted that he had originally made a “very different” assessment to Degenhardt (allowing 10 days delay to the builder to the value of $11,350), but that he had replaced his own view with that of Degenhardt’s (who advocated zero days). Indeed, during cross-examination, Jeffery agreed that with almost every EOT, he had reflected Degenhardt’s opinion. Jeffery further admitted to using Degenhardt’s exact text. However he rejected the notion that he had simply “rubber-stamped” Degenhardt’s views. Jeffery adamantly maintained that he “formed [his own] opinion” and that it just so happened that Degenhardt’s assessments were “the same”. Jeffery subsequently qualified this statement by admitting that there were “minor anomalies” (only in his recollection regarding EOT 1) where Degenhardt’s assessment was a day or half of one day less than Jeffery’s original assessment.

Variations

# The defendants alleged that Jeffery changed the variation figures to preserve the $176,000 contingency amount, as estimated by him. Jeffery said that he informed the bank in October 1999 that none of the builder’s variation claims up to that point had been approved. This was despite the fact that the builder had by that stage already claimed about $195,000 in extra work done (full assessments later carried out revealed the amount in dispute was in fact $85,241). Mr Digby put it to Jeffery that the reason why he did not approve any of the claims was that he was concerned that the contingency fixed by himself at $176,000 would be very quickly “whittled away”. Essentially, counsel for the plaintiff attempted to point out that Jeffery was concerned with containing costs through, at least partly, rejecting Kane’s variation claims. It was pointed out by Mr Digby that Jeffery was not just the superintendent, he was in fact paid to be the bank’s consultant on the project as well (raising conflict of interest issues as discussed), and that limiting Kane’s variation claims was therefore in his direct interest.

# Jeffery denied these assertions. Jeffery said that, in October 1999, he had allocated $125,000 for variations pending (whereas Kane claimed $195,000). Jeffery said that he had not yet approved the amount of $125,000 as he was “negotiating” with Kane on the disputed amount. Jeffery said that he found this difficult as Kane often “stood by what they were claiming” without making any concessions on costs.

# Jeffery also said that he sought additional information to make sure that he “hadn’t missed anything”. Ultimately, Jeffery said that he refused to approve the amount claimed by Kane as he was “not arriving at their figures” in his calculations.

# Jeffery admitted that Sopov was involved in arriving at figures for variations insofar as Sopov attended some meetings with Kane and Jeffery, and also some meetings alone with Jeffery. Jeffery denied that he was actively attempting to keep the parties separate in resolving variations.

# Counsel for the plaintiff suggested that Sopov’s involvement would have made it impossible for Jeffery to come to an even-handed conclusion about the fair and reasonable amount to be paid to the builder in relation to the variation claims. However, Jeffery disagreed, stating that he considered both Sopov’s and Kane’s financial positions based on the information he had from both sides.

# Jeffery said that he agreed that significant time had elapsed between when the builder submitted the claim and when Jeffery had processed it. Jeffery said that in progress report 3, pending variations were valued at $125,000, and in progress report 4 they were valued at $73,000 (up until that point only $5,658 had been approved).

# Jeffery said that he did not recall what changed his mind about the merits of the variations; however he denied that his dual role as bank reporter (containing and verifying costs) and superintendent (allowing fair and reasonable payment) influenced him. Specifically, Jeffery said that “there was no concern that estimated costs had to be maintained” and that there was no pressure from Sopov to justify what was payable.

# Jeffery said that, by the end of 1999, the builder had claimed $353,000 in variations; of this, $8,900 had been approved. In progress report 6 in February 2000, Jeffery said that he increased the variation amount pending approval to $126,380; but he could not explain why.

# Jeffery said that he was aware of his ability to order performance of extra work as a variation under cl.40. This included the power to direct certain work to be omitted from the contract and the power to vary the way in which works were performed under the contract.

# Jeffery further recalled that in some instances he communicated to the builder that he, as superintendent, expected the builder to provide a credit to the principals in connection with the work as varied. However, he could not recall whether he documented this in any formal way.

# Jeffery said that he did not discuss with the builder matters like credits that it should provide for work “directed to be done differently”, because this was something that would be done at the end of the contract. Jeffery said that any unresolved issues, including variations and time extension issues and credits for work directed to be done differently, would be dealt with at the end of the contract.

Deduction Variations

# Jeffery agreed that the deduction variations had not been made the subject of a formal claim by the defendants under the contract, nor was the builder notified that this would be the case, while Kane was still working on the project, i.e. not prior to September 2000. At trial, Jeffery said that the document “variations not yet claimed” was produced as a running list of deduction variations. He also said that he believed that the builder saw this particular list; however, Jeffery acknowledged that the list was not printed with progress certificate 15 (as at 30 August 2000). Jeffery nevertheless maintained that the document was supplied to the builder, on occasion, as an attachment to progress certificates.

# By the time that progress report 7 was submitted at the end of February 2000, the $176,000 contingency allowed for in the contract was nearly exhausted, with only $7,593 remaining. Jeffery said that he had indicated to the bank that there was a $45,000 deduction that may become applicable in the end cost calculation.

# Jeffery said that Sopov was the person who had identified the possibility of this $45,000 deduction, or at least “some” of the items. Jeffery stated that Sopov did not detail what this amount related to, rather, in effect Sopov had said “will you have a look at this and see whether there is something which could be deducted from the contract price?”. Jeffery conceded that about 10 months after Kane left the Boilerhouse project, Sopov “combed through the specification to find points of complaint in relation to works that had been done up until September 2000”, thus giving rise to literally hundreds of deduction variation items.

# At trial, it was not possible to examine and cross-examine all items claimed by the defendants as deduction variations. The items discussed below therefore merely intend to give an idea of the evidence presented by Jeffery, one of the main witnesses on this point, and are not intended to give a complete evaluation of items claimed.

Plasterboard Walling Work

# In relation to the allegation that the builder did not complete all the required plasterboard work, Jeffery said that Slattery had valued internal plasterboard wall work at $5,395 more than the contract price. Jeffery said that in RFI 117 dated 16 September 1999, the builder suggested alterations needed to be made to the plasterboard walling and requested authorisation to change the way in which the walling and bulkhead work was to be undertaken.

# Jeffery stated that in RFI 189, dated 20 October 1999, the builder referred to discussions about amended wall types and layouts and advised him of changes that it was proposing to make in relation to the plasterboard work. Jeffery further said that on 19 November 1999, he informed the builder that the information attached to RFI 189 was acceptable and “the works could continue based on that information as has been the case to date”.

# Jeffery said that a defects list was compiled from around March 2000. However, the superintendent admitted that he did not bring to the attention of the builder the presence of any other defect or deficiency in the plasterboard work other than the need for the provision of a compliance statement.

Vitrepanel

# Jeffery agreed during evidence that the contract documentation indicated quite clearly that the vitrepanel was to be a render finished material. He conceded however that the vitrepanel was not in fact render finished. In RFIs 159 and 176, the builder communicated concerns about the drawings and conveyed that if vitrepanel was required then there would be a price variation.

# Jeffery agreed during evidence to the suggestion that there was ongoing discussion between himself, the superintendent and the builder in relation to which sample would be approved for the CFC cladding. He concurred with Mr Digby when he was asked if it was correct to say that the cladding which was ultimately installed for the Boilerhouse project was the same cladding approved as the material to be applied.

# Jeffery did say however that the architect, Toscano Architects, had advised him, by way of a letter dated 18 October 1999, that in its opinion the vitrepanel product (as finally approved for use) was not an item they recommended should be fixed with concealed fixings.

# In relation to the external soffit linings, the builder communicated to Jeffery its belief of Slattery’s approval for the use of 9mm villaboard cement sheeting for those linings. In correspondence to the superintendent dated 10 July 2000 the builder stated “we trust this meets your [the superintendent’s] satisfaction”. No response was apparently forthcoming from the defendants as to the unsuitability of the villaboard. Jeffery also agreed that Slattery had confirmed by letter dated 20 July 2000, that the proposal put forward about the cement sheeting was acceptable to them, but that nevertheless, this item was claimed during proceedings as a deduction variation for the reason that it was something that was not, according to the defendants, properly done under the contract.

Hinged Doors

# With respect to the suggestion that the builder did not install doors with rebated meeting styles as required by the contract documents, Jeffery conceded in cross-examination that the Raven weather seal specification, which allegedly formed the basis of the $33,000 deduction variation, was only relevant to external timber doors. Of the 33 doors in contention, most were in fact cupboard doors and “common area” doors.

Missing Mullions

# For deduction variation 17.6, the defendants claimed that the contract provided for mullions to be installed in all wardrobes in all apartment bedrooms, but that this had not been done. The builder contended that there was a variation because the contract drawings did not show mullions. The builder ultimately decided not to claim a variation, noting a nil change in the scope of the work, even though it contended that there were additional mullions. Jeffery said that he approved the work to be undertaken as the builder undertook it, and invited a variation be submitted for extra work. The defendants nevertheless contested the builder’s claim.

# Jeffery further said that he subsequently submitted a deduction variation for $3,740 for 34 missing mullions under Sopov’s recommendation. The builder said that the deduction should have been $1,200. During re-examination, Jeffery claimed that he in fact charged $1,200 for this item in the final certificate.

Door Weather Seals

# The defendants claimed a $3,069 deduction variation for the builder’s alleged failure to install Raven door weather seals. Counsel for the plaintiff put it to Jeffery during evidence that only one door would be relevant to the Raven seal specification. However, Jeffery said that he could not confirm that suggestion.

Failure to Install Lift Door Jams and Reveal Linings

# In relation to RFI 79, Jeffery agreed that shop drawings L1 and L2 were drawings for the lift detail, including lining and reveals provided by the lift contractor. However, Jeffery noted that detail “F” (a detail of lift door including jams and reveals for lift, typically at every level) “was not necessarily what was applicable on-site”.

# While noting that a Slattery document dated 8 September 1999 showed formal approval of shop drawings submitted by Kane to Slattery for the construction of the lifts, Jeffery said that he made no complaint as superintendent about what materials were installed, nor did he find fault with the standard of work employed.

Alucobond Cladding

# The argument with regard to the Alucobond cladding centred around the quantities of the material used. If more Alucobond was used than specified in the tender documentation, then Jeffery agreed that Kane should be paid more as appropriate. If however less Alucobond was used, then the builder would not be paid; rather, the principals were entitled to make adjustments by way of a deduction variation. The defendants claimed there were valid deduction variations in relation to the Alucobond cladding. In a report compiled by Mr Roger Goodwin who was instructed by Sopov to prepare an estimate of the work not carried out at the Boilerhouse project, Goodwin assessed that $15,287 was the amount the principals could claim with respect to the Alucobond cladding. This was calculated by reference to the contract area, 550 square metres, and the area of work actually completed, 503 square metres. Jeffery however maintained, on behalf of the defendants, that the figure for Alucobond cladding works to be done was more like 191 square metres, as at the time, progress certificate 15 assessed the Alucobond cladding as 81 per cent complete (at 30 August 2000).

# Under cross-examination, Jeffery agreed, “in theory”, that his figure of 191 square metres of Alucobond remaining to be installed, together with the 450 square metres already used as at 30 August 2000, would be the total amount of Alucobond cladding used for the project. However, Mr Digby pointed out the anomaly of these figures given that the contract area for the Alucobond cladding was at 550 square metres. Although it would appear that some of the contract works incorrectly specified Alucobond cladding (with Rheinzinc necessarily substituted instead), the amounts contended constituted an area of 12 metres (the defendants) or 34 metres (the plaintiff). Hence, if either of these figures are deducted from the 550 square metres outlined in the contract, the amount claimed by the defendants is still somewhat curious. If Jeffery calculated 81 per cent of this amount to equate to 450 square metres, then the figure claimed by the defendants as remaining to be done – 191 square metres – was over the amount they should have claimed in the event a deduction variation would be recognised here.

Mechanical Works

# Jeffery was also cross-examined about the mechanical services which the defendants claimed as deduction variations. The builder contended that, with regard to these works, it only needed to perform works on the shell of the building and not the interior. Jeffery said that he agreed that this was his understanding of the builder’s argument. Much of the argument at trial between the parties on this point concerned the scope of the works delineated in the contract documents, since these dictated the extent of the works remaining to be completed once Kane suspended the project in September 2000. For instance, with regard to the mechanical services for the perimeter of the building, Kane argued there was a lack of detail as to the specifications or what was envisaged in terms of the mechanical works systems to be installed. Kane argued that since the contract documents lacked detail and proper specifications, the works were not required under the contract and it should therefore not have to pay the amounts “remaining to be completed” as claimed by the defendants.

Costs to Complete

# In his witness statement, Jeffery stated that in recording the costs to complete, costs were calculated from an “open book” process provided by Sopov. By “open book”, Jeffery said that this meant that he “inspected invoices and records of payment being BPay, MasterCard statements, receipts, cheque books, bill notes and NAB bank statements on a regular basis as being evidence of the completion costs”. The costs to complete were incurred by Stacks Properties during the final stage of the works, following the departure of Kane from the site up until the time the works were in fact fully completed. Jeffery said that during this time he was on-site approximately two or three times per week.

# Jeffery noted that he did not record the cost of completion of contract works and the cost in rectifying defects separately. Instead, Jeffery said that he verified amounts expended by the principals according to three criteria: general labour, trade contractors and materials.

# Jeffery said that, on or about 30 August 2002, he issued a certificate under cl.44.6 of the contract certifying costs incurred by principals valued at $1,181,548. Jeffery said that the amount of $212,981 was referred to as “Balance of Works to Complete”, namely, works not done as part of the original contract and therefore not valued as a deduction variation. In giving evidence, Jeffery agreed that this cl.44.6 certificate did not endeavour to estimate or record costs which would have been incurred by the builder if it had completed the works itself. Rather, it was an assessment of the value of works actually done in order to effect completion of the project. Jeffery said that he used photos and a work status report to estimate the costs to complete works. But during cross-examination, Jeffery said that in preparing his costs to complete, he did not rely solely upon the photos and the status report as indicated in the witness statement. He said that he had also carried out a site inspection around the time when the photographs were taken.

# In calculating the balance of works to complete for the cl.44.6 certificate, Jeffery indicated during cross-examination that he had made various allowances within his trade breakdown, including allowances for labour, plant and equipment, and allowances against “Future Possible Costs” – that is, costs which Jeffery estimated might be incurred in relation to finishing the project. He also revealed that in preparing the certificate, he included some works completed prior to 6 October 2000 in his calculations of costs to complete, for example the metal work and stair contractors, since they had not been paid the outstanding amounts for their work. Jeffery said that he saw nothing wrong with including earlier costs in his calculations and considered it was appropriate to add them in.

# Jeffery also said that in preparing the costs to complete, wages and superannuation figures relating to the Sopov family were given to Jeffery by Norma Walker and taken on face value without any verifying documentation, back-up payment vouchers, or group certificates. Jeffery said that he did, however, see receipts for petrol, telephones and contractors’ all-risk insurance.

# Jeffery conceded that, had he been acting properly as a certifying superintendent, he would have verified each of the items of cost that he was certifying to the builder. Jeffery said that only a very small amount of costs owed to CAMC (for example) by the principals for work completed prior to 6 October 2000 remained outstanding. The progress payment summary prepared on 16 January 2001 recorded Jeffery’s budget for completion costs for the month of October 2000 at $1,896. This was the amount that he reported to the bank. Later, in the overall summary of costs to complete, Jeffery said that the amount for October 2000 had increased to $16,110.38. Jeffery said that he adopted the latter amount in response to further costs provided to him by Sopov, and that a similar scenario occurred in November 2000, again because he adopted figures provided to him by Sopov.

# Jeffery conceded that he did not certify, as the independent superintendent, on his own evidence, many of the items in the cl.44.6 certificate. During re-examination, Jeffery said that when Norma Walker submitted figures to him in relation to wages and superannuation, he assessed figures according to what he considered to be a fair and reasonable amount for the works, and that the final figures Jeffery used were the same as the ones provided by Walker. Jeffery said that apart from wages and superannuation, the process undertaken by him to arrive at the figures referred to in the certificate was to look at cheque butts, invoices and any other documents associated with payment on the project.

# Finally, on or about 28 April 2003, Jeffery prepared and issued the final certificate pursuant to cl.42.8 of the contract. The final certificate certified that $1,515,199 was owed to Stacks Properties by the builder. During cross-examination, Jeffery stated that certain items included in this final sum were not listed or notified to the builder before the final certificate was issued.

Defective Works

# Jeffery said that, as superintendent, he understood that he had a formal responsibility to identify defects and require them to be attended to by the builder from time to time. He said that he had made every reasonable effort to ascertain parts of the work which were defective or incomplete. Jeffery did not however recall telling the builder on any occasion the period of time in which he expected a defect to be attended to once it was identified. Jeffery said that the record of site meeting No. 44 on 12 September 2000 attached a running list of accumulated defects and reflected the position of defects according to him at that that date.

# One particular issue relating to the defective works focussed on at trial was practical completion to Apartments 1, 2 and 3. In a letter sent to CAMC dated 29 September 2000, Kane claimed practical completion of these three apartments. Jeffery said that he believed that at that time the apartments were “nowhere near” the stage of practical completion. Jeffery said that he recalled responding to the letter by saying that once the defects outlined by the architect (Mark Irving of Toscano Architects) had been attended to, then practical completion would be granted. During re-examination, Jeffery confirmed his view that certification of completion was not possible, noting that Irving was unable to complete inspection for his (Irving’s) report, dated 18 September 2000, because “the works were so far from being practically complete”. According to Jeffery, Irving gave up on the inspection after spending only about 45 minutes on-site. Jeffery said that he did not directly assess the accuracy of Irving’s assessment as to the practical completion of the apartments, but that he was involved in taking a video of the apartments around the same time and was generally familiar with the status of the works.

Liquidated Damages

# Jeffery claimed that he did not advise Sopov in relation to the liquidated damages that he was going to put into the contract. However, counsel for the defendants attempted to demonstrate that Jeffery had in fact played a more active role, at one point alleging that he had raised the option of liquidated damages to Sopov as one way in which they might be able to “balance the books”. According to that view, this was so that Jeffery, in his role as bank reporter, at the end of January 1999, could convey to the bank that projected completion was within the estimated budget of $3.65 million (the same argument made with respect to the rejection of Kane’s variation claims in order to preserve the $176,000 contingency).

# Jeffery, however, denied that suggestion. He stated that his role in relation to the liquidated damages claims was in fact limited to informing the bank of “all relevant monetary circumstances relating to the project”. He said that his role with respect to liquidated damages was therefore not an advisory one. Nevertheless, the witness later qualified that statement when he admitted under cross-examination that he would have told Sopov what he thought he could charge in liquidated damages against the builder on a monthly basis.

# In his progress reports to the bank, Jeffery agreed that that the overall figure of variations allowed was steadily decreasing and the overall figure for liquidated damages was increasing. For instance, as highlighted by counsel for the defendants, for progress report 7, liquidated damages were $175,000; while by progress report 10, the amount had increased substantially to $235,400. Nevertheless, Jeffery denied any conscious manipulation of the figures for bank reporting purposes.

Contract

# In cross-examination, Jeffery acknowledged that Slattery assisted Sopov in negotiating the contract with Kane. He said that he assisted in working on the contract’s appendix and also the general conditions, but that he did not review the contract from the perspective of the Domestic Building Contracts Act. Jeffery stated that this was the task of Mr Crawford Fulton, another quantity surveyor and an associate at Slattery. Jeffery said that, before May 1999, his involvement was only that of quantity surveyor reporting to the National Australia Bank (“NAB”). Jeffery stated that he understood that Fulton had been taking the lead role in contract negotiations.

Progress Reports

# From about mid-April 1999, Jeffery commenced the task of producing regular reports to the NAB in relation to the project. Those reports were produced pursuant to Slattery’s engagement by the bank, under the terms annexed to the letter from the NAB to Slattery dated 14 April 1999. In his reports to the bank, Jeffery was required to assess whether the project was proceeding in accordance with the construction programs.

# Under the contract, the builder was contractually obliged to provide a construction program within 14 days of acceptance of tender. However, the first construction program was not provided until 3 August 1999, 43 working days (that is 33 per cent) into the construction period.

# Jeffery gave his opinion that every program provided was more a record of what had happened up to that date, rather than a prospective program. Jeffery said that the tasks to complete were inconsistently recorded from one program to the next. He said that one such example was the task of “External Windows, Door and Façade”, which was originally programd to start on 23 September 1999 and set down for completion 20 days later on 14 October (Boilerhouse program No. 1). However, subsequent programs provided different (and later) starting dates and longer completion periods.

# In cross-examination, Jeffery said that he understood that the process of issuing progress reports involved verifying, on a monthly basis, that there had been a fair and reasonable assessment of the amount of work undertaken on the project. Jeffery said that he was officially also charged with issuing progress certificates in that he prepared the paperwork and compiled the figures, however he stated that someone else from Slattery assessed on-site works and prepared the documentation. Jeffery also said that Fulton signed off on the actual progress payment certificates.

# In re-examination, counsel for the defendants took Jeffery through progress certificates 4 to 13. Jeffery described how he used a variation register (spreadsheet) to reach his calculations, and he indicated how these calculations were ongoing.

Progress Report 1

# In cross-examination, Jeffery agreed that, in the early stages of the project, he had envisaged that it might become important at some point to re-evaluate the cost of finishing the project. Nevertheless, $3.65 million remained the “benchmark amount” throughout.

Progress Report 3

# At the time of the preparation of progress report 3, the builder produced the first construction program. Jeffery concurred with the view that he had said nothing to the bank to suggest to them that the program was in any way unsatisfactory. He agreed that he reported to the bank that progress on-site was proceeding in accordance with the revised program.

# In cross-examination, Jeffery agreed that pending variations at the time of progress report 3 were valued at $125,000. He also agreed that by progress report 4 they were $73,000 (up until that point only $5,658 had been approved). Jeffery stated that he could not recall what changed his mind about the merits of the variations. He denied that his dual role as bank reporter (containing and verifying costs) and superintendent (allowing fair and reasonable payment) influenced him. That is, he was not concerned that estimated costs had to be maintained and there was no pressure from Sopov to whom he had to justify what was payable.

Progress Report 4

# Progress report 4 was submitted in December 1999 and covered the November 1999 period. For the first time since the preparation of a progress report, the completion date (at that stage March 2000) remained the same, which Jeffery agreed indicated that progress that month had been in accordance with the program and satisfactory. Jeffery could not explain why variations pending had reduced so dramatically from progress report 3 to progress report 4.

Progress Report 6

# Progress report 6 was submitted to the bank in February 2000. At this stage the anticipated completion date was April 2000. During cross-examination, Jeffery said that he had reported to the bank that progress on-site was proceeding in accordance with the revised program. He stated that he was not necessarily “happy” with progress, but that it was on track. Jeffery agreed that if the builder had suffered any significant delay in this period, Jeffery would have advised the bank. Jeffery could not explain why he had increased the variation amount pending approval to $126,380.

Progress Report 7

# When Jeffery was asked during cross-examination why variations approved were so much less than variations pending, he responded that it was probably because he was still trying to reach an agreement with the builder as to an approved variation amount. Jeffery said that he could not recall whether or not he was concerned about the fact that only a small minority of variation claims had actually been approved. Jeffery was also asked whether it “concerned” him that he had to advise the bank at this point that he would be recognising $159,420 of the builder’s variation claims, which might come as a surprise to the bank since up until progress report 7, he had in fact only approved $8,978 in total for variations claimed.

# Progress report 7 conveyed to the bank numerous possible means by which the figures could remain within the estimated cost of $3.65 million. Jeffery canvassed the likelihood of deduction variations, liquidated damages and decreased approval levels for variations. It was put to Jeffery that his statement “[w]e are therefore satisfied that the project cost is still within the bank’s lending facility limits” was indicative of his intention and need to keep figures within the original estimated amount. Jeffery denied this suggestion.

# Jeffery referred to “progress on-site this month” being “slow due to major rectifications being carried out on the walls”, namely stud wall rectification work. He agreed (both in his capacity as superintendent and as bank reporter) that the builder was endeavouring to minimise delays on-site. Progress report 7 also indicated delays in relation to industrial action.

Progress Report 8

# The liquidated damages amount of $175,000 claimed in progress report 7 was only taken into account in calculating progress report 8. During cross-examination, Jeffery denied that it was the principals who asked him to put these figures into the report. He also denied that the calculation was done in progress report 8 (as opposed to earlier progress reports) in order to provide a basis for the bank that the budget was not about to overrun. Jeffery continually denied that he introduced deductions to show the bank that there was still a significant contingency available to protect them from overrunning the original estimated cost of $3.54 million. According to Jeffery, the consequence of an overrun did not pose a problem.

# At the end of March 2000, Jeffery was still negotiating time extensions and time extension costs with the builder. He denied that one of the reasons for such protracted discussions was that it was another way of not adding figures to the balance sheet. In particular, it was put to Jeffery that inclusion of these additional costs would mean that he was put in the position of having to report to the bank that the project cost was no longer within their lending facility.

Progress Report 9

# Progress report 9 was submitted in May 2000. During cross-examination, Jeffery stated that he believed that the $200,000 liquidated damages amount raised at this point would have been his own calculation, although he did suggest the possibility that he may have discussed the matter with Sopov. On the other hand, Jeffery stated that the contents of the report were prepared entirely without Sopov’s involvement. Jeffery said that he could not recall Sopov ever contacting him in relation to them.

# Jeffery stated that the increase in the deduction variation sum was a result of additional items coming to light. He said that he could not recall whether by the end of April 2000 he had raised with the builder his intention to deduct $50,000 in deduction variations.

# Kane submitted $282,000 in EOT claims, $272,000 of which were at the time that progress report 9 was submitted and was under discussion. Kane provided bank guarantees as retention moneys under the contract totalling $173,000.

Progress Report 10

# In progress report 10, the increase in liquidated damages appears to have allowed Jeffery to report a contingency of approximately $350,000. During cross-examination, Jeffery once again denied that he altered the figures to affect the contingency. Jeffery agreed that he reported a rejection of variation claims amounting to $305,000, whereas in the previous month he had informed the bank that he had rejected a much lower figure of $250,000.

# In the report, Jeffery noted that “Kane Constructions have accepted our assessment of $190,147”, being the amount payable under the certificate. Jeffery denied that he was inferring by this that there wasn’t a much larger figure being claimed – as was in fact the case regarding amounts in connection with progress claim 12. Jeffery said that he was not suggesting that the builder was not pressing for much larger amounts under the claim. He said that in banking the $190,147, the builder “agreed to the amount on the certificate”.

Progress Report 11

# In progress report 11, submitted on 24 July 2000, a new entry appeared on the balance sheet entitled “Allowance for Future Variations”. Jeffery could not recall what this entry related to.

# Jeffery stated that he communicated to the bank that “whilst there is disagreement on a large number of issues, Kane Constructions have made it clear that it is their intent to complete the project to their contractual obligations and that the quality and finishes will not be compromised”. Jeffery claimed that an employee of Kane’s had told him this about the company’s intentions. Although he could not recall the particular Kane employee who conveyed these sentiments, Jeffery said that he had accepted the genuineness of them.

# Jeffery stated that the amount given as the value to complete ($1,000,000) was an estimate made by Jeffery excluding defects not yet brought to his attention. In relation to the defective and incomplete work that Jeffery was aware of, he did not recall whether adjustments had been made to the calculation of costs to complete, although he agreed that his role as superintendent involved regularly appraising himself of defective or incomplete work. Jeffery agreed that he did not value, as owed to the builder, work which he believed to be defective.

# Jeffery further stated that it was possible that, as superintendent, he would have the power to decide whether the defect was one that needed rectification before completion of the contract or whether he could allow it to be corrected in the year after practical completion. He admitted, however, that he had not thought of such a situation arising.

Progress Report 12

# During this period, on 4 August 2000, Jeffery left Slattery to set up his own organisation, CAMC. Jeffery continued to supply Slattery (who were at that stage in official correspondence with bank) with information relating to cost of the work, costs to complete, and the likely completion date. Jeffery was also still able to report to the bank (via Slattery) that the project was under the projected budget of $3.65m.

# Jeffery was not able to explain what had happened to the deduction variation figure which was no longer referred to. However he denied that this figure was ignored, since liquidated damages figures were so high as to meet the contingency.

Progress Report 13

# By progress report 13, liquidated damages decreased Kane’ payment up to this stage of the works to $132,618. The amount deducted was $220,000. By 19 September 2000, Jeffery had become aware that the principals had deducted that sum.

Progress Report 14

# Jeffery assessed the progress of the project as being 91 per cent complete.

Progress Report 15

# By the time progress report 15 was produced, the builder had left the site, and the principals had proceeded works under their own administration. Nevertheless, Jeffery continued in his capacity as quantity surveyor. Under the heading, “Financial”, a revised budget was produced for these works: $281,553 was the estimated value to complete construction costs up until the end of November 2000. Jeffery stated that, while he provided the figures for this report, he did not see the report in its final form, as prepared by Slattery, before it went to the bank.

# Progress report 15 stated that the estimated value of works to complete totalled $506,795, into which a $150,000 contingency was built, allegedly to cover unexpected events, bringing the base costs to around $350,000. In Appendix B of the report, Jeffery certified to the bank that the works were being “carried out in accordance with the contract documents and approvals”.

# Jeffery stated that he expected that, by this stage, the job would be completed by February 2001, and no later than March 2001. In order to reach this estimate, Jeffery said that he made regular site visits (two to three times a week) and inspected what was left to be done. Jeffery said that he could not recall how much effort this involved.

# Jeffery said that, while he continued to provide consulting services as quantity surveyor, his formal role of superintendent under the contract was no longer relevant, insofar as he no longer supervised works or made decisions about how work was to be done.

Progress Report 17

# With regard to progress report 17, Jeffery denied that he extended the columns in his report in anticipation of the project running beyond March 2001.

Termination

# A letter from the plaintiff’s solicitors, Deacons, dated 5 October 2000, refers to contract termination pending action by the superintendent by 12 noon on Friday 6 October 2000.

# Just before midday on 6 October 2000, Jeffery issued revised progress certificates 14 and 15. Jeffery claimed that the issuance of the certificates just before the deadline was a mere coincidence; that he had been doing some paperwork at the time. The certificates contained express allowance against the builder for liquidated damages, the first time any reference to liquidated damages was made in the progress certificates. Jeffery denied that he was asked to issue the certificates (i.e. by Sopov) and said that he could not recall whether he was in contact with Sopov or Archer around this time. When asked by counsel for the plaintiff if he could have been in contact with one of these two people or associated persons, he responded “I guess”.

(3) BROWN

# David Arthur Brown gave evidence in his capacity as a senior mechanical services consultant with the firm Fryda Dorne & Associates (“Fryda Dorne”). Brown’s role in the Boilerhouse project was to carry out inspections of the mechanical services installation at various times when requested by Kane, for the purpose of determining compliance with contractual requirements and assessment of standards of workmanship. Brown’s investigations were therefore most relevant to the issues of defective works and variations.

# Brown asserted that on each inspection it was noted that “significant aspects of the works had not been carried out in accordance with the contract documents, the approved shop drawings, or to typical industry standards”. These shortfalls were noted in a defects lists produced by Fryda Dorne following each inspection. In most instances, Brown stated that he did not re-inspect the works after advice that the defects had been rectified.

# Brown described several instances where he stated that rectification works were not addressed or not completed satisfactorily by Kane, including the sealing of duct joints. During cross-examination, Brown stated that many of the works could not be re-inspected since “the works had been closed in”, by which I assume he meant either that Kane had left the site or the project was finished altogether. Brown was therefore unable to say whether these “closed in” works had been rectified or not.

# Brown stated that he had received a number of requests to accept inferior alternatives to change the specific standards of equipment and installation. He stated that these requests were usually accompanied by ultimatums or at least statements requiring an immediate response. Brown stated that the substitutes were rejected unless they provided an equivalent standard to the original specification.

# During cross-examination, Brown admitted that a flexible duct proposal was put forward by the plaintiff. However, it was rejected by Brown and subsequently not installed.

# In his witness statement, Brown cited the mechanical exhaust systems as indicating a “severe shortfall in specified performance requirements”. Counsel for the plaintiff suggested to Brown that any shortfall could be attributed to the sub-contractors, Admiral Air Conditioning, who were engaged by the principals, rather than by the plaintiff or by the initial sub-contractors, AllCare Air Conditioning.

# With regard to the variations, Brown stated that he reviewed the claims made by Kane with respect to mechanical services. Brown regarded both NPV38 (“Extra Fire Dampers and Collars”) and NPV92 (“Ductwork for Exhausts of Range Hoods”) to be a “site co-ordination issue between the builder and mechanical sub-contractor”.

# With respect to NPV46R (“Plant Platform and Handrail”), Brown stated that such alterations and their associated costs should have been included in the tender price. During cross-examination, Brown agreed that one reason why the plant platform was required to be larger might have been to create a greater clearance (of 1.2 metres) for the York Millennium equipment that the contractor was using. If that was true, then Kane would not be able to claim this item as a variation. However, counsel for the plaintiff suggested that the initial equipment required a clearance of only 900 millimetres. Counsel highlighted documentation from Apac Carrier to that effect.

# With regard to Stacks Properties’ counterclaim, Brown reviewed several variations in his witness statement, specifically variations 23.2 through to 23.18, and also deduction variation 23.1. With some qualifications, he considered the large majority of claims to be valid.

(4) LONG

# Keith Ian Long gave evidence in his capacity as a consulting structural and civil engineer. Long was the principal of Keith Long & Associates Pty Ltd (“KLA”).

# Long was engaged by architect, Ross Carpenter, to undertake the structural design and documentation for the Boilerhouse project. His role also involved checking the steelwork shop detail drawings for structural content (but not for the structural dimensions).

# Long disputed Kane’s allegations that it suffered extensive delays to the completion of the structural steel, due, among other things, to the lack of detail in the structural design drawings. Long asserted that there “were no major changes to the structural elements of the project”. Long further stated that it was not his “task to approve variations on the Boilerhouse project”. In cross-examination, Long stressed that he did not approve variations, rather, he assessed what was structurally achievable. His evidence essentially concerned one major issue: the balcony step-downs (a structural steel issue).

# Long stated that on 27 July 1999 he received from Slattery Australia a request by Kane Constructions for information regarding the balcony step-downs (the step-down to the north and west balconies to apartments 11 and 12 was designated to be 190mm). In RFI 48, Tivendale stated that there was a discrepancy in the step-downs, saying that the step-down should be cut out of the beam and that a 150mm cut would be too much. Tivendale suggested that a 70mm step-down with a fall would be more appropriate. Long replied by stating that there was no discrepancy on the drawings; that the extent of a step-down was an architectural issue; and “that 70mm set-down for balconies was adequate”.

# Long stated that he received a further request from Kane Constructions in RFI 60 on 6 August 1999. RFI 60 sought clarification as to whether the 190mm “drop” was still warranted at the specified terraces. Further, on 9 August 1999, Long stated that Sopov asked him to check the design of the UB sections for the beams to the balconies for a 170mm cut-out.

# Long stated that he responded to RFI 60 on 10 August 1999 and recommended that all the beams that required cut-outs at balconies be a 310UC beam with a 70mm cut-out. However Kane Constructions chose to adopt UB sections rather than UC ones. Long said that the UB beams were cheaper than UC beams.

# Long said that he nevertheless approved the shop drawing for the UC beams since “they were structurally adequate” and that a 190mm set-down “could have been achieved with the UB section (410mm deep) and 170mm cut-out”. During cross-examination, Long noted that the UC beam had “twice the strength of bending and the area is much greater than a UB”. However, Long said that he had no conversation with the architect, Hampton, about these matters.

# Long also said that he made a note on the shop drawings that they were on hold, after Sopov told him that “the 103mm cut to the beam drawn by the shop detailer may not achieve the 190mm set-down”. Long’s testimony appeared to concede that the deeper step-down required by Sopov eventually led to the installation of a “cranked beam”.

# Long said that he met with Sopov and Tivendale at KLA’s offices in early September 1999. At this meeting, set-downs to balconies were discussed, but Long could not otherwise recall the substance of the conversation or whether anything particular was agreed about the set-downs. During cross-examination, Long agreed with counsel for the plaintiff that Sopov was making architectural decisions.

# Long rejected Tivendale’s implication that Long stated that “a 150mm set-down apparently suggested by Hampton would involve too much of a cut-out from the structural steel beams to the balconies”. Long further recalled discussions with Tivendale (although he could not recall if Sopov was present) about the proposed changes to the steelwork to the balcony on apartment 11. Long said that he conveyed to Tivendale that the proposed changes to the apartment 11 balcony would not work and suggested that Kane should “revert to the original structural framing system shown on the original structural documents”.

# During cross-examination, Long was asked about RFI 124, dated 20 September 1999, sent by Le Hy Ta regarding a request to review revised shop drawings, including 27A which referred to the balcony step-down showing a 170mm cut. Long testified that a 170mm cut would not necessarily equate to a 150mm step-down since it would depend on the “the relationship with the location of the beam within the ceiling space”. Long further said that he had told the builder that it was structurally satisfactory.

# Long rejected the assertion made by counsel for the plaintiff that, by telling the builder that it was structurally satisfactory, this implied that the builder could go ahead and have it fabricated. Rather, Long argued that the builder needed it to be checked by the architectural advisor. Long “entirely disagree[d]” with counsel’s assertion that when a “professional consultant [such as Long] approved a shop drawing, that means that it is approved for manufacture by the Builder”.

(5) PANDOV

# Victor Pandov was responsible for making an on-site video recording of work carried out at the site, at the direction of Jeffery and Sopov. In their testimony, both Sopov and Jeffery confirmed that the video was taken by Panov at their direction.

(6) DEGENHARDT

# William Herbert Clarence Degenhardt gave evidence for the defendants in his capacity as a project planning consultant and as the Managing Director of BILD Pty Ltd (“Bild”). Bild specialises in providing professional planning and construction services and advice to clients and developers.

# Degenhardt stated that, in February 2000, he was asked by Jeffery to review the construction programs of Kane Constructions and independently assess the extension of time claims.

# In carrying out this task, Degenhardt said that he was provided with documentation including the contract; drawings; specifications; builder’s construction programs; and extension of time claims and supporting documentation. He also inspected the site and spoke with Kane Construction representatives and to Sopov and Jeffery.

# As a result of his investigations, Degenhardt prepared four reports: (a) Program Delay Report and Extension of Time Claim Report of 15 February 2000; (b) Revised Program Report of 11 April 2000; (c) Revised Program Report of 20 July 2000; (d) Program Delay Report of 10 October 2000.

# A significant part of Degenhardt’s reports turned on the question of variations falling under the EOT claims. Degenhardt relied on what Jeffery had determined about variations, except for where he could “verify” the variations. He also assumed that the documents provided to him were the only relevant documents.

# Degenhardt formed his own view in relation to the variations about extension of time claims, namely, the lift pit (EOT 1); the floor wastes to laundries (EOT 7); and the light boxes (EOT 9).

# In relation to the EOTs, Degenhardt’s witness statement reflected the inadequacy of Kane’s program. He said that there was no logical relationship between the external façade and the internal fit-out of the building. He also said that some of Kane’s programs didn’t have procurement activities expressly set out and that this represented an inadequacy.

# Counsel for the plaintiff suggested to Degenhardt that all of the works off-site need not necessarily have been included in the program; however Degenhardt asserted that “you need to program those critical works that could have an influence on the program, whether they be off-site or on-site”.

# Degenhardt said that, while it was not impossible to assess an extension of time claim without a program being available, it would be “extremely difficult”. He further reiterated that external or off-site activities could impact on the delay and that a full assessment must include them.

# Degenhardt said that, in a complicated project such as the Boilerhouse, it was important to have a program early in the contract in order to properly program the work of contractors and sub-contractors.

(7) GOODWIN

# Roger Goodwin gave evidence for the defendants in his capacity as a quantity surveyor and as an associate of The Rawlinsons Group Pty Ltd. In his witness statement, Goodwin said that, on or about 17 June 2003, he was instructed by Sopov to prepare an estimate of the work not carried out at the Boilerhouse project. Goodwin said that he did not see any witness statements from Sopov, Jeffery or Irving before preparing his report.

# Goodwin further stated that he had not seen any of the plaintiff’s witness statements relating to the broad issue of deduction variations. Goodwin said that he was asked to assume that the items of deduction variations were works that did not comply with the contract. Goodwin said that he was instructed by Sopov to ignore the pricing on the original document that he was given that had set out “the owners’ claim for deduction variations totalling in the order of $1.2 million”. Goodwin said that it was clear at his second meeting with Sopov that he was to make a totally independent assessment.

# Goodwin said that he “contacted the relevant suppliers or sub-contractors and discounted present rates back to 1999 prices”; that he used “Rawlinsons’ own publication as a guide and a check”; and that he “used a 10 per cent margin for profits and overheads”. He conceded that it “would be reasonable” to conclude that it was not possible for him to identify what documents he had regard to in reaching his conclusions about the deduction variations, other than those referred to in annexure B of his witness statement. Goodwin further said that, in cases where there was uncertainty regarding the scope of the work, he did not price it.

# Goodwin’s summary of variation costs is attached to his witness statement as “Annexure B”. The grand total was $639,974. Each item was individually costed in Goodwin’s report and the trade total summaries appear in the annexure as follows:

1. Preliminaries		$30,344

2. Demolition		$1,385

3. Groundworks		$3,033

4. Concrete			$54,784

5. Structural Steel		$14,871

6. Steel Wall Framing	$11,966

7. Masonry			$7,331

8. Metalwork			$71,474

9. Woodwork		$58,604

10. Hardware		$5,474

11. Rheinzinc			$3,786

12. Roofing			$10,722

13. Alucobond		$15,287

14. Other Cladding		$36,807

15. Insulation			$6,101

16. Windows			$50,259

17. Doors			$49,009

18. Painting			$1,381

19. Plastering			$41,005

20. Resilient Finishes	$26,217

21. Hydraulic Services	$34,897

22. Electrical Services	$57,690

23. Mechanical Services	$47,547

24. Lift Services		$6,875

25. (unspecified)

26. General 			(unable to price items)

TOTAL			$639,974

(8) PERMEWAN

# John Patrick Permewan gave evidence for the defendants in his capacity as a qualified architect. His Order 44 statement was prepared at the request of the defendants’ solicitors. Permewan’s specific instructions were to prepare a report based on the variations listed in the Order 44 statement of the expert witness, Gilfillan, and to comment on those variations, except in those cases where Gilfillan’s opinion was that they were not variations.

# Permewan said that he visited the site in July 2003. He said that he was there for several hours with Sopov, and that for part of the time, Mr Magee was there also. Permewan testified that he had not been given any instructions about the extent to which works had been completed as at 18 September 2000; nor was he aware that, in the most recent progress claim before 18 September 2000, Kane had claimed the completed work to the value of 94 per cent and that the relevant certificate from the superintendent certified that works had been completed to the extent of 91 per cent.

# Permewan said that the “claimed variations and supporting documentation provided by the builder are generally perceived to lack clarity and completeness”. Permewan further said that “[t]he RFIs preceding any actual variation claim often appear to be based on a failure to read all the relevant documents, or so selectively, or as an attempt to draw the superintendent into protracted correspondence which may ultimately lead to some variation based on items within that correspondence and not the contract Scope of Works”.

# Permewan noted that clause 11(b) in annexure A to the contract stated that the percentage payable to the builder for profit and allowance on provisional sums allowed under that clause was 5 per cent “and not the 10 per cent which appears to be claimed by the builder against such allowances”; however Permewan regarded an allowance of 10 per cent as “not unreasonable”.

# Permewan’s opinions on the variations listed in Appendix 1 of Gilfillan’s report may be summarised as follows:

| Item | YES: A Variation | NO: Not a Variation | Other |
| --- | --- | --- | --- |
| 1. Repair to existing water service |  | × |  |
| 2. Excavation in Rock | √ |  |  |
| 3. Break Out and Remove Concrete | √ |  |  |
| 4. Extra for Galvanized Fire Service |  | × |  |
| 6. Car Park Concrete Beam |  | × |  |
| 8. Stormwater Drain Crossing |  | × |  |
| 9. Extra Ground Floor Slabs | √ (Areas 1 and 3) | × (Area 2) |  |
| 12. Agricultural Drain Lift Motor Room |  | × |  |
| 13. Window W3 – Stormwater Pipe | √ |  |  |
| 14. Fire Proof Slabs & Brick Wall | √ |  |  |
| 19R. Pilkington Evergreen Glazing |  |  | “The final cost of any variation should reasonably be the cost of the cheaper glass actually installed in the building, less the cost of the ACI Pilkington Evergreen glass for the windows as required by drawings A14-A and A15-A.” |
| 20. Slab Penetration Infills |  | × |  |
| 21. Plywood Backing with Quietel |  | × |  |
| 22R. Fire Detection System |  | × |  |
| 23. Additional Walls | √ |  |  |
| 29. Fire Rated Doors and Frames |  | × |  |
| 32. Extra to Conceal Columns to Second Floor Apartments | √ |  |  |
| 33R. Suspended Slab-Stair 3 |  |  | “We are instructed that the principal acknowledges this work was undertaken as a variation.” |
| 35. Terrace Gutters |  | × |  |
| 36. Extra Rheinzinc |  | × |  |
| 37. City West Water Fees |  | × |  |
| 38. Extra Fire Dampers and Collars |  | × |  |
| 39. Additional Ductwork and Grilles |  | × |  |
| 41. Doors D7, D10.08 and D13.08 | √ |  |  |
| 44. Cranked Beam 3B26 |  |  | “We are instructed this item was carried out at the request of the principal and is accepted as a variation.” |
| 46R. Roof Plant Platform and Handrail |  | × |  |
| 47. Toilet Accessories |  |  | “There is a requirement for the builder to supply all toilet accessories for the project for a reasonable sum and to adjust the supply only price against the $8,000 allowance referred under schedule 2 of Appendix B3 of the contract.” |
| 48. Shower Screens |  |  | “That the builder is entitled to be paid a reasonable amount for the supply only price of the items against the $10,000 PC as a reasonable maximum.” |
| 49. Demolition of duct at chimney |  | × |  |
| 52. Royal Wall Hung Pans | √ |  |  |
| 53. Preseal to Sadler Tiles |  | × |  |
| 56. Staircase 7 – Apartment 8 |  | × |  |
| 57. Wardrobes PC Sum |  | × |  |
| 60. Additional Wall in Office |  |  | “We are instructed that the principal accepts this variation subject to checking of the price claimed.” |
| 62. Gallery Entrance Gates |  |  | “We are instructed the principal accepts this variation.” |
| 63. Additional Brickwork / Parapet |  | × |  |
| 64. Cutting of Slab in Apartment 10 |  |  | “We are instructed the principal accepts this variation.” |
| 65. Lift Motor Room Ventilation System |  | × |  |
| 66. Laundry Floor / Wastes |  | × |  |
| 67. Adjacent Building Plumbing |  |  | “We are instructed that the principal requested this variation. However we are further instructed that the variation was never carried out.” |
| 70. Additional for Water Tapping | √ (for Sunday work) |  |  |
| 71. Penetration through Beams – Mechanical |  | × |  |
| 72. Add CFC for Laundries |  | × |  |
| 73R. Additional Track Lighting | √ |  | Instructions are that this work refers to work, requested by the principal, to the gallery. |
| 74. Additional Tiles to Second Floor | √ |  |  |
| 76. Skirting Tiles to Ensuite Cupboards |  | × (but “possible small credit”) |  |
| 77. Change to Gallery Light Wiring | √ |  | Instructions are that this work refers to work, requested by the principal, to the gallery. |
| 78. Timber Flooring |  | × |  |
| 79. Add 36W Gallery Light | √ |  | Instructions are that this work was requested by the principal. |
| 80. Gas Cooktop GPO’s |  | × |  |
| 81. Charge floor waste in Unit 5 |  |  | No opinion, since the claim is “unclear and lacks substantiation”. |
| 85. Clean off sign on West Elevation |  |  | “We are instructed that the principal accepts this item as a variation.” |
| 86. Integra Basin |  |  | “We are instructed that the principal accepts this item as a variation.” |
| 88. Isolator Switches |  |  | “We are instructed that the principal accepts this item as a variation.” |
| 92. Ductwork for Rangehood Exhaust |  | × |  |
| 94. Structural beam at apartment 10 terrace |  | × |  |
| 95. Relocate bath, Apartment 9 |  |  | “We are instructed that the principal accepts this item as a variation.” |
| 96. Weatherproof Hopleys Trusses | √ |  |  |
| 101. Detector Valve Booster | √ (“if the Scope of Works was altered’) |  |  |
| 102. Recessed Downlights |  | × |  |
| 104. Additional Fire Rates Boxes in Ceiling Level 2 |  | × |  |
| 105. Florida Pan in Apartments 7 and 10 |  |  | “We are instructed that the principal accepts that the change took place and there was a variation.” |
| 106. Rheinzinc at North East Elevation | √ (but “further clarification required as to whether the item is in fact a credit or debit variation”) |  |  |
| 107. Additional Beam at Main Entry Gates |  |  | “We are instructed that this item is accepted by the principal.” |
| 113. Alternative Recessed IDF Unit |  |  | “We are instructed by the principal that they accept this variation.” |
| 115. Wiring for Toilet exhaust fans air roof |  | × |  |
| 117. Pivot Doors Floor Springs |  | × |  |
| 118. Fire Rating to Soffits at Second Floor Terrace |  |  | “We are instructed that the principal accepts this item.” |
| 119. Install extra cable for Apartment Submains |  | × |  |
| 120. Alterations to Brick Pier for Fire Booster Assembly |  |  | “We are instructed that the principal accepts this variation.” |
| 121. Gallery Entry Columns and Lintel Propping |  | × |  |
| 122. Alterations to basin to suit vanity heights |  |  | “We are instructed by the principal that no alterations took place.” |
| 123. Redirect Fire Services |  | × |  |
| 125. Pre-primed MDF Skirtings |  |  | “That the superintendent accepted a substitution on the condition that pre-primed timber was used, and that the builder by using the substituted material accepted the condition imposed by the superintendent. We are of the opinion the acceptance of the substitution and the conditions are interrelated and effectively inseparable if the approval was to operate.” |
| 126. Additional Penetrations of Roof for Toilet Exhaust |  | × |  |
| 127. Existing Floor Levels surveys to apartments 1, 2 and 3 |  | × |  |
| 128. Aluminium Screen Frames |  |  | “We are instructed that the principal accepts this variation.” |
| 129. Additional Phone points in Units 5, 6 and 7 |  |  | “We are instructed that the principal accepts this variation but queries the amount.” |
| 130. Floor Levelling to Laundry Areas |  | × |  |
| 131. Office Bulkhead Hydraulic and Mechanical Alterations |  | × |  |
| 134. Plasterboard to Underside of Stair 2 |  |  | “We are instructed this item is accepted by the principal.” |
| 135. Access Panel to Bathroom Hobs |  |  | “We are instructed that the principal accepts this item.” |
| 137. Additional Downlights in APT 12 and APT 11 Cable Modifications |  |  | “We are instructed that the principal accepts this item.” |
| 138. Office Entry Brick Nibs |  |  | “We are instructed that this item is accepted by the principal.” |

# In cross-examination, counsel for the plaintiff questioned Permewan on nine variations. These were as follows:

NPV 1: Striking a water pipe under an existing concrete slab

# Counsel for the plaintiff suggested to Permewan that if the pipe was only 25mm underneath the concrete slab rather than the 75mm minimum required by the Australian Standard – and that if this did not appear on the drawings – then the builder could not know of its existence at the place where it was struck. However, Permewan contended that the builder might be able to know about it.

NPV 4: Supply and installation of galvanised piping to the fire services

# Counsel for the plaintiff stated that the galvanised pipes which Kane installed under NPV 4 were not stated in the contract, nor allowed for under the tender clarification; however Permewan said they didn’t need to be. Permewan said that his understanding was that the builders had directly negotiated with the principals, stating that they could save them money by taking out the sprinklers, but that they still had to have an end result that complied with the law and therefore they couldn’t charge extra for it later. In re-examination, counsel for the defendants drew Permewan’s attention to the contract drawing which stated that “Fire service below ground shall be seamless copper tube type B, and above ground shall be formed of galvanised pipe”. Permewan agreed that such a description was clear.

NPV 8: Removing parts of the concrete slabs to install drainage pipes

# Counsel for the plaintiff suggested that beneath the two concrete slabs in the photograph there was a third concrete slab to be cut through that was not shown. Permewan said that he was not aware of the third slab; however, he contended that the builder still must bear the burden of proof by providing the necessary detail when claiming a variation.

NPV 20: Concrete slabs with holes to be filled

# Permewan said that there was nothing specifically in the contract documentation or specification that required Kane to fill in these holes. Permewan also agreed that Kane had been instructed to fill in the holes by Long, in response to Kane’s RFI 055.

NPV 21: Plywood Backing with Quietel

# Counsel for the plaintiff suggested that it was not apparent that 7mm thick plywood backing to 13mm thick Quietel insulation was required in several areas; however, in cross-examination, Permewan conceded that it would often be redundant to depict the requirement as such and that the documentation and specifications should be construed as a whole. In his report, Permewan had stated that no variation was valid in this instance.

NPV 35: Terrace Gutters

# Permewan said that his instruction from Sopov was that this item only referred to Level 2 on the eastern façade. In cross-examination, Permewan conceded that if his instruction was wrong, then the item would constitute a variation.

# NPV 37: City West Water Fees

# Permewan said that these items are part of the normal work of the builder and are therefore not a variation.

# NPV 71: Cutting penetrations through beams to enable ducts to pass through

# In denying the validity of this variation, counsel for the plaintiff suggested that Permewan was confusing RFI 222 (which dealt with penetrations to the steel beams) with RFI 407 (which dealt with the ceiling or the locations where the height of the ceiling was to be revised); however Permewan stated that they were “part of the same assembly” and “can’t be separate”.

# NPV 78: Timber Flooring

# In response to cross-examination by counsel for the plaintiff, Permewan stated that he did not agree that no method of floor levelling was set out in the specification. Permewan conceded that, on the basis that there was an error in the drawings, that the substitution of the Kempest floating floor in lieu of carpet would be a legitimate variation if the Kempest floating floor was greater than the carpet floor.

# NPV 94: Structural Beam at Apartment 10

# Permewan stated that even if the beam wasn’t shown on the structural drawings; since it was evident on the architectural drawings, it should be included within the scope of works. Permewan rejected counsel for the plaintiff’s suggestion that it was a clear omission since it did not appear on the structural drawings; given that it was still within the documents.

SUBMISSIONS ON EXPERT EVIDENCE: LYNAS AND DEGENHARDT

# Two experts were called, Lynas and Degenhardt. Lynas gave evidence in relation to the critical path and the progress of the development. He was not involved, in any way, in the actual project itself. Lynas’ expertise lay in programming and extensions of time and he was called by the plaintiff as an independent expert. Objection was taken to his evidence, and it was heard and received subject to the objection.

# An expert witness is required to state the methodology used that provides the foundation for the formation of the expert opinion: see Makita (Australia) v Sprowles; also Arnotts Ltd v Trade Practices Commission. The approach is that the court should be in a position to test the conclusions reached by the expert and of understanding the process of reasoning used by the expert.

# Lynas provided his opinion based upon materials and information given to him by the plaintiff. He used a number of contemporaneous documents such as the foreman’s diary, the statement of Tivendale, and his experience in analysing computer programs with respect to time delays on building projects. Lynas’ evidence was partially written, partially oral and, also, the subject of computerised PowerPoint presentation in Court during evidence. I note that Lynas was a civil engineer having a tertiary qualification in science and 30 years construction experience. He had provided management advice in relation to programming and construction related issues over many years, including with respect to major projects. I have no doubt as to the expertise of Lynas. The issue to be determined is whether the foundation to his opinion was properly formed such that I should accept his opinion.

# The defendants complained that Lynas formed his opinion on the basis of his acceptance of the information given to him by the plaintiff, in particular, the plaintiff’s version of the constitution of the contract scope of work. The defendants also criticised Lynas on the basis that in forming his opinion he failed to have regard to the off-site activities such as shop drawings, fabrication and painting of structural steel. In the course of his evidence, it became apparent that Lynas was unaware that the contract required a program that dealt with all activities including off-site activities. Ultimately, Lynas analysed the critical path of the building works as depicted in the several programs produced by the plaintiff and, also, analysed the extension of time claims setting out the factual matters assumed in connection with each of the EOT claims. Thereafter, he provided his opinion on whether the delays within the EOT claims affected the critical path of the works.

# Having had the opportunity to read and observe the evidence given by Lynas, I conclude that it was appropriate expert evidence and that his methodology was sufficiently explained to enable the Court to assess and test it. I also conclude that he was suitably qualified to give the evidence he did. As to whether the evidence of Lynas was prejudiced or affected by the fact that it was given to him by the plaintiff, I reject that assertion on the basis that the plaintiff set out in considerable detail all of the items and materials provided to Lynas to enable him to form his opinion. I consider that the complaint of the defendants in this respect is without foundation. I consider, therefore, that the evidence of Lynas was admissible. Insofar as the evidence is relevant for the purposes of the finding of fact with respect to the time delays and EOT claims, I conclude that the evidence was useful, but ultimately, of limited assistance because of the fact that there was ample evidence on both the side of the plaintiff and the defendants as to the circumstances that surrounded each of the EOT claims.

# The other expert who was the subject of objection was Degenhardt. He was called by the defendants in relation to the structural steel delays. The plaintiff complained that Degenhardt did not provide a sufficient basis to identify the manner in which he reached his opinion in a report dated 3 July 2003. There was further complaint that his methodology was not identified. Having had the benefit of reading and observing Degenhardt’s evidence, I am satisfied that his methodology was sufficiently explained to enable the Court to test his opinion and conclusions. Similar to Lynas, I regard the evidence of Degenhardt to be of limited assistance. Ultimately, as with Lynas, it is a matter of assessing the evidence of those involved with respect to the structural steel issues. I conclude that Degenhardt’s evidence was admissible but, as I say, of limited assistance.

Role of THE Superintendent

# Clauses 23 and 24 dealt with the role of the superintendent.

# It was the case of the plaintiff that the defendants breached cll.23 and 35.5 of the agreement. In the Further Further Amended statement of claim, the plaintiff alleged that the defendants breached cll.23(a), (b) and (c) of the contract which required the defendants to ensure that the superintendent acted “fairly and honestly” (cl.23(a)), “within the time prescribed under the contract or where no time is prescribed, within a reasonable time” (cl.23(b)), and was able to arrive at “a reasonable measure or value of work, quantities or time” (cl.23(c)). Allegations of breach of cl.23 were in the context of variations, extensions of time and delay costs. Clause 35.5 referred to claims for extension of time to practical completion. It lists valid causes of delay which entitle the contractor to extensions of time to practical completion i.e. industrial action and inclement weather. The plaintiff contended however that the superintendent failed to grant a reasonable extension of time to the date of practical completion when it requested an additional 180 days. In failing to grant the extra 180 days, the plaintiff alleged that the superintendent failed in the proper exercise of the power granted under cl.35.5. As a result, the plaintiff claimed it incurred loss and damage in the sum of $763,908.

# The plaintiff relied upon three express provisions in the contract: firstly, that the plaintiff was required to execute works under the contract to practical completion by the specified date for practical completion, namely, 10 December 1999; second, that the contractor was liable for severe monetary penalties for non-completion within the stipulated time by way of liquidated damages; and third, that the contractor was entitled to extensions of time under the contract. The plaintiff submitted that the failure of the superintendent to properly deal with and determine extensions of time and the consequential breach by the defendants of cl.23 “…went to the heart of obligations which the principals were required to discharge via an appropriate, competent, honest and fair superintendent.” It was submitted that, arising from the way in which the construction contract operated, and the fundamental nature of the effect on the contractor of a breach of cll.23 and 35.5, this provided the basis to characterise the obligations imposed upon the principals by cl.23 as fundamental. It was submitted that the breach of the fundamental obligations, therefore, amounted to repudiatory conduct on the part of the principals. It was further submitted for the plaintiff that the evidence was overwhelming that the principals failed to ensure that at all times there was a superintendent under the contract exercising the essential functions as expressly required under cl.23 of the contract.

# The first superintendent was Tony Hampton. It was clear that Hampton proved to be unacceptable to Sopov who disapproved of Hampton’s approach. Specifically, in giving evidence, Sopov referred to Hampton’s recognition of Kane’s claims, for instance variations, as having made him “angry”, because in Sopov’s opinion the builder’s claims sometimes or often had no bases. It was apparent that Sopov viewed the approach of Hampton as one that amounted to allowing the builder to claim items as it wished. Hampton was a qualified architect and appointed under the contract to act as superintendent. He issued a number of instructions as he was entitled to do pursuant to cl.40 of the contract. Hampton directed extra work to be performed and, further, advised the builder that such work would be in the nature of a variation and that the builder should submit a claim for the appropriate costs for that extra work. This is apparent from the superintendent’s directions 1 – 16, made between 23 June 1999 and 14 July 1999. In his evidence, Sopov made plain his view that Hampton was failing to do that which he, Sopov, required. Sopov gave evidence that he did not know why Hampton resigned as superintendent. It is difficult to accept such a purported lack of knowledge when it was apparent from the evidence of Sopov that he was dissatisfied with Hampton’s performance as superintendent. Numerous instructions were issued by Hampton in his capacity as superintendent during June 1999. These were noted as variations and Sopov objected to this course of conduct. Hampton did not give evidence. However, in a letter he wrote to Sopov dated 16 July 1999, reference was made by Hampton to a lack of “consensus” between him and Sopov as to “fundamental aspects of our work”.

# It then transpired that Jeffery was appointed as superintendent to replace Hampton after the latter’s resignation. Jeffery was a quantity surveyor by profession. The plaintiff criticised his appointment by the principals, charging that Jeffery failed to undertake the important role of independent certifier, viewing his role as one of performing quantity surveying for the defendants. In his evidence, when questioned about his role and his understanding of it, Jeffery made it apparent that he did not draw a distinction between the role of superintendent on the one hand and the role of quantity surveyor on the other. It was urged for the plaintiff that Jeffery did not appreciate the nature of the independent role that a superintendent was required to maintain. It was further submitted that his conduct reflected his misconception of the independence of the role of the superintendent. Emphasis was placed by the plaintiff upon the preparedness of Jeffery to discuss with Sopov the prospect of finding items of deduction against the builder under the contract price. Jeffery said as much in his evidence. Further, reliance was placed upon the discussions and investigations conducted between Sopov and Jeffery as to the sums that could be deducted from the builder’s contract price without communicating the fact of the discussions and the investigations to the plaintiff. The plaintiff described these discussions as “bipartisan” and submitted that they were not the act of an honest, fair, reasonable and independent superintendent who was to ensure that both the principal and the builder had an opportunity to put their position forward in relation to relevant items. Jeffery was criticised by the plaintiff for performing no more than a “rubber stamp” role as to sums of money that the defendants informed he should include in the costs to complete certificate. It was urged that Jeffery breached his duty as independent superintendent to ascertain and determine the cost incurred in completion pursuant to cl.44.6 and was obliged to require substantiation of costs incurred pursuant to cll.41 and 44.6. Ultimately, it was put for the plaintiff that Jeffery was dominated by Sopov and did as the latter directed or, alternatively, was incompetent and misconceived the nature of his role and the duties he was required to discharge under the contract.

# I consider that Jeffery had an undesirably close relationship with Sopov given the independent role the superintendent is expected to maintain. The circumstances were compounded by Jeffery’s failure to determine extension of time claims within the appropriate periods, namely, within 28 days pursuant to cl.35.5.

# Upon consideration of the delays by Jeffery in determining the EOTs, and his conduct in communicating his determinations in the letter dated 8 May 2000, I am led to conclude that he did not act competently, or independently, in this role as superintendent. The plaintiff urged a finding of undue influence by Sopov over Jeffery. I am not prepared to make that finding. Rather, I am of the view that Jeffery failed to understand the obligations of his role and postponed making the decisions he ought to have more promptly made as superintendent, in all likelihood, because of the interference of Sopov. An allegation of undue influence is a serious matter, notwithstanding that it is often difficult to define.

# While I am not satisfied that the circumstances constituted undue influence, I am satisfied that Jeffery failed to perform his role as superintendent in a competent and independent way. This had a cumulative and influential effect upon the performance of the contract. It is apparent from the correspondence that there was a great deal of tension between Jeffery and the plaintiff and the plaintiff’s employees and sub-contractors. In a letter of the plaintiff dated 21 January 2000, a specific complaint was made that Jeffery was not independent. Jeffery did not respond until 2 March 2000 and in my view did not address the allegation of the plaintiff of 21 January 2000 other than to refute the allegations. Jeffery failed to comprehend the need not only to be seen to be independent but actually to be independent. The plaintiff urged that the response of Jeffery in his letter of 2 March 2000 should lead to a finding of undue influence. I remain of the view that the letter only went so far as to reinforce my view as to the incapacity of Jeffery to act independently as he was required to do under the contract because of his procrastination and incompetence in that regard.

# Overall, the approach of Jeffery, as he admitted in his evidence, was one of avoiding to make decisions whilst endeavouring to keep discussions alive between the plaintiff and the defendants in the hope that an agreement would emerge. Unfortunately, that was not his role.

# There was an additional factor that placed Jeffery in an unfortunate context. He was, while superintendent, acting at the same time as the certifier for the National Australia Bank. In the latter role he confirmed the figure of $3,650,000 as a realistic budget for the project as early as August 1999 in an interim report to the bank. Whilst that of itself would not be sufficient to lead me to conclude that Jeffery failed to meet the requisite standard of independence, it was an unfortunate position in which to allow himself to be placed. I do not regard Jeffery as in any way to have acted dishonestly. Rather, I view him as a witness who set about with best intentions to resolve disputation between the plaintiff and the defendants. As I have observed already, that was not his role.

# Notwithstanding this finding of fact with respect to the conduct of Jeffery, it is necessary to turn to the matter of the construction of the expression “honestly and fairly” in cl.23 of the contract. The expression does not appear to have been judicially considered. However, some assistance can be drawn from the observations of McFarlane J in Perini Corporation v Commonwealth of Australia. In that case, the builder contracted with the Commonwealth to build the Redfern Mail Exchange and the certifier was a Commonwealth official called the “director of works”. Whilst not directly concerned with conduct and actions that satisfy the standard contract requirement of acting “honestly and fairly”, McFarlane J examined several factors that were relevant to the making of the decision of the certifier (in this case the superintendent). It was held that the certifier could rely on other persons to supply information on which the certifier could in turn exercise a discretion; the certifier was bound to provide a decision on any application for extension of time within a reasonable time; and that the certifier could consider departmental policy but would be acting wrongfully if he considered himself as controlled by department policy. In the context of securities, the expression “efficiently, honestly and fairly” has been considered: see Storey v National Companies and Securities Commission. In that case, Young J observed:

“Considerations of this nature incline my mind to think that the group of words ‘efficiently, honestly and fairly’ must be read as a compendious indication meaning a person who goes about their duties efficiently having regard to the dictates of honesty and fairness, honestly having regard to the dictates of efficiency and fairness, and fairly having regard to the dictates of efficiency and honesty”.

# Young J in Storey further considered the expression “efficient”:

“So far as ‘efficient’ is concerned, someone is an efficient person or performs his duties efficiently if he is adequate in performance, produces the desired effect, is capable, competent and adequate”.

# Still within the corporations context, Bollen J in RJ Elrington Nominees Pty Ltd v Corporate Affairs Commissions (SA) considered the expression “honestly”:

“I think that the word ‘honestly’ may comprehend conduct which is not criminal but which is morally wrong in the commercial sense. It comprehends conduct which is not straightforward. Moreover, I think it may comprehend such conduct viewed objectively”.

# In the present context it would seem to me that a superintendent would act “honestly and fairly” when that individual is not dishonest, is just and impartial and conducts him or herself in a reasonable manner.

# I am augmented in my view, therefore, that there is no issue that Jeffery acted dishonestly.

# It is also appropriate to visit the commentaries and authorities with respect to undue influence. Commentators have considered that undue influence arises in certain circumstances but including where there is improper pressure, influence or interference by the owner.

# It is useful to consider the analysis in Hudson’s Building and Engineering Contracts in Australia on the topic:

“It is submitted that fraudulent motion is irrelevant in considering [interference] which is sufficiently wide to cover any improper interference with the certifier’s independence and function by either party. It is, of course, both usual and proper for both parties to make representations, however strongly worded, to the certifier upon any matter or dispute upon which the contract requires him to certify. The dividing line between such representations and pressure of an improper kind is not difficult to discern in practice, and broadly speaking any pressure or action which goes beyond representations confined to the merits of the matter in question, or which does not expressly or impliedly recognise the certifier’s ultimate right and duty to decide the matter impartially on its merits, will be suspect:

“where a surveyor is put into that position to give a certificate, I do not say that he is an arbitrator, but he is an independent person. His duty to give the certificate according to his own conscience and according to what he concedes to be the right and truth as to the work done, and for that purpose he has no right to obey any order or any suggestion by these people who are called his masters; for that purpose they are not his masters”.

# In Hudson’s, it was further stated that:

“No doubt where interference or pressure by an owner results in no certificate being given, the prevention principle will apply but the cases show that other forms of influencing or interference need only be such as to cast doubt on the certifier’s independence … once the certifier’s independence has become suspect, the courts will not concern themselves unduly with the extent or degree of influence over the certifier, or its precise impact on the certificate in question.

Apart from cases where, on the facts, the prevention principle can properly be invoked, the basis for this ground of avoidance of certification of decisions will be an implied term prohibiting the improper influencing of certifiers, it is submitted”.

# There is a line of authorities where the courts have considered interference of the certifier or superintendent by the principal.

# A set of indicia of interference of a superintendent may be extracted from the authorities. First of all, with respect to the role of the superintendent, interference leading to impartiality can arise in a series of circumstances. These include when the superintendent allows judgment to be influenced;  when the superintendent is in a position whereby the certificate is deprived of value;  when the superintendent acts in the interests of one of the parties and by their direction; when the position is misconceived and the superintendent acts as mediator; when there is not sufficient firmness in order to decide questions based on his or her own opinion;  where judgement and conduct are controlled by the principal; and where the superintendent considers the assent of the principal to be necessary, has ceased to be a free agent and does not give full disclosure of every communication between the superintendent and the principal. Finally, the superintendent may lose independence without actually intending to do so or even without knowledge they have done so.

# In relation to the principal, interference will arise where there is an attempt to lead the superintendent astray in the interests of the principal; and where there is correspondence and communication of an improper character between the principal and the superintendent. In relation to the contractor, interference will arise where the contractor has no knowledge of the interfering conduct so as to prevent the builder raising the point.

# In Peninsula Balmain Pty Ltd v Abigroup Contractors Pty Ltd, the New South Wales Court of Appeal considered, in a limited context, the duty of superintendents to act honestly and impartially. In that case, the principal entered into a project management agreement with the superintendent that authorised the superintendent to act as agent of the principal in “all matters relating to the design and construction of the project”. The contract was not disclosed to the contractor under the building contract. The contractor argued that the engagement by the principal of the superintendent to act as agent and its not being disclosed to the contractor was a breach of the contract and, also, s.52 of the Trade Practices Act. On appeal, Hodgson JA held that the superintendent is not in all matters acting as the principal’s agent and in the circumstances of the case, there had not been a contractual breach or misleading and deceptive conduct because of the non-disclosure of the project management agreement. Hodgson JA (with whom Mason, P and Stein JA agreed) said:

“However, in my opinion, the better view … is that the Superintendent is the owner’s agent in all matters only in a very loose sense, and that, when exercising certifying functions in respect of which the Superintendent must act honestly and impartially, the Superintendent is not acting as the owner’s agent in the strict legal sense. In my opinion, this is confirmed by the consideration that the use of a certificate by the Superintendent does not bind the owner to any extent beyond what is proscribed by the building contract itself, so that the owner can challenge such certificates. If the Superintendent was acting as the owner’s agent in the strict sense, the issue of the certificate would be an act done by the owner through its agent, which the owner could not then challenge. “

# Although Peninsula was a case concerned with a project management contract, the observations of Hodgson JA are of assistance in construing the relationship between principals and superintendents generally under building contracts. Turning then to the indicia of interference already outlined, I remain of the view that Jeffery did not act competently and allowed himself to be placed in a position where he ceased to be independent.

SET-OUT: STRUCTURAL STEEL AND EOT 4

# The issues of the set-out, structural steel and EOT 4 were interwoven. It is convenient and practical, therefore, to deal with these issues in the same section.

# It was common ground between the parties that the structural steel delays were critical to the date of practical completion and EOT 4. Clause 28 of the contract outlined the contractual obligation of the plaintiff to perform the set-out. The defendants did not plead in their defence that the plaintiff breached its obligations with respect to set-out under cl.28.

# The evidence of the defendants with respect to set-out was provided by Jeffery. He gave evidence that there were “an extraordinary number of set-out errors”. The plaintiff complained that the criticism of the defendants with respect to set-out was not properly made and, further, that there was no evidence of specific instances of errors. It was acknowledged by the plaintiff that there were a series of RFIs that related to variations from the original contract works. Tivendale, Kane’s project manager, conceded that those RFIs impacted on the set-out of the works. He said that the plaintiff performed the surveys and provided grid lines and that the sub-contractor worked from the grid lines and contract drawings to provide the set-out position for internal walls. Tivendale also said that a survey was carried out by Williamson in the first three weeks of the project and that Omond transferred those lines up the gridlines as the works proceeded. He further stated that the contract documents stated the size of the particular room that was desired but did not include any of the walls or closed dimensions from one side of a grid to the other.

# Williamson gave evidence about these matters. He was not cross-examined about set-out. Tivendale described a series of difficulties arising under set-out: difficulties with room dimension, lack of specification in the contract documents regarding wall thicknesses and the failure of the dimensions to work off the gridlines. Tivendale demonstrated the difficulty with the set-out by reference to drawings A38–A in relation to the floor plan of apartments 10 and 13. He pointed to the drawings and the fact that whilst they showed room sizes they did not provide dimensions of the wall thicknesses. Tivendale said that for this reason it was not possible to know the overall dimension from one side of an apartment to the other. He said that experience disclosed that work was performed by the plaintiff from one side of an apartment to the other and when the other side was “reached” ultimately the wall did not line up with the edge of the terrace which in turn was governed by the set-up of the ground floor. Tivendale said that there were set-out errors on several occasions that resulted in the services being installed in the building in the wrong places.

# Tivendale described set-out difficulties encountered with MTK, the plastering firm. He said there was a list of RFIs relating to the correction of set-out difficulties and items that were not working as shown on the original documents. In his evidence, Tivendale said that MTK was responsible for the set-out of the walls and that MTK worked off the contract documents and the set-out drawings. The arrangement was that if MTK encountered difficulties it was to notify the plaintiff who would then resolve the problem. As an example of a problem encountered, Tivendale referred to apartment 9 (and also apartments 10 and 13) where he said that the plaintiff had to return and fix the position of the wall and associated plumbing because of errors. The evidence of Tivendale in this respect was not contradicted.

# Tivendale said that MTK was provided with all the architectural drawings, including the set-out drawings AA01, AA02 and AA03, and also the apartment fit-out drawings, from AA28 through to AA40. Tivendale said that the only other documents provided to MTK were the RFIs that clarified the directions of the superintendent. Tivendale said that the fundamental problem was a combination of the fact that the set-out did not contain the thicknesses of the walls and that no adjustments were made to take into account other instructions received by Kane in relation to variation of the works. Tivendale gave evidence, by way of example, that the plaintiff received a specific instruction relating to the terrace areas and the Alucobond areas in the set-out of the structural steel that referred to a different position than that shown on the drawings.

# Tivendale expanded on the difficulties encountered. He said that, in relation to apartments 10 and 13, the set-out of the wall between the living room and the dining room and between the second bedroom and the laundry had to line up with the edge of the terrace. Tivendale explained that the dimensions from the laundry through the ensuite to the wall did not exactly place the wall in that position and that it was somewhere between 300mm or 400mm out of alignment. Tivendale said that as a consequence, the plumber was required to relocate a service duct. He said that there were similar problems encountered with apartments other than 10 and 13 and that they were caused by the lack of indication on the drawings as to the thickness of the walls. The project manager also stated that there were changes to the works that had consequential ramifications for other apartments.

# Tivendale said that he raised the issue of the lack of detail in the drawings as to the thickness of the walls with the architect Hampton. He said he raised it early in the contract. He said that the issue was raised in an RFI when the plaintiff made a specific enquiry in relation to the thickness of the walls, in particular, as to their constitution. Tivendale said, and I accept, that the plaintiff was informed by Hampton that once it started to perform the set-out it would have to raise queries and have them answered. Tivendale said the direction came from Hampton in the first month of the project. He said there were no errors by the plaintiff in undertaking the survey. He said the method of the plaintiff was to walk through the gridlines based upon the overall set-out dimensions. He said that the next step, as part of the structural steel set-out, was for Kane to provide the blueprint for the external walls and the gridlines and the location of the installation of the structural steel.

# Tivendale did not consider there were any errors by the plaintiff in that process. The defendants did not call Carpenter, the original design architect; Hampton, the original superintendent; Irving, the architect on-site from November 1999; and furthermore did not cross-examine Williamson who performed the set-out works on the project. The defendants originally intended to rely upon the witness statement of Irving, however, it seems due to the non-availability of the witness to appear at trial, counsel agreed to rely on his witness statement.

# I accept the evidence with respect to the difficulties that arose over set-out. Examination of the plans and drawings, together with the examples given by Tivendale with particular respect to apartments 9, 10 and 13, supported his evidence. I conclude that the plaintiff has made out its claim with respect to set-out.

# I turn then to the matter of structural steel delays. The contractor, DVP Engineering Pty Ltd, let their drafting sub-contract on 18 June 1999 to S & D. The principal draftsperson for S & D was Qi Shao. She gave evidence that the structural drawings were inadequately detailed for the purpose of producing shop drawings for the fabrication of structural steel. Qi Shao said that, had the documentation been adequate, she could ordinarily have expected that the drafting could have been completed within four to six weeks. She gave evidence that the drafting commenced in mid-June 1999 but in fact was not completed until late October 1999, a period of approximately four months.

# Qi Shao identified inconsistencies in the drawings, and drawings which she said were unworkable due to insufficient detail, compounded by delay caused by subsequent alterations. She estimated that more than 40 per cent of the shop drawings were in fact revised. S & D, through Qi Shao, complained to DVP on 16 November 1999 explaining the problems experienced in undertaking the drawing work. Specifically, S & D complained at the lack of information on architectural drawings, the lack of information for the balcony and hand-rail work, changes made by the defendants to balcony set-down levels, the need to revise and redraw more than 50 drawings, the revision of the balcony gutter detail and the addition of a number of columns and channels along grid A, further balcony changes in grids A and C thereby necessitating the redrawing of 15 drawings, and changes to beams 27A and 29A.

# Both Qi Shao and S & D were criticised at trial as to their professionalism and capacity to undertake the work involved in the project. Dordevic, the principal of DVP, gave evidence as to his dealings with S & D from time and time and his satisfaction with their standard of workmanship. Importantly, Dordevic said that the time allowed to fabricate the structural steel was two weeks but that as a result of the delays caused through the preparation of the shop drawings, the fabrication of structural steel took a period of two months between 15 September 1999 and 22 November 1999.

# Dordevic explained delays to the structural steel arising from the gallery shopface drawings and alterations to delete six columns, 12 connection points to the ARC columns on six beams and the relocation of bolt holes on the beams for the altered hand rail layout. He also listed level 2 columns and level 3 beams and balcony changes. Dordevic said that columns and beams that had been manufactured in the workshop of DVP had to be altered. In particular, Dordevic said that revisions were made to the steel work to apartment 11 and this involved the revision of 13 shop drawings in relation to steel which had already been fabricated. He said that the area including the beam described in drawing 27A was put on hold until the correct drawings were approved. He said that DVP was instructed not to commence fabrication of drawings until approval which did not come from the engineer until 6 October 1999.

# Dordevic also described changes to the shop drawings for the balcony for apartment 11. He said that those changes were made on-site when the altered steel was finally delivered. He said that the beams that had already been installed were done so on the basis of earlier approved shop drawings and that the beams had to be removed, delaying the project for nine days. Dordevic said that on 5 November 1999 beam 3B26 was further revised from a straight to a cranked beam after it had been installed. This, he said, involved a further delay of nine days. Dordevic said that the instructions in relation to beam 3B26 were again altered on 12 November 1999 thereby causing further delay between 19 and 23 November 1999, a period of 2.5 days.

# Dordevic also referred to problems arising from a design oversight and the need to provide additional columns. He said that those problems created a delay between 30 September and 14 October 1999 of five days. Dordevic said that he considered the erection of steel on-site should have taken 10 consecutive days but that, as a direct result of the difficulties of the documentation, delays were caused to fabrication and to fabricated steel members. As a consequence, Dordevic said the erection of the structural steel at the project took 12 weeks to complete from 21 September to 13 December 1999.

# Dordevic said that he believed the main problem could be attributed to the delay caused to S & D in the production of their shop drawings. He said that, instead of DVP being able to complete the job, they had to perform it on a piecemeal basis.

# There were other issues connected to the steelworks that related to Dordevic. An error of some concern was the gallery façade steel. Dordevic was criticised at trial for the way the task was performed. It was suggested to Dordevic that the gallery façade was not part of the main structure (with the underlying suggestion that it should not have caused primary delay to the completion of the steel work). Dordevic rejected the suggestion and said that the gallery façade steel columns were attached to the main structure. He said that there was a continuous connection between the steel members and that they all formed part of the gallery façade.

# Dordevic also stated that the structural steel work on the roof could not be finished before other parts of the roof steel had been connected. He said that the roof could not be sealed until other members were connected to the roof steel. Further, Dordevic said that the gallery façade steel could not be left to be completed until later, after the main structure was built, because it was necessary to set the perimeter from the bottom of the building and to work upwards. Similar evidence was given by Degenhardt. Again the problem was attributed by Dordevic to the delay in the production of the shop drawings by S & D, in turn caused by all the changes and difficulties that S & D encountered.

# Qi Shao, in her evidence, said that from the beginning there were so many items missing from the drawings and such a lack of information that an unusual number of meetings were convened to clarify discrepancies and lack of information. Qi Shao described a series of problems that appeared to compound these difficulties as she worked through the job. She described the lack of dimensions and the constant need to seek clarification; her incapacity to move forward with the job; difficulty in producing the holding down and marking plans because of lack of dimension on the structural and architectural drawings; issues about the exact location of an arch, columns and other matters related to columns; difficulty with a gridline; insufficient detail about set-out; details that were required about entry to the building; and changes to design.

# The plaintiff submitted a notice of delay on 17 September 1999. It disclosed that the delay claim was based on delay to shop drawings and the manufacture of structural steel. It was concerned with events up to 17 September 1999. A letter from Kane to Jeffery on 8 October 1999 also informed of delays to the structural steel and their “flow on effect” and enclosed a copy of a revised Boilerhouse program to reflect these delays. The delays claimed formed part of EOT 4. The letter and revised program was accompanied by a document entitled EOT Costs Assessment. It set out a claim for a delay of 32 days together with a claim for a “contingency” period of 15 days. The defendants complained that, in the course of his evidence, Tivendale transformed the 15day contingency period into an actual delay claim when in fact it never constituted such.

# The evidence of Qi Shao was important to the EOT 4 claim, she having attributed the delay of her work to the lack of detail and information in the drawings with which she was provided. Under the contract, the plaintiff bore the responsibility to obtain satisfactory and sufficient dimensions. The defendants attributed the difficulties encountered by Qi Shao to the failure of the plaintiff to retain a quantity surveyor to survey and set out the work.

# The determination of the issues arising from the set-out, structural steel and, consequentially, EOT 4, are very complex and difficult to separate. Insofar as there were inconsistencies, or an absence of, or inapplicable details in contract drawings, those were matters about which Tivendale, Qi Shao, Dordevic and Long gave evidence. They were matters that fell within the province of the plaintiff. The plaintiff carried an obligation to ensure that appropriate drawings were available to sub-contractors. However, to the extent that difficulties were encountered because of changes, late changes and rejection of structural steel and shop drawings and, also, lack of timely responses to queries by S & D and DVP regarding the drawings, the fault appears to largely lie on the side of the defendants.

# Specific delays were encountered with respect to the structural steel and the shop drawings as to the commencement of drafting; the gallery face; the re-design of the structural steel to the second and third floor beams and balconies, the re-design of the north-west corner and inconsistencies in the balcony step-downs; beams 97A and 99A; and level 3 columns and roof beams.  For EOT, Kane claimed 32 days overall.

# The plaintiff estimated the delay caused by the commencement of drafting with respect to the structural steel was 12 days. I do not consider such allowance should be made. The drafting should not have commenced, stopped, been  delayed and then resumed in the absence of satisfactory detail and clarification.

# In relation to the gallery face shop drawings, the plaintiff claimed there was a delay of 8.5 days. Tivendale gave evidence that gallery façade steel work was structural and critical because it dictated where the southern level 2 columns and the southern level 3 floor beams and roof columns were to be located. He accepted that the ARC columns were not structural but considered they were part of the structural steel package. He also considered that the ARC columns and terrace gutters were on the critical path. Dordevic supported the evidence of Tivendale with respect to the gallery façade work and its critical nature. Tivendale emphasised that the tender clarification of the plaintiff stated that there was insufficient detail on the contract drawings in relation to the gutters. He said that there were discussions on-site between 16 July and 6 August 1999 when the plaintiff requested details in relation to the gutters. He said Sopov and Jeffery advised that the drawings contained the detail. I accept the evidence of Tivendale and Dordevic with respect to the gallery face shop drawings. I consider that 8.5 days should be allowed in respect of that item.

# The next item in this category related to level 2 columns and level 3 beams and balconies, the step-downs/apartment 11 balconies and the re-design of the northwest corner. The plaintiff claimed 25 days. On 27 July 1999, RFI 48 advised of inconsistencies in step-downs. A response was received that the step-downs were inadequate. On 6 August 1999 the superintendent directed 70mm step-downs on the east balcony and 190mm step-downs on all other balconies. Kane advised against 190mm step-downs. Further communications occurred. The plaintiff instructed S & D to complete drawings based on a structurally acceptable step-down. Ultimately, on 3 September 1999, a step-down of 140mm was agreed. Sopov disputed that there was an agreement. However, I accept the evidence of Tivendale as to the events of the meeting on 3 September 1999. Further discussion, RFIs, meetings and instructions were provided. Ultimately, the shop drawings in relation to the step-downs were approved on 6 October 1999. On 5 November 1999, beam 3B26 was altered from a straight beam to a cranked beam. By that time, the beam had already been fabricated and installed. On 12 November 1999, instructions were received by the plaintiff to alter the beam and 3B26 was approved. Between 19 and 23 November 1999, the existing or old 3B26 was removed and revised 3B26 was installed.

# A large component of this particular dispute between the plaintiff and the defendants was as to the instruction for the step-downs. Whilst Tivendale acknowledged that the drawings showed a 190mm cut-out on the north-western corner of the building, he relied upon the RFIs as to the risk to the structural integrity of the beam if such a cut-out was made. He also relied upon the agreement of a step-down of 140mm at the meeting on 3 September 1999. I have accepted the evidence of Tivendale. Whilst there was a discrepancy in the drawing that ought have been rectified or dealt with by the builder under the contract, a change was agreed on 3 September 1999 at the meeting. The delay between 27 July (when RFI 48 was submitted providing advice as to inconsistencies in step-downs) and the eventual resolution of the step-downs and cut-outs (at the meeting on 3 September 1999) would lead to a delay attributable to the plaintiff in the order of 12 days and a delay attributable to the defendants in the order of 12 to 14 days. I would regard it as fair and reasonable in the circumstances that an allowance of 12 days with respect to the step-downs within EOT 4 be allowed to the plaintiff.

# The next component affecting the set-down, structural steel and EOT 4 was concerned with level 2 columns and level 3 beams and balconies, in particular beams 97A and 99A. The plaintiff claimed 3.5 days with respect to this item. Dordevic gave evidence that beams 97A and 97B were not shown on the structural drawings. He said that the beams were inserted as a result of his discovering that the wall that was to support the members was too short. He considered, therefore, that it was necessary to support the members with beams 97A and 99A. Whilst Tivendale was not cross-examined on this aspect of the claim of the plaintiff, it demonstrated a deficiency in the drawings that ought to have been identified earlier. It was the obligation of the plaintiff under the contract to identify the deficiency, if any, in the drawings at an earlier time. I do not consider it fair and reasonable in all the circumstances that a delay of 3.5 days as sought by the plaintiff should be allowed in this respect under EOT 4.

# The next component concerned the level 3 columns and roof beams relating to the parapet heights. The plaintiff claimed a delay of four days. As at 24 September 1999, a conflict in heights for the drawings in A07-A was identified. It was apparent that the plant platform was to be fixed into the brickwork on the south side of the building and to extend over the roof and be supported by columns. It was necessary for the platform to have sufficient clearance above the roof to allow for the installation of the roof decking. On 4 October 1999, RFI 143 was submitted. Ultimately, shop drawings were provided on 29 October 1999 and structural steel erection commenced on 15 November 1999. The witnesses for the plaintiff, Tivendale, Lynas and Qi Shao, were not cross-examined on this matter. I am satisfied in all the circumstances that it is fair and reasonable to allow the plaintiff four days in relation to level 3 column beams and roof beams concerned with parapet heights.

# Ultimately, I conclude that in relation to set-downs, structural steel and EOT 4 claim, and in light of the plaintiff’s claim, it is appropriate to allow the plaintiff a total of 32 days.

EOTs 1 - 18

# The plaintiff claimed that it was delayed during the course of the works by various events and, therefore, the date for practical completion warranted extensions of time. There were 18 extension of time claims by the plaintiff totalling approximately 180 days. The events relied upon in support of each EOT were set out in the further amended statement of claim. The detailed events relied upon to support each of the 18 EOTs were set out in particulars provided by the plaintiff.

# Clause 35.5 of the contract made provision for the submission of a written claim for an extension of time for practical completion. It provided that if the builder, that is the plaintiff, was delayed in reaching partial completion by a particular category of cause and if the builder gave the superintendent a written claim within 28 days after the delay occurred outlining the facts on which the claim was based, the plaintiff was possibly entitled to an extension of time for practical completion. The causes specified in the contract included industrial conditions and inclement weather, provided such causes occurred on or before the date of practical completion. The causes also included delays caused by the principals, that is the defendants, the superintendent, the principals’ employees, consultants or other contractors or agents, latent conditions, variations as directed under cl.40 of the contract, repudiation or abandonment by a nominated sub-contractor, any breach of the contract by the defendants and other causes that were expressly stated in the contract to be a “cause for extension of time”. Clause 35.5 provided, further, that the superintendent was required within 28 days after receipt of the notice of the extension of time claim to grant a reasonable extension of time. It provided, also, that if within the 28 days the superintendent did not grant the full extension of time claim, the superintendent was required before the expiration of the 28 days to give the plaintiff notice in writing of the reason.

# In addition to cl.35.5 and the provision for EOTs, it remained open to the superintendent, at any time and from time to time before the issue of the final certificate, by notice in writing to the plaintiff, to extend the time for practical completion for any reason. Furthermore, under cl.35.5, the superintendent was obliged to certify an extension of time for the plaintiff where it may be fair and reasonable to do so, notwithstanding a plaintiff’s failure to make a claim or non-compliance with the relevant timing requirements for an extension of time claim: see Abigroup v Peninsular Balmain. Hence, the plaintiff urged that when considering the entitlements of the plaintiff under the contract, the court is in the same position as the superintendent, including to the extent of considering whether extensions of time ought be granted and, also, whether in the circumstances it would be fair and reasonable to grant the plaintiff an extension of time.

# Before turning to the individual EOTs, it is instructive to consider the principles generally applied with respect to EOT claims. An adjustment to the time of practical completion is only available where there has been an actual delay and the delay was caused by one of the events set out in the contract. Any delay that does not affect practical completion is irrelevant. Further, where the contractor has been delayed by one of the reasons set out in cl.35.5 of the contract, for example, delay caused by an act of the principal in combination with another valid delay, then the situation of concurrency may exist and the contractor would not be entitled to an additional extension of time; it would be calculated as if just one event of delay had occurred.

# The approach to be applied by the courts with respect to EOT claims was considered in McAlpine Humberoak Ltd v McDermott International Inc (No.1), a UK Court of Appeal case. In October 1981, the plaintiff sub-contractor, McAlpine, was invited by the defendant, the main contractor, McDermott, to tender for the construction of nine steel pallets forming part of the top weather deck for an offshore drilling rig known as the Hutton Tension Leg Platform in the Shetland Basin. In November 1981, McDermott sent a letter of intent to McAlpine awarding the contract for four of the pallets, however the contract was only finalised on 24 March 1982. The contract itself was expressed to have been in effect from 18 November 1981.

# The trial judge concluded that the issue of drawings had resulted in frustration of the contract (which “came as a surprise to the parties, since frustration had not been pleaded, or argued”). The finding of frustration by the trial judge (which led the trial judge to award the plaintiff quantum meruit equal to their costs plus 10 per cent profit) was overturned by the Court of Appeal. Leave was granted for the defendants to appeal on fact as well as on law.

# Essentially, McAlpine contended that the contract between the parties had been broken and that they were entitled to recover on a proper valuation of certain variations. The plaintiff claimed £3,590,000 in damages from the defendants. In deciding the case, the court contemplated how delay was to be taken into account when considered against the time by which the work might have been completed. For instance, is a contractor entitled to an extension of time until at least after the date of that instruction? The Court of Appeal considered that, as a general rule, a period of excusable delay should be added to the end of the contract period, however, that the outcome of each case in this regard must depend upon the wording of the contract.

# The Court of Appeal in fact specifically rejected the trial judge’s findings in McAlpine with regard to delay and extension of time issues. At first instance, the judge determined that the “concatenation of causes of delay and disruption” claimed by the plaintiff all boiled down to two basic causes: (i) the issue of additional drawings which had a flow-on effect to the rest of the work; and (ii) the slow response of McDermott to numerous Technical Queries (TQs – similar to RFIs in this case) to approve drawings and designs. The effect was therefore “frustration” of the contract.

# Cause (i) was rejected by the Court of Appeal on the basis that the revised drawings did not “transform” or distort the substance and identity of the contract. As for (ii), the Court of Appeal failed to find that the time taken by McDermott to respond to the plaintiff’s TQs inhibited the progress of the works overall.

# In his Honour’s judgment, with which the other two members of the Court were in full agreement, Lloyd L.J. noted that the appropriate approach to be taken departed from that preferred by the trial judge. At first instance, McAlpine’s experts made broad assumptions to the effect that a great deal of delay in relation to each instruction was critical and impacted in full upon the completion date, without appropriately considering the overall context of the works being carried out on-site at the time. According to Lloyd L.J., the approach of the defendants was in fact far more desirable:

“When the defendant’s witnesses came to give evidence, they undertook the task which was never undertaken by the plaintiff, of tracing the impact of every drawing revision, VO [Variation Order] and TQ [Technical Query]… The judge [at first instance] dismissed the defendants’ approach to the case as being ‘a retrospective and dissectional reconstruction by expert evidence of events almost day by day, drawing by drawing, TQ by TQ and weld procedure by weld procedure, designed to show that the spate of additional drawings which descended on McAlpine virtually from the start of the work really had little retarding or disruptive effect on its progress’. In our view the defendants’ approach is just what the case required.”

# Lloyd LJ was in this way able to provide strong guidance on the appropriate approach to be taken to these sorts of cases. The analysis should be principally a factual one, with good records in support. The relevant events and their effect should be looked at according to the time in which they occur and in the context of the work actually going on at the time. In other words, global claims are bound to fail.

# Lloyd LJ went on to state in McAlpine that the notion that “if time was at large, the price was also at large” lacked support in the authorities. In reaching this conclusion, Lloyd LJ examined the effect, if any, of Wells v Army & Navy Co-operative Society and the following line of cases, where the plaintiff commonly sought liquidated damages, and generally where there was either no fixed date for completion or where the completion date had been changed. In Wells, the employer’s claim for liquidated damages ultimately failed because the employer could not rely on the original date of completion nor on a power to extend the date of completion. Lloyd LJ pointed out that it would be a mistake however to rely upon Wells and the following line of authority directly in this case given that the defendants were not seeking liquidated damages. Nevertheless, Lloyd LJ also noted that nothing in the authorities suggested that even where time was “at large”, that the price would be also.

# In particular, when considering delay as against the date of practical completion, the court in McAlpine considered that the following attitude would generally be the correct one (albeit one that ought to be treated with caution given that each case differs according to the wording of the contract):

“If a contractor is already a year late through his culpable fault, it would be absurd that the employer should lose his claim for unliquidated damages just because, at the last moment, he orders an extra coat of paint.”

# In a nutshell, the employer, or in this case the principal, preserves the right to damages for delay, whether liquidated or unliquidated, where the contractor has no legally sound explanation as to delay.

# In McAlpine, the case proceeded through an extremely long trial, lasting 92 days. The Court of Appeal in McAlpine warned that it was a particular danger in cases such as these that what is “trite” - but nevertheless correct - law may be forgotten in the mass of detail. Thus, despite the superabundance of facts as in the matter before me, the success of the plaintiff’s case in reality relies upon just a few points of law. In short, there needs to be a breach of contract or some other contractual justification for the claim to be made out.

# McAlpine outlines the general approach which should be taken with respect to EOT claims. More specifically, with EOT claims, the burden of proof is on the claimant to establish actual delay. Whilst theoretical calculations, particularly those contained in computer software programs, are useful tools in the building industry, generally further information will be required. Whilst there may be assumptions and calculations, it is necessarily a matter of the claimant proving in the proper way that there has been actual delay such as to substantiate claims for reimbursement.

# Thus, in this case, it behoved the plaintiff for the purposes of the EOT claims to establish that it had actually been delayed and that damage was actually suffered by reason of that delay. The defendants argued that the plaintiff failed on both counts.

# As observed, to assist in deciding the point, McAlpine casts the necessary approach as one that requires a builder, in this instance the plaintiff, to present a drawing by drawing, beam by beam, column by column, gutter by gutter factual analysis to show how a particular event had the effect of delaying other identified work.

# For the purposes of the EOT component of its claim, the plaintiff, in this case, relied upon the evidence of Tivendale and, also, the expert evidence of Lynas. Evidence was also given by Dordevic and Qi Shao with respect to the set-out and shop drawings and the impact upon delay; Skarajew as to events on-site through his diary; Omond and, also, Lynas as to the technical analysis of the EOTs and the delays. The evidence of Tivendale in this regard was received subject to objection. The defendants argued that Tivendale was not on-site, did not have first-hand knowledge of the delays and the circumstances that allegedly caused those delays and that he lacked the expertise to give such evidence. I do not accept the objection. Clearly Tivendale had expertise in light of his professional qualifications and experience. As the project manager he also had experience with respect to the site itself. More particularly, Tivendale had experience in relation to the application of software utilised on modern building sites. In the context of a substantial building work it is inconceivable in the modern day and age that technological resources could not be utilised. The Court of Appeal in McAlpine was not concerned with the software support which was so obviously available to the plaintiff in the present case. In my view, the evidence relied upon by the plaintiff was appropriate and admissible.

# The question then arises as to whether or not the extension of time claims were made out. So far as the expert evidence of Lynas is concerned, in my view, for reasons I state at the end of this judgment, it was admissible and presented in an appropriate form constituting expert evidence. It was not evidence of the fact of the delay but evidence, quite properly, as to the nature of the delay and whether it was fair and reasonable in all the circumstances in a technical and complex context.

# In addition to their complaint concerning the lack of proper proof of the EOTs, the defendants attacked the plaintiff’s claim for EOTs on a number of bases: firstly, it relied upon s.33 of the Domestic Building Contracts Act, which I deal with separately; second, the defendants asserted that the plaintiff was entitled to only six days and three hours of the total 180 days claimed in the EOTs; third, the plaintiff had applied for 169 days and seven hours extensions of time only; fourth, the superintendent had extended time by 11 days and six hours in any event; fifth, the defendants argue that cl.35 of the contract precluded the plaintiff making EOT claims beyond 69 days and seven hours.

# I turn next to the individual EOT claims. There was agreement between the parties that the critical EOT claim was EOT 4, which was principally concerned with delays connected to set-out and the shop drawings, as already dealt with above.

# Inevitably, extension of time claims involve the immersion of the court in the minutiae of the building site. In the present case, as already observed, a total of 18 extension of time claims were made. However, within each EOT there were extensive sub-claims relating to a variety of issues. Ultimately, it is appropriate in a case of this nature for a court to adopt a robust view based upon the evidence before it, somewhat akin to the approach taken in building cases by the application of the Scott Schedule. I have, therefore, carefully considered the evidence with respect to each of the EOTs in this case.

# When a proceeding comes before the superior court of the State, it is desirable and in the interests of justice that such a robust approach be taken notwithstanding the extent of time taken up at trial and the expanse of documents preoccupied with the EOTs. Hence, each claim is looked at individually and the evidence analysed, albeit in a concise and brief manner, requirements as set out by the Court of Appeal in Fletcher Construction Australia Ltd v Lines MacFarlane & Marshall Pty Ltd (No. 2).

EOT 1

# EOT 1 was dated 19 July 1999. The delay was based upon alleged latent conditions. The claim by the plaintiff was for 13 days consisting of eight days for excavation for an overrun pit and five days for work to a car park entrance. The documents in support of the eight days for excavation disclose only a  four day delay together with one day that was saved by deletion of the tanking of the overrun pit. Thus, there was a net delay of three days with respect to excavation. The balance of EOT 1, being five days for work concerned with the car park entrance, were acknowledged by Tivendale to be works that were not critical and could have been done at any time. It was suggested for the defendants that Tivendale had manipulated his software programs to produce an “ex post facto justification” for the claim. I do not consider that the criticism should have been made. However, as the works could have been done at any time, I do not consider that the five day delay with respect to the carpark entrance under EOT 1 was made out.

# I conclude that three days should be allowed for EOT 1.

EOT 2

EOT 2 arose from industrial action. Two days were claimed by the plaintiff. In my opinion, there was no real issue that the two days should not in fact be granted. I am satisfied that is appropriate.

# I conclude that two days should be allowed with respect to EOT 2.

EOT 3

# EOT 3 also arose as a result of industrial action. The plaintiff claimed 3.25 days by way of industrial action between 12 August and 1 September 1999 and alleged additional consequential work between 9 and 10 September 1999. I am satisfied that additional work was carried out on the Level 2 Slab (notwithstanding that it was not included on the critical path at this time). I accept the evidence of Tivendale.

# I conclude that a total of 3.25 days should be allowed for EOT 3.

EOT 4

# EOT 4 is concerned with connected issues of the set-up and the shop drawings. It involved a total extension of time claim of 45 days. It was also pivotal to the case because of the consequential ripple effect it had on the whole construction project. I have already dealt with EOT 4 separately.

EOT 5

# EOT 5 was dated 9 November 1999. It arose as a result of industrial action. Three days were claimed and 2.5 days were allowed. There was no dispute by the defendants as to that allowance. On the evidence, I conclude that 2.5 days should be allowed on EOT 5.

EOT 6

# EOT 6 related to a series of matters: inclement weather, industrial action, issues relating to a critical beam 3B76, extra works related to installation of purlins and cleats, extra work for the installation of plywood backing and changes to the working calendar. EOT 6 involved a claim for a total of 16 days and four hours. The first component of EOT 6 was concerned with inclement weather. Two days were claimed and one day and six hours were approved. I accept that the allowance was correct. One day was claimed with respect to industrial action and allowed. I accept that this was appropriate. Two days were claimed but none approved with respect to the removal, alteration and reinstallation of beam 3B76. It was a cranked beam located at level 2 in the corner terrace. Tivendale gave evidence that the beam was removed on 19 November 1999, worked on off-site and re-installed on 23 November 1999. Tivendale said that the extra work delayed the structural steel and other works from being performed on-site. There was no satisfactory explanation by Tivendale as to why the delay was caused, no analysis as to the steel on-site, no details of the steelworkers located on-site, nor any proper explanation of the delay. Notably, there did not appear to be entries in the site diary of Tivendale in this regard. I cannot be satisfied that any allowance should be made with respect to beam 3B76.

# Next, under EOT 6, there was a claim for one day and four hours with respect to the installation of purlins and cleats. This claim related to the roof gutter on the east façade. It is clear that the work was always part of the contract work. Tivendale said that the extra work on the roof gutter delayed the roofing sub-contractor and consequently delayed the critical path of the project. However, I observe that the sub-contractor was not called to give evidence. I am not satisfied that the claim with respect to purlins and cleats is made out.

# The next component of EOT 6 is concerned with the installation of plywood backing to area level 3 utilising a product known as “quietel”, for which Kane claimed five days delay. To a large extent this issue arises with respect to NPV 21. It is apparent from the specification and the manufacturer’s recommendations that the product, namely quietel, was required. It is apparent, further, that the drawings clearly provided for the installation of quietel. Insofar as there was a discrepancy or difficulty, it behoved the builder, that is the plaintiff, to observe any discrepancy. In any event, in my view it has not been shown why level 3 flooring was critical at the time, that is, with respect to EOT 6, or how the delay interfered with practical completion. I do not consider that the claim is made out or that any delay should be allowed.

# Finally, under EOT 6, five days were claimed with respect to changes in the working day calendar. This issue appears to be concerned with the working calendar as imposed by the union. I regard the contract as one that was entered into with a set date for practical completion. The prospect of changes in the industrial calendar were matters about which the plaintiff ought always have been aware, particularly being an experienced builder. Further, I do not consider it fair and reasonable in all the circumstances to allow the five days claimed.

# There was a further issue that appeared to arise under EOT 6 concerning plant platforms and handrails. There was some suggestion that they had an impact upon the commencement of the roofing. The evidence was not satisfactory in this respect. Ultimately, it came down to an assertion by Tivendale that the plant platform and handrail issues caused delay to the installation of the roofing without further evidence. In any event, these items were always part of the contract work. I am not satisfied that any further allowance should be made under EOT 6 with respect to these matters.

# It follows that I conclude that a total of two days and six hours should be allowed under EOT 6.

EOT 7

# EOT 7 was concerned with three items: the installation of floor waste, a total of 42 hours being claimed; installation of plywood backing, a total of 18 hours being claimed; and set-out for mechanical penetrations, a total of four hours being claimed. In total, therefore, EOT 7 involved 64 hours or, in effect, eight days. I observe that each of the items, floor wastes, plywood backing and mechanical penetrations, were part of the original scope of the works. They were also required to satisfy warranty requirements. With respect to floor wastes, the evidence of Tivendale was broad. I am satisfied that the delays were not necessary in order to satisfy warranty requirements. I do not consider that any allowance should be made with respect to floor wastes; in any event, they originally formed part of the contract works.  With respect to plywood backing, Tivendale asserted in a general manner that delay was caused by the plywood backing installation. However, the installation was, in any event, required by the manufacturer. There is no evidence, beyond broad assertion by Tivendale, as to how the installation of the plywood backing caused the delay. I am not satisfied that this component of the EOT claim is made out. With respect to mechanical penetrations, Tivendale referred to the delay in his evidence. However, beyond the bald assertion that delay was incurred, there was a distinct lack of evidence to support the claim. In any case, in the attachment to his witness statement dated June 2003, Tivendale stated that the delay for this component was concurrent with the installation of the plywood backing.

# I conclude that no allowance should be made under EOT 7.

EOT 8

# For EOT 8, Kane claimed a total of 15 days. EOT 8 mainly concerned claims for inclement weather, extra works to steel alterations, extra walls to pull up 19mm structure board and install 18mm CFC board, and industrial action. The matter of alterations to steel works were, in any event, part of the contract works. Further, there was insufficient evidence as to how the alterations delayed the work and affected the date of practical completion beyond the assertion of the fact. With respect to the structural board and the installation of CFC board, delay was said to be caused due to weather and industrial action aspects. However, it appeared that the inclement weather and industrial action claimed under EOT 8 occurred after the date for practical completion. It is difficult to see how it can therefore be claimed. In any event, there was insufficient evidence as to the overall state of the works at the applicable date under EOT 8. Further, the structural board and the installation of CFC board were contract works. Again, there was insufficient evidence as to the nature of the delay and how it in fact affected practical completion.

# I conclude that no allowance should be made under EOT 8.

EOT 9

# EOT 9 was lodged on 23 March 2000. At that time, Kane claimed 11 days and 3.5 hours however, in the plaintiff’s closing submission dated 30 October 2003, Kane claimed 16 days and 3 hours as per Tivendale’s evaluation. EOT 9 was concerned with delays alleged to arise from inclement weather, industrial action and extra works. According to the final submission, two hours were claimed with respect to inclement weather, five hours were claimed with respect to industrial action, and then a further six days were claimed with respect to subsequent action (by the CFMEU in support of an enterprise bargaining agreement claim), and further industrial action leading to a claim of four hours and subsequent extra works involving nine days was claimed. There was insufficient evidence as to the consequential delay caused by industrial action and inclement weather. In any event, these matters arose after the date for practical completion. So far as extra works were concerned, they were concerned with fire rated boxes. These matters were within the original scope of work being required under the Building Code of Australia and, also, being part of the manufacturers’ recommendations.

# I conclude that no allowance should be made with respect to EOT 9.

EOT 10

# EOT 10 was dated 18 April 2000.

# EOT 10 stemmed from industrial action. The claim was based on delay arising from CFMEU statewide industrial action, a claim of three hours; a subsequent and consequential loss of productivity involving two days and three hours; followed by further loss of productivity on account of sub-contractors leading to a claim of one day and two hours; followed by industrial bans leading to a claim of 4.8 hours. The claim was therefore for a total of four days and 4.8 hours.

# Insufficient evidence was given of the consequences of the alleged delays. Furthermore, the relevant industrial action occurred after the date for practical completion. I cannot be satisfied that the claim has been made out.

# I conclude that no allowance should be made under EOT 10.

EOT 11

# EOT 11 involved a claim arising from inclement weather, industrial action and extra works described as “P50/P60”. Eighteen hours were claimed for inclement weather, six hours for industrial action and nine days were claimed with respect to P50/P60. Again, the industrial action occurred after the date for practical completion. In any event, there was insufficient evidence as to how the action gave rise to consequential delays, thereby impacting upon the date for practical completion. So far as P50 and P60 were concerned, I accept that these matters were part of the contract works. The need for these works arose from the removal of the third sheet of Fyrecheck under the tender clarifications. I observe that there were requirements to be met under the Building Code of Australia and in order to accord with the manufacturer’s recommendation. Ultimately, there was insufficient evidence as to how P50 and P60 caused consequential delays.

# I conclude that no allowance should be made under EOT 11.

EOT 12

# EOT 12 was concerned with extra works to design and fabricate appropriate support details to pivot doors, 13 days; inclement weather, two days; industrial action, three days; further industrial action, three hours; further industrial issues (enterprise bargaining agreement negotiations), seven days; and extra work to install P50/P60 as related to EOT 11, four days being claimed.

# With respect to the design and fabrication support details for the pivot doors, the support details were always included in the contract. There was not sufficient evidence to explain how the design and fabrication of the support details of the pivot doors on levels 2 and 3 actually delayed practical completion of the works. I do not accept that they did so. In relation to the installation of P50 and P60, these matters have been largely dealt with under EOT 11. In relation to inclement weather and industrial action, no sufficient evidence was given as to the consequential delays that may have occurred by these matters. In any event, both inclement weather and industrial action in this respect occurred after the date for practical completion.

# I conclude that no allowance should be made under EOT 12.

EOT 13

# EOT 13 was also concerned with the design and fabrication of pivot doors. Five days were claimed. It also included claims for inclement weather, one day and six hours; together with industrial action, one day and six hours; and consequential delay of one day.

# It is clear that the pivot doors were always specified in accordance with the contract and, also, that the instructions of the manufacturer were known. Insufficient evidence was provided by the plaintiff as to the actual delay and its consequences. The plaintiff did not produce shop drawings for the installation of the pivot doors. It is apparent that, if shop drawings had been prepared, any problems would, in all likelihood, have been obviated. Insofar as there was any delay, I would conclude that it was caused by the plaintiff. I am not satisfied that delay has been made out. If it was, I would, in any event, not be satisfied that it was fair and reasonable in the circumstances to allow any time under EOT 13 in this respect.

# In relation to inclement weather and industrial action, insufficient evidence was provided as to the consequential delay caused by these matters. In any event, the matters of inclement weather and industrial action occurred after the date for practical completion.

# I conclude that no allowance should be made under EOT 13.

EOT 14

# EOT 14 was concerned with extra works for the design and fabrication support detail for pivot doors, four days; inclement weather, four hours; and delays necessitated by the bursting of a water main, one day. Five and half days in total were therefore claimed for EOT 14. I have dealt with the matter of the pivot doors under EOT 12 and EOT 13. I am not satisfied that the claim is made out with respect to the pivot doors under EOT 14.

# I am satisfied, on the evidence, that difficulties were encountered with the bursting of a water main that necessarily delayed practical completion and that it is appropriate to allow one day. The issue appeared to be largely unchallenged by the defendants.

# I conclude that one day should be allowed under EOT 14.

EOT 15

# EOT 15 was concerned with the installation of Alucobond soffit at level 3, ardit floor levelling and, also, inclement weather. The various works, Alucobond and floor levelling, constituted a claim of six days; the inclement weather led to a claim of one day and four hours.

# It is apparent that the installation of Alucobond soffit on the third level was at all times part of the contract works. I am satisfied on the evidence that delay arose from a failure on the part of the plaintiff to properly co-ordinate the work. Furthermore, there was insufficient evidence as to the stage the works had reached at the time of the installation of the Alucobond soffit to level 3. I observe that no shop drawings were provided by the plaintiff in relation to the Alucobond soffit. In all likelihood, delays were caused by the plaintiff itself in that respect. I am not satisfied that an allowance should be made in respect of level 3 Alucobond soffit. In any event, I consider that it would not be fair and reasonable in the circumstances to make the allowance sought by the plaintiff.

# With regard to ardit floor levelling, it is apparent that this item formed part of the contract works. So far as inclement weather is concerned, there was insufficient evidence as to consequential delays arising from that element. In any event, the matter of inclement weather occurred after the date for practical completion.

# I conclude that no allowance should be made under EOT 15.

EOT 16

# EOT 16 concerned delays said to arise from industrial action, two hours, and extra works associated in particular with the installation of the Alucobond. A total of 12 days were claimed with respect to the latter. Kane’s claim for 12 days and 2 hours in the final submission was for one extra day than it originally claimed for this EOT (11 days and 2 hours).

# Again, insufficient evidence was provided by the plaintiff as to the consequential delays caused by the industrial action. With respect to the Alucobond and the claimed two days under EOT 16, there is insufficient evidence as to the specific date of the delay and the nature of the delay and its consequences. Essentially, the approach of the plaintiff in this regard was to make a broad-based claim with insufficient specificity. I cannot be satisfied on the evidence before me, with respect to EOT 16, as to the period of delay and the actual consequences of the delay. In any event, the installation of the Alucobond was always part of the contract.

# I conclude that no allowance should be made under EOT 16.

EOT 17

# EOT 17 was concerned with industrial action, three hours; and inclement weather covering two separate periods, one involving a claim for 49 hours and the other for 20 days respectively. I cannot be satisfied on the evidence before me as to the actual consequential impact of inclement weather on the works or industrial delay upon the project, nor given the scarcity of evidence am I able to substantiate the effect such claims may have had on the date for practical completion.

# It follows that I do not consider any allowance should be made under EOT 17.

EOT 18

# For EOT 18, the plaintiff claimed a consequential extension of 10 days. According to Kane, the calendar showed that it was to undertake works between 18 September and 2 October 2000. However, on 18 September 2000, the plaintiff issued a notice to suspend the works under cl.44.9 of the contract. It alleged in the letter that the contractor had given notice in writing dated 8 September 2000, pursuant to cl.44.7 of the contract, requiring the principals to show cause as to why the contractor should not exercise their right under cl.44.9 of the contract to suspend works. On 2 October 2000, the principals took the work out of Kane's hands. In light of my findings with respect to termination and the circumstances surrounding the show cause notices exchanged between the principal and the defendants, I consider that the plaintiff is entitled to the 10 days claimed. In any event, I consider that, in the circumstances whereby the defendants took control of the works on 2 October 2000, it is fair and reasonable to allow the 10 days claimed by the plaintiff.

# I conclude that 10 days should be allowed under EOT 18.

# I conclude, therefore, that the plaintiff should be allowed a total extension of time of 56 days and four hours.

TERMINATION

# Termination was a pivotal issue in the case for each side, albeit based on different factors. I deal first with the termination case of the plaintiff. In essence, it was the case of the plaintiff that termination came about by virtue of the owner’s failure to pay progress certificates numbered 14 and 15 leading, after service of the plaintiff’s show cause notice, to the cashing in by the owner of the bank guarantees provided by the builder, without notice to the builder. It was the plaintiff’s case that termination was brought about by the actions of the owner.

# I turn then to the facts alleged by the plaintiff as relied upon to support its claim for termination.

The Progress Claims

# Between 2 July 1999 and 28 September 2000, the builder submitted a series of progress claims to the superintendent, Jeffery. Progress claim no. 1 was prepared for the builder by an employee of the builder, Short. He did not give evidence and there was no issue about that certificate, it not being in question. Progress claims nos. 2 – 15 were prepared by Le Hy Ta. There was a later progress claim, no. 16, that was prepared by Tivendale. All progress claims were submitted to the superintendent, Jeffery. In most instances, and importantly with respect to progress claims 14 and 15, Jeffery was the supervisor at the relevant time. The evidence of Le Hy Ta and Jeffery revealed a timeline for the submission of progress claims by the builder and the issue of payment certificates by the superintendent, Jeffery. There were some minor discrepancies as to some of the dates but they were of no consequence.

# The evidence of both witnesses disclosed a pattern to the claim and certification process. First, the builder would submit a progress claim and shortly afterwards a site inspection would be conducted. Generally, Jeffery would make a request for further information as to the amount claimed. These were known as the “RFIs” of which there were hundreds.

# A pattern developed with the progress claims whereby they were received late, meetings would be convened on-site, further details would be requested and the particular progress certificate would be issued by the superintendent thereafter. It was the plaintiff’s case that this arrangement was permitted by the owner, in particular, by the superintendent, Jeffery, in his capacity as the agent of the owner. As a result, it was argued, the conduct of the owner in permitting the progress certificates to be managed in that way constituted an estoppel or a waiver or acquiescence of Kane’s entitlement under cl.42.1 of the contract.

# The defendants described the arrangement as the “varied assessment procedure”. The plaintiff denied any such variation, estoppel, waiver or acquiescence, rather it relied solely on cl.42.1.

# Clause 42.1 dealt with progress claims, payment certificates, calculations and time for payment. It specifically required the builder (described in the Terms as “the Contractor”) to deliver claims for payment to the superintendent within the prescribed times (namely, at the times described in the Annexure - the 28th day of each month - and within the time described in cl.42.7 as “[w]ithin 28 days after the expiration of the Defects Liability Period, or where there is more than one, the last to expire”) supported by “evidence of the amount due” and “such information as the Superintendent may reasonably require”. There was then a mandatory requirement imposed on the superintendent to issue to the owners (as “Principal”) and the builder a payment certificate stating the amount of the payment that, in the opinion of the superintendent, was to be paid by the owner to the builder, or by the builder to the owner, as the case may be. Clause 42.1 further provided that within 28 days of receipt by the superintendent of a payment claim, or within 14 days of issue by the superintendent of a payment certificate (whichever was the earlier), the owner was to pay the builder, or the builder was to pay the owner as the case may be, an amount not less than the amount shown in the certificate as due.

# Despite cl.42.1, it remained open to the owner or builder to dispute the amount, notwithstanding payment, pursuant to cl.47 of the contract. Jeffery said that he and Le Hy Ta agreed to implement a “varied assessment procedure” whereby each month the builder was to submit its payment claim to the superintendent who would then arrange an on-site meeting for the purposes of assessing the work claimed. If the superintendent required any additional information to assess the claim, it would lodge a request with the builder. Upon receipt of the requested information, so Jeffery claimed, the superintendent would notify the builder of the outcome, that is, the amount certified, and issue a recommendation for payment.

# Relevantly, cl.48 of the contract provided that the terms of the contract could not be “varied, waived, discharged, or released, except with the prior consent from the Principal in each instance.”

# Against this contractual context, the builder submitted two progress claims, nos. 14 and 15, which came to be problematic.

Progress Claim No. 14

# Progress claim 14 was submitted by the builder on 1 August 2000 in relation to the works up to 31 July 2000. The claim was for the amount of $1,216,546.64, and included a claim for variations in the amount of $871,504.86. A week later, on 8 August 2000, a site meeting was convened between Jeffery and Le Hy Ta. Jeffery requested further information from Le Hy Ta with respect to the calculation of the amounts claimed for hydraulics, Alucobond and resilient finishes. A fortnight later, on 21 August 2000, Jeffery requested further information from Ta concerning the tiling finishes. That information was provided by the builder on the same day.

# On 23 August 2000, Jeffery, as superintendent, issued payment certificate 14 (apparently in response to progress claim 14) for the amount of $340,562. This certified amount excluded from progress claim 14 virtually all of the variations claimed by the builder. On 24 August 2000, the builder sent a tax invoice to the owner for the full amount certified by the superintendent on progress certificate 14 plus GST in the sum of $34,056.20, for a total invoiced amount of $374,618.20. At the time of providing progress certificate 14, the superintendent certified that the works were 86 per cent complete. On 28 August 2000, the owner paid a lesser amount on the progress certificate, namely the sum of $132,618.20. This was calculated by the owner by taking the certified amount of $340,562, and deducting liquidated damages of $220,000, leaving a balance of $120,562. The owner then added $12,056.20 GST to reach the total amount of $132,618.20.

# On 1 September 2000, Kane submitted progress claim 15 for $1,231,742. On 6 September 2000, a site inspection was held by Jeffery and Le Hy Ta in accordance with the usual arrangements between the parties. The usual pattern was that Jeffery would request more information which was subsequently provided. Additional information was requested on 13 September 2000 regarding the Alucobond in relation to progress claim 15. The requested information was provided on 13 September 2000. Delivery dockets were also requested; these were also supplied.

# Meanwhile, on 8 September 2000, the plaintiff issued a notice to show cause under cl.44.7 (see Appendix L, cl.44.7: “Default of the Principal”). The notice alleged that the principals had committed a “substantial breach of contract” in that they failed to make payment to the contractor for the sum of $1,216,546.64 claimed in progress claim 14, instead making payment of only $132,618.20. The plaintiff notified the principals that they were required to show cause in writing as to why they, Kane, should not exercise their right under cl.44.9 of the contract. Clause 44.9 of the contract referred to the right of the contractor to suspend the “whole or any part of the work” under the contract by giving notice in writing to the defendants. The clause further stated that:

# “if within 28 days after the date of suspension under Clause 44.9, the Principal[s] fails to remedy the breach or, if the breach is not capable of remedy, fails to make other arrangements to the reasonable satisfaction of the Contractor, the Contractor may by notice in writing to the Principal[s] terminate the Contract”.

# Three days later, on 11 September 2000, the defendants sent a letter to the plaintiff. The letter was sent to Kane Constructions from Stacks Properties and signed by Stacks’ representative, Cole Sopov. It referred to Kane’s show cause notice of 8 September 2000 and essentially stated the following:

- Denial that the principals had committed a breach of pursuant to cl.42.1 of the contract, as alleged by the builder;

- That the payment of $132,618 for progress claim 14 was the correct sum to have paid for work completed up to 30 July 2000. Stacks confirmed that this amount was inclusive of liquidated damages that was deducted at a rate of $1,100 per day for failure to achieve practical completion by 13 January 2000;

- That Stacks Properties on 25 August 2000 had called Kane’s contract administrator, Le Hy Ta, to advise that under cl.43 of the contract, the builder must supply a statutory statement stating the all payments due to employees, sub-contractors etc. had been made before progress certificates could be issued.

# On the same day, 11 September 2000, the plaintiff gave the defendants a builder’s declaration of payment with respect to progress claim 15. On 13 September 2000, the plaintiff responded to the defendants’ show cause letter saying:

- “We maintain our allegation that the principals have committed a breach of contract.

- “The superintendent failed to issue a payment certificate in response to this company’s claim dated 1 August 2000 [progress claim 14] within 14 days of the claim…

- “… the obligation of the principals [to pay within 28 days] became… an obligation to pay the full amount of the progress claim on 29 August 2000...

- “The principals failed to make payment of progress claim no. 14.

- “The principals are not entitled to deduct liquidated damages from the amount otherwise payable to this company under clause 42.1.

- “Kane Constructions Pty Ltd maintains the position set out in its notice of 8 September 2000”.

# The letter furthermore stated that the provision of any statutory declaration was irrelevant to the principals’ alleged breach; as was the observation made by Stacks Properties in its notice dated 11 September 2000 that the matter was the subject of proceedings at the Victorian Civil and Administrative Tribunal (“VCAT”).

# Next, on 18 September 2000, the plaintiff issued a notice of suspension of work under cl.44.9. It alleged in the letter that the contractor had given notice in writing dated 8 September 2000 pursuant to cl.44.7 of the contract requiring the principals to show cause as to why the contractor should not exercise their right under cl.44.9 of the contract to suspend works. The letter stated that the principals had failed to show any such cause.

# On 21 September 2000, the defendants issued a show cause notice under cl.44.4 as to why the principals should not take the whole or the part of the works remaining to be completed under the contract out of the hands of the contractor, or to terminate the contract. On 28 September 2000, the plaintiff wrote to the defendants denying that the principals’ notice to show cause had “any validity or effect” as a notice under cl.44.2 of the contract. In that letter, the builder informed the principals that it had acted within its contractual rights and that they would lift the suspension to the works once the principals acted to “remedy their breach”.

# The plaintiff also submitted progress claim 16 for $1,104,818. On 29 September 2000, the plaintiff removed its plant, equipment and materials from the site. By that time, relations between the plaintiff and the defendants were difficult, to say the least. On 2 October 2000, the former solicitor then retained by the defendants wrote to the plaintiff purporting to issue a notice under cl.44.4, advising that the remaining works had been taken out of the plaintiff’s hands. On 5 October 2000, solicitors for the plaintiff, Deacons, wrote to the defendants’ solicitor, Brendan Archer, stating that the contract would be terminated at noon the next day (6 October 2000) unless the notice received by Kane on 2 October 2000 was withdrawn.  The principals acknowledged in writing Kane’s entitlement to an extension of time in respect of the period 18 September 2000 to 6 October 2000; and the principals remedied their “default” by paying Kane the “balance owing” with respect to progress claim 14 dated 1 August 2000.

# On 6 October 2000, revised payment certificates 14 and 15 were issued for the amounts of $120,562 and $187,000 respectively. Meanwhile, on the same day, 6 October 2000, the defendants cashed the builder’s guarantees, two cheques made payable to Stacks Properties Pty Ltd for $86,850 each (for a total of $173,700). No notice was given of the execution of such action. Again, on 6 October 2000, the solicitors for the plaintiff wrote to the former solicitor for the defendants and asserted repudiation and acceptance thereof, purporting to terminate the contract. The letter alleged that:

# “… earlier today your clients, in clear breach of the contract, had recourse to the securities provided by our client pursuant to the contract. That conduct further evidences your clients’ intention not to be further bound by the contract.

# Your clients’ conduct, in all the circumstances, is repudiatory. Our client has instructed us to accept that repudiation on its behalf which we hereby do.”

# The last step was the issue of provisional payment certificate 16 for $197,951 on 11 October 2000.

# As already described, the defendants re-occupied the site and completed the project and later sold many of the units. At the time of the trial there were sections of the site that remained incomplete or unsold. The plaintiff submitted against this background that the defendants repudiated the contract and that they were entitled to accept such repudiation and terminate as it did. The plaintiff relied upon the historical conduct of the parties over the course of the contract in relation to the submission and treatment of the progress claims and the payment certificates. Kane rejected the allegation that there was a variation of the assessment procedure for the treatment of progress claims (as claimed by the principals) or that, in the event that there had been a different assessment procedure, that it constituted an estoppel or waiver or acquiescence to the contractual entitlement of the plaintiff.

# There was no evidence of a variation of the contract. Le Hy Ta gave evidence to the effect that he did not have discussions with Jeffery about the dates for the submission of progress claims or about the dates that the payment certificates were required under cl.42.1. Jeffery said he did not specifically discuss an amendment to the contractual regime with Le Hy Ta. At most, their arrangement seems to have developed through the course of the contract, with the parties more or less adopting the following practice: Firstly, a progress claim would be submitted; second, a site meeting would then be convened to consider the progress certificate; third, any additional information requested would be provided; and fourth, a payment certificate would be made by the superintendent after the submission of a progress claim by the principals.

# Furthermore, cl.48 of the contract specifically excluded any variation to the contract except with the “consent of the principal in each instance” (my emphasis). As well, cl.42.1 provided for the builder to be paid the amount due under a payment certificate, or, in the event that a payment certificate was not issued, for the builder to be paid within 28 days the amount on the progress certificate. Here, the course was that the defendants paid the plaintiff within 14 days of the issue of the payment certificate and, until payment certificate 14, paid the whole of the sum certified. The course of events after the submission of progress certificate 14 was important. Following its submission on 1 August 2000, a site meeting was convened on 8 August 2000 and further information was requested and provided. All of this was consistent with the practice and arrangements throughout the life of the contract up to that point in time. During the assessment process, nothing was said by the defendants (or the superintendent, Jeffery) about non-compliance of progress claim 14 with cl.42.1 of the contract.

# The defendants asserted that progress claim 14 was invalid. They argued that they had no obligation to pay under either progress claim 14 or payment certificate 14 (beyond the amount therein stated). They relied on several points in particular. Firstly, it was said that progress claim 14 was not lodged by the due date under the contract, and that in any case, there was a lack of sufficient supportive evidence. Second, it was said that the payment obligations under the contract were varied by the parties upon the introduction of the goods and services tax (“GST”). The third point raised was that progress claim 14 was assessed under an existing procedure that had been agreed between the parties and that an estoppel arose against the plaintiff asserting any contractual rights under progress claim 14. The defendants also relied upon the provisions of the Domestic Buildings Contracts Act to support their submission that progress claim 14 was invalid. I intend to deal with that submission in a later part of the judgment.

# There is longstanding authority to the effect that a principal under a building contract is bound to pay upon the terms of a properly issued certificate, even where a certificate may subsequently be found at the end of the day to incorrectly represent the amounts ultimately owing between the respective parties. Consequently, while progress claims and payment certificates might properly be regarded as provisional in nature, in construing cl.42.1, courts have long regarded strict compliance as to the payment of progress certificates as fundamental to the interests of legal stability in construction contracts.

# The defendants asserted that the plaintiff did not acquire or enjoy any contractual rights arising from progress claim 14 and that it was wrong for the plaintiff to rely upon it as a trigger for the show cause notice. I intend to deal with this issue before turning to the issue of the deduction of liquidated damages as a trigger for the show cause notice.

# Strictly speaking, the plaintiff was in fact at least four days late in the submission of the claim since the due date for claims was the 28th day of each month (as indicated in the contract Annexure). Progress claim 14 fell due on 28 July 2000 but was dated 1 August 2000. The question to be decided on this particular point therefore is whether the late submission of the claim meant that the claim was of no effect or invalid; in turn leading to the defendants’ submission that the plaintiff failed to comply with cl.42.1 and provide sufficient or proper evidence in support of the claim.

# Clause 42.1 stipulates that where a claim is not lodged, the superintendent may nevertheless issue a payment certificate. However, the contract does not clearly state what happens in the event of a premature or late claim being made.

# In Brewarrina Shire Council v Beckhaus Civil Pty Ltd, the council (the appellant) argued that the contractor, Beckhaus, had been several weeks premature in submitting the relevant claim, progress claim no. 7, as the contract stated that progress claims could only be made “monthly”, and the claim had not been so made. On the other hand, Beckhaus claimed that, provided that one claim was made in each month, then it met the definition of the requirement for “monthly” claims to be made. Young CJ in Eq dissenting, favoured the contractor’s interpretation, observing that the High Court in “another connection took the same view” in Federated Seaman’s Union of Australasia v Commonwealth Steamship Owners’ Association.

# Ipp JA, however, rejected Beckhaus’ interpretation, favouring instead the view put forward by the council, namely, that the word “monthly” suggested to him that the claims should have been made at intervals of one month each, as opposed to one claim made in each month. His Honour was, however, unable to uphold the council’s appeal in this respect owing to the lack of evidence as to the date on which on-site work commenced. It was therefore not possible to determine the date in each month when the claims should have been made.

# Ipp JA’s approach may be viewed as stricter than that of Young CJ in Eq, in the sense that it indicates that where claims are not made on more or less the exact date stated or alluded to in the contract, they will be held to be ineffective. Applying Ipp JA’s approach then, it would seem that progress claim 14 may be held to be ineffective owing to the fact that it was at least four days late.

# However, notwithstanding the generally favourable treatment of Brewarrina by the Victorian Court of Appeal in Aquatec-Maxcon Pty Ltd v Minson Nacap Pty Ltd, I am reluctant to accept the apparent interpretation of Ipp JA regarding the timing issue of progress claims, as it stands alone. With regard to this particular point, Brewarrina primarily focussed on the interpretation of the word “monthly” rather than on the actual invalidity as a result of early or late submission of the relevant claim. Strictly speaking, it is unclear whether the NSW Court of Appeal stands for the principle that claims not submitted on the exact date are invalid.

# Other case law would appear to support the contractor’s view that claims are valid provided they are submitted around the date they are due each month. For example, such a view appears to have gained implicit acceptance in Daysea Pty Ltd v Watpac Pty Ltd. As in the case before this Court, the special conditions in Daysea provided that, for purposes of cl.42.1, the “times for payment” were the “28th day of each month”. On 4 November 1999, the appellant, Daysea, lodged progress claim no. 16 for $560,188. For the purposes of cl.42.1, it was “deemed” to be delivered some weeks later on 28 November. On 22 February 2000, the appellant again lodged an apparently early progress claim, this time no. 18 in the sum of $617,528. That claim appeared to have repeated what was claimed in claim no. 17 (which was declared “redundant” by the principals’ representative because it was lodged before claim no. 16 had been finalised), detailed matters which had been claimed but not allowed in earlier claims and certificates, and claimed work carried out with respect to variations. It was conceded that for purposes of cl.42.1 that claim was (once again) “deemed” to have been lodged on 28 February 2000.

# Daysea is in harmony with a long line of authorities suggesting that it is not important for the contractor to submit the claims on time, provided they are submitted around the time they are due. What has been made clear in these cases is that it is necessary for the contractor to receive prompt payment of claims so that it is able to fulfil its obligations to progress the works and pay its sub-contractors. Thus late submission of claims seems to some extent to be acceptable; while late certification is less so, except where the issue of a condition precedent in cl.42.1 arises (for example the need for further evidence and information)..

# The defendants may not therefore claim that progress claim 14 was invalid or of “no effect” because it was submitted late.

# Nevertheless, it would appear that according to current authority, where a valid claim is received, the superintendent is entitled to suspend the issuance of the certificate where the superintendent requires further evidence and information to issue a certificate. The defendants contended that payment certificate 14 was issued late for just such reasons, that is, the superintendent’s requirement for additional information from the builder in support of the claim.

# The defendants rely upon the decision in Brewarrina (Shire Council v Beckhaus Civil Pty Ltd) to support their proposition in this regard. Brewarrina was accepted by the Victorian Court of Appeal in Aquatec-Maxcon Pty Ltd v Minson-Nacap Pty Ltd. Although the circumstances in Aquatec were different to this case and further, that the Court of Appeal did not consider directly the application of Brewarrina to the circumstances such as arise in the present case, it seems that I am bound by the adoption of Brewarrina in Aquatec, or at the very least, ought regard Brewarrina as highly persuasive and relevant authority to the present case, despite the prior and longstanding authorities which state that a late certificate will be treated as invalid, resulting in payment of the whole amount claimed.

# Aquatec was an appeal from a decision of Byrne J granting summary judgment to Minson-Nacap for the amount of its unsettled claims. In 1997, Aquatec, the main contractor and appellant, engaged Minson-Nacap, the sub-contractor, to design and construct works for a water treatment plant in Lorne and Apollo Bay. However, the appellant later alleged defective works by the respondent and refused to pay a number of certified claims. Several claims subsequently made by the respondent were not certified at all. The respondent therefore applied for summary judgment of the outstanding amounts claimed.

# There were three main issues on appeal. Firstly, the appellant denied the existence of a sub-contract between the appellant and the respondent. The court rejected this argument, contained in appeal grounds 1 to 4, observing that Aquatec had unconditionally agreed in earlier pleadings that a sub-contract existed. It was therefore not open to them to now argue that a sub-contract did not exist. Second, the appellant contended that the trial judge erred in construing cl.42.1 of AS 4303-1995, the sub-contract (grounds 5 and 6). Third, Aquatec argued that the trial judge had erred in construing cll.44.4 and 44.10 of AS 4303 1995 (ground 7). It is the second ground of appeal in particular which is relevant to the present case given the plaintiff’s argument that progress certificate 14 was invalid because it was late and the principals’ defence that the claim lacked evidence and information in support at the time it was submitted.

# The Victorian Court of Appeal in Aquatec concurred with the majority decision of the NSW Court of Appeal in Brewarrina in construing cl.42.1 of AS 4303 1995 as meaning that the provision of sufficient information or evidence to support a payment claim was a condition precedent to the issue of the payment certificate by the superintendent. For the purposes of the present case, it is sufficient that cl.42.1 of AS 4303 1995 is, so far as it is relevant, the same as in AS 2124 1992, the contract used in this case. In reaching their determination, the Court in Aquatec observed that at that time, so far as their Honours were aware, Brewarrina was the “only decision which currently exists on this particular point of construction of this paragraph of the clause”. The Court cited Ipp JA (with whom Mason P agreed) observing that there was “an important contractual and practical purpose for the requirement that the contractor provide evidence of the amount due and information reasonably required” by the superintendent. The Court found that the matters raised a triable issue as to whether the superintendent was in fact obliged to issue certificates in respect of the relevant progress claims and whether Aquatec was required to pay those claims within the time specified in cl.42.1. The appeal was therefore allowed on these grounds.

# With respect to progress claim 14 in this case, the superintendent was one week late in certifying the claim (according to cl.42.1, on a strict interpretation it should have been certified 14 days after the claim was submitted on 1 August 2000; in fact, it was submitted on 23 August 2000). Prior to Brewarrina, established law stated that the consequence of late certification was that the principals were obliged to pay the full amount of a contractor’s claim 28 days from the submission of the claim, i.e. that a late certificate is simply ineffective. This was the view of Byrne J in Zauner Construction Pty Ltd v No 2 Pitt Street Pty Ltd and the Queensland Court of Appeal in Daysea Pty Ltd v Watpac Pty Ltd.

# However, given the apparent change in the law since Brewarrina and Aquatec, the contention of the defendants that certification of a claim in cl.42.1 is subject to the condition precedent that sufficient evidence and information be provided to the superintendent to assess the claim must hold.

# It follows that payment certificate 14 was as a result not invalid and not in breach of cl.42.1 as the builder claimed. This was not, therefore, of itself a valid ground to act as a trigger for Kane’s show cause notice issued on 8 September 2000.

Deduction of Liquidated Damages

# Nevertheless, even if the certificate was a valid one under the contract as explained, the principals still had an obligation under cl.42.1 to pay the amount certified by Jeffery for certificate no. 14.  Clause 42.1 clearly states:

# “Subject to the provisions of the Contract, within 28 days after receipt by the Superintendent of a claim for payment or within 14 days of issue by the Superintendent of the Superintendent's payment certificate, whichever is the earlier, the Principal shall pay to the Contractor or the Contractor shall pay to the Principal, as the case may be, an amount not less than the amount shown in the Certificate as due to the Contractor or to the Principal as the case may be…”. (My emphasis).

# Thus, the defendants had a clear obligation to pay within 28 days of the superintendent’s receipt of the claim for payment, submitted on 1 August 2000; therefore, payment clearly fell due on 29 August 2000 for an amount not less than the amount certified in the certificate, namely, $340,562.

# Nevertheless, on 28 August 2000, the defendants paid an amount less than that stated in the certificate. It is apparent that Sopov took it upon himself to deduct liquidated damages in the amount of $220,000 from this figure, paying only $132,618 including GST. It was only on 6 October 2000, some eight days later, that Jeffery issued a “revised” certificate for the amount paid.

# In their pleading, the defendants alleged that the superintendent had amended the payment certificates in accordance with cl.42.2 of the contract with respect to payment certificates 14 and 15 to take into account liquidated damages payable by the plaintiff to the defendants. However, cl.42.2 relates to correction of any errors discovered by the superintendent in previous certificates. It is possible that the defendants realised the mistake made, as during the course of the trial the defendants purported to withdraw revised payment certificates 14 and 15 and abandon reliance upon them.

# Even so, the deduction of liquidated damages by the defendants on 28 August 2000 was unauthorised and constituted a fundamental breach of the contract. Clause 42.1 of the contract provides that failure to make a payment under the contract (in breach of cl.42.1) constitutes a “substantial breach of contract” as provided in cl.44.7(a). I therefore find that the defendants were in substantial breach by not paying all of payment certificate 14. I find that there was a substantial breach by way of the deduction of the sum of $220,000 on 28 August 2000. The authorities clearly state that it was not open to the defendants to deduct liquidated damages without an appropriate certificate and the recently decided Court of Appeal judgments in Brewarrina and Aquatec do not diminish that fact.

# It follows that the unauthorised deduction of liquidated damages from progress certificate 14 constituted a breach of cl.42.1 of the contract. Kane was correct to point out in its show cause notice dated 8 September 2000 that it was a valid ground for triggering termination of the contract, as Kane finally did on 6 October 2000.

# There were other, scattered complaints by the defendants with respect to the contents of the plaintiff’s show cause notice: lack of date, wrongful amount claimed and lack of allowance for liquidated damages. There were also additional complaints of alleged agreement by the plaintiff to the amount specified in payment certificate 14, non-compliance with GST obligations and non-compliance with the Domestic Building Contracts Act.  The remaining matter is the issue of the treatment by the plaintiff of GST.  I do not consider it to be relevant.  Rather it was a matter of the contractual obligation under the contract and obligations flowed there from. In any event, the parties acted in a constant manner with respect to the progress certificates. I am not satisfied that the acts surrounding GST obligations were sufficient to amount to a variation of the contract.   I do not accept that any of these complaints were made out. In relation to the Domestic Building Contracts Act issue and its application, I intend to deal with that subject at a later point.

Estoppel

# I turn now to the matter of the alleged estoppel. There was no issue between the parties as to the procedure for assessment and the way it in fact occurred in each instance. The dispute centred around the consequences for the assessment procedures of payment certificates 14 and 15. It was asserted that, arising from the historical conduct between the parties, they conducted themselves on the assumption that a particular practice for assessment applied, and that it would be unconscionable for the plaintiff to depart from that assumption.

# I do not consider an  that estoppel arose in the circumstances. The elements of estoppel are not present in this case. I find that there was no evidence of an assumption made by either party relating to the adoption of a certain practice for assessment; nor was there any inducement made by the plaintiff or an entering into contractual relations on the basis of the asserted assumption; or the exercise of rights based on the asserted assumption; and nor was there knowledge that the plaintiff (or its agents) knew that the defendants (or their agents) laboured under the alleged assumptions. On no basis do I consider an estoppel arises in this instance.

Progress Claim 15

# I now turn to consider the matter of progress claim 15.

# The plaintiff’s show cause notice alleged that the defendants had committed a “substantial” breach of cl.42.1 by failing to pay the amount specified under progress claim 14, paying a lesser sum in response to the amount certified in the payment certificate. That certificate was valid pursuant to cl.42.1 and, as already discussed, did not constitute a valid ground for the show cause notice issued by the plaintiff, since the defendants were not in breach of their obligations under the contract. Kane had already put formal steps in place with regard to its show cause notice under cl.44.4, primarily because of non-payment of payment certificate 14, by the time payment certificate 15 was issued in mid-September 2000.

# For payment claim 15, the plaintiff sought $1,231,742.00 – that figure apparently included the amount of $220,000.00 deducted by the defendants as “liquidated damages” that remained outstanding according to the plaintiff under payment certificate 14. Payment certificate 15 was issued by the superintendent on 14 September 2000 for $220,800.00. On 6 October 2000, Jeffery issued “revised” payment certificates 14 and 15. “Revised” payment certificate 15 was for $187,000 following the deduction of liquidated damages. The plaintiff argued that the defendants were indebted to Kane for the amount originally certified by the superintendent, namely, a sum of $220,800.00 According to Kane Constructions, that amount is owed to them and remains outstanding.

# The defendants maintained their right not to pay both certificates 14 and 15, at least partly because “the amount claimed by the Plaintiff in Progress Claim No. 15 included the amount claimed in Progress Claim No. 14”. The defendants alleged that if they were obliged to pay the full amount of progress claim 14, or the full amount of the original amount certified for certificate no. 14, then payment certificate 15 “superseded any obligation… of the Defendants to pay the amounts referred to in Progress Claim No. 14”. I do not accept that proposition. Apart from the inclusion of liquidated damages deducted under progress certificate 14, progress claim 15 encompassed works separate to that documented under the previous claim. Whilst progress claim 15 incorporated Kane’s claim for $220,000.00, which the builder maintained was “wrongfully” deducted as liquidated damages from progress certificate 14, that in itself is insufficient to permit the principals from withholding payment. The fact that the superintendent approved separate amounts under both the claims, $220,800.00 originally for payment certificate 15 and on another occasion, $340,562 for payment certificate 14, provided further evidence in support of the view that the claims and certificates covered different periods and therefore different costs. In any case, Le Hy Ta prepared both progress claims 14 and 15. He gave evidence, which I accept, that each claim was prepared on the basis of quantity of contract works completed, materials supplied and/or installed, and labour provided (including in respect of variation works undertaken) at the time of the relevant claim. Progress claim 14, submitted on 1 August 2000, therefore covered the quantity of works, materials and labour costs for the preceding four week period. Likewise, progress claim 15 was submitted on 1 September 2000 and covered costs for the four weeks preceding that particular period.

# Moreover, the defendants had a clear contractual obligation to pay $220,800 endorsed by the superintendent for certificate no. 15 within the specified period. Relevantly, cl.42.1 of the contract states that the defendants should pay within 28 days after receipt by the superintendent by a claim or within 14 days of issue by the superintendent of the superintendent’s payment certificate, whichever is earlier. Progress claim 15 was received on or about 1 September 2000; thus, if the defendants were obliged to pay within 28 days after receipt, then payment was due around 29 September of that year. The superintendent issued payment certificate 15 on 14 September 2000; if payment was due within 14 days, then payment was due by 28 September 2000. The earlier of these two dates would appear to be the latter, that is, “within 14 days of issue by the Superintendent of the Superintendent's payment certificate”, or by 28 September 2000. The defendants did not claim that progress claim 15 was suspended owing to further evidence and information required by the superintendent as with progress claim 14. It is therefore assumed that payment was due by this date. Nevertheless, payment certificate 15 was not paid at that time and remains outstanding.

# The first certificate issued for $220,800.00 was valid and there was a contractual obligation on the part of the defendants to pay the amount certified by the superintendent.

# Before leaving the matter of repudiation, for completeness, it is appropriate to ask: Was the calling up of the builder’s guarantee by Sopov a “substantial breach” of the contract on the part of the defendants, amounting to repudiation?

# The plaintiff claimed that by breaching cl.5.5 of the contract, the defendants had committed a “substantial breach” under the contract.  “Substantial breach” by the principal was defined in cl.44.7 as including, but not limited to:

# failing to make a payment, in breach of Clause 42.1;

# failure by the Superintendent to either issue a Certificate of Practical Completion or give the Contractor, in writing, the reasons for not issuing the Certificate within 14 days of receipt of a request by the Contractor to issue the Certificate, in breach of to Clause 42.5;

# failing to produce evidence of insurance, in breach of Clause 21.1;

# failing to give the Contractor possession of sufficient of the Site, in breach of Clause 27.1, but only if the failure continues for longer than the period stated in the Annexure; and/or

# failing to lodge security in breach of Clause 5.

# The words “include but not limited to” indicate that the list contained in cl.5.5 was not, however, intended to be exclusive.  The question raised here is whether the cashing of the builder’s guarantee by Sopov constituted a “substantial breach” also leading to repudiation of the contract?

# There are three express requirements contained in cl.5.5 with respect to the recourse to retention monies and conversion of the security.  The plaintiff contended that the defendants did not in the first place demonstrate an entitlement under cl.5.5(a) to exercise a right under the contract with respect to the security. Even if they were able to demonstrate such an entitlement, the plaintiff claimed the defendants breached cl.5.5(b) of the contract by failing to give the required five days notice of their intention to have recourse to the security. The plaintiff further argued that the defendants were in breach of cl.5.5(c) of the contract for their failure to allow another five day period to elapse after the required notice and prior to the conversion of the security, consisting of two bank guarantees.

# The defendants were clearly in breach of all three requirements contained in cl.5.5.  As stated above [in para. 768], the facts bear out that conclusion. Nevertheless, the question to be determined here is whether the defendants were in “substantial breach”, amounting to repudiation.  That question is important to this case given the fact that whilst every contractual breach may entitle the aggrieved party to damages, not every contractual breach will have the effect of terminating the contract.

# According to Lord Wright in Smyth (Ross T) & Co. Ltd v. T.D. Bailey, Son & Co., “repudiation of a contract is a serious matter not to be lightly found or inferred”.  His Lordship cited the following passage from Mersey & Iron Co. v. Naylor, Benzon & Co. with approval, saying that one must have regard to:

“ ‘... actual circumstances of the case in order to see whether the one party to the contract is relieved from its future performance by the conduct of the other; you must examine what that conduct is, so as to see whether it amounts to a renunciation, to an absolute refusal to perform the contract, such as would amount to a rescission if he had the power to rescind, and whether the other may accept is as a reason for not performing his part…’ ”.

# Gibbs C.J. in Shevill & Anor v The Builders Licensing Board likewise observed that a contract may be repudiated where one party renounces their liabilities under it, evincing an intention to no longer be bound by the contract.  His Honour further observed that repudiation may also occur where one party demonstrates an intention to fulfil the contract, but in a manner “substantially inconsistent with his [or her] obligations and not in any other way … ”.  The conduct of the allegedly repudiatory party must be “such as to convey to a reasonable person, in the situation of the other party, repudiation or disavowal either of the contract as a whole or of a fundamental obligation under it.”  It is to be remembered that not all breaches may free the other party from his or her obligations under the contract, particularly where a breach may be compensated in damages.

# Having said that, it is also not necessary that there should be an express statement for repudiation to be found.  As with the majority of cases in this area of contract law, this case is concerned with the question of whether the principals’ conduct in this regard can be considered as repudiatory in nature.

# Nevertheless, with respect to repudiation, the authorities do not clearly state the proper course of action to be taken in circumstances where one party acts on or claims an inappropriate interpretation or construction of the contract.  A party eschewing their obligations under the contract (or who will not accept performance from another party) except according to an erroneous interpretation of those obligations, may be found to have repudiated the contract.  Likewise, a party attempting to terminate a contract where no such right exists may have repudiated the contract.  However, it seems less likely that repudiation will be found in these circumstances.   As Pearson L.J. observed in Sweet & Maxwell Ltd v. Universal News Services Ltd.:

“In the last resort, if the parties cannot agree, the true construction will have to be determined by the court.  A party should not too readily be found to have refused to perform the agreement by contentious observations in the course of discussions or arguments…”.

# The general approach would seem to be that there are two principles that reduce the possibility that repudiation where a party insists upon a different view of the contract.  First, where termination is justified on the basis by reference to other grounds available at the time for termination, even though those grounds were not known at the time of the proposed repudiation to the aggrieved party.  Secondly, where the repudiatory party acts in accordance with a bona fide belief as to the correctness of the interpretation which it sought to place upon the contract.  In DTR Nominees Pty Ltd v Mona Homes Pty Ltd, the court accepted that where a party asserts and relies on an incorrect interpretation of the contract and does so in all honesty, that conduct will not necessarily amount to a rejection of the contract.

# There were several instances whereby the defendants relied on an incorrect interpretation of the contract in this case.  First of all, the defendants sought to rely on the “unconditional undertaking” comprising the security given by the plaintiff, which according to the defendants provided that: “… it is unconditionally agreed that the Financial Institution will make the payment or payments to the Principal forthwith without reference to the Contractor notwithstanding any notice given by the Contractor not to pay same” [my emphasis].  This was not the correct position to take with respect to the bank guarantees.  The date of the two bank guarantees provided by the National Australia Bank was 16 June 1999.  The final terms of the contract were not agreed to and executed until 20 August 1999.  By the time the final contract was executed governing the overriding rights and obligations of the parties, cl.5.5 was agreed to.  Clause 5.5 by that time specifically stated that if one party was to have recourse to the security, then it was to give five days notice to the other party of their intention to take this course of action.  The contractual rights and obligations of the parties with regard to the security provided by Kane in favour of the defendants are therefore to be found in the contract, and not the undertaking given by the bank.

# As well, with respect to cl.5.5(a), the defendants also erroneously asserted  that it was their right to access the security, constituting two bank guarantees.  This was based on the incorrect assumption that they were entitled to have recourse to the security owing to the “breaches of the plaintiff”, namely, as the defendants contended, the plaintiff’s issuance of the show cause notice as based upon breaches of the agreement and its subsequent illegal suspension of works under the agreement.  Sopov said that he attended his then solicitor’s office on 6 October 2000 and that his solicitor advised him to draw down on the security held by the principals pursuant to the contract.  Sopov said that he signed an authority allowing his solicitor to draw down the security; which his solicitor duly did.  Sopov said that he did not think about any need to give the builder written notice of this action, and that instead, he simply acted according to his legal advice.  This advice, however, was in fact incorrect.

# However, although erroneous interpretation of the contract makes it less likely that repudiation will occur, that is not to say that repudiation will not occur where one has regard to the conduct of the parties and the circumstances of the case as a whole.  In Vaswani v Italian Motors Ltd, the Privy Council held that a party asserting an incorrect interpretation, despite honest intention, will be found to have repudiated the contract where that party has also engaged in conduct detrimental to the aggrieved party or inconsistent with the contract remaining on foot.

# In the present case, it appears clear to me that the defendants evinced an intention not to be bound at an earlier stage than the date the bank guarantees were cashed and moreover, engaged in conduct inconsistent with the contract remaining on foot.  I have already referred to Sopov’s evidence in this regard. Notably, when  pressed under cross-examination, Sopov’s admitted that he wished to take the works out of the builder’s hands on 29 September 2000, though this evidence contradicted some of his other statements.  As well, the “pre-emptive strike” mode in which the defendants cashed the bank guarantees following a history of disagreements between the parties over many contractual issues evidenced the defendants’ intention not to be bound to the contract.  That action also made it highly unlikely that the parties would have a conducive, harmonious working relationship in future.  I accept that the action of the defendants in this respect was also clearly detrimental to the plaintiff.

# In DTR Nominees, the High Court suggested that the aggrieved party (in this case, Kane) should take steps to persuade the mistaken party of his or her error.  Nevertheless, Sopov admitted that the defendants were not presented with the opportunity to persuade the principals to another course of action before the defendants called upon the bank guarantees.  This was because he, Sopov, did not think it was necessary to tell the plaintiff what the defendants were about to do with the bank guarantees.

# Finally, the act of repudiation itself is not sufficient to discharge the contractual obligations of the repudiatory party.   It is necessary that the non-defaulting party accepts the repudiation for the contract to be at an end.  The plaintiff contractor in this case submitted that, by facsimile dated 6 October 2000 from the plaintiff’s solicitors to the defendants’ then solicitor, it accepted the defendants’ repudiation, thereby terminating the agreement.  I agree with that interpretation of events and furthermore, I accept that 6 October 2000 represented the date whereby the contract finally came to an end.

Suspension of Works and Repudiation

# The defendants also alleged that the suspension of works by the plaintiff was invalid, in any event. They asserted four bases of invalidity of the show cause notice: first, for the reasons relevant to progress claims 14 and 15 and cl.42.1, already stated and accepted by me; secondly, for the reasons under the Domestic Building Contracts Act as dealt with later and also rejected; thirdly, for the argument that progress claim 14 was superseded by payment certificate 15 as already described and rejected; and fourthly, that the suspension of the work itself constituted a breach of the agreement.

# Before dealing with the latter, it is appropriate to analyse the sequence of events from the time of the show cause notice and the suspension of works. I have described the response of the defendants to the plaintiff’s show cause notice and the suspension of works. The defendants took over the site. The plaintiff asserted that the defendants took the work out of their hands. The defendants countered the allegation asserting that the conduct of the plaintiff in suspending the works and the state in which the builder left the site evinced an intention to abandon the contract.

# It was submitted for the defendants that the conduct of Kane in suspending the work was a substantial breach and repudiation of the contract. Reliance was placed upon the absence of readiness or willingness on the part of the plaintiff to perform contractual obligations. Of course, whether a repudiation has occurred will be resolved objectively and by inference from the circumstances of the individual case. It was urged for the defendants that at the time that the works were suspended, Kane was in dispute with Sopov and had issued proceedings at VCAT. Thus, it was urged, Kane had already resolved to put an end to the works. That resolution was confirmed by the removal of site sheds, plant and equipment from the site without notice to the defendants. It was argued that by the suspension of the work and refusing to lift the suspension and perform its obligations, Kane manifested an intention not to perform the contract.

# However, cl.5.5(a) of the contract made specific provision that the defendants were able to resort to the bank securities if, and only if, certain contractual pre-conditions were satisfied. The conditions were that a right had been triggered under cl.5.5(a); that five days’ notice in writing had been provided; and that a further five day period had elapsed after the written notice. The defendants were unable to satisfy compliance with any of these conditions at trial. Hence, I find that the defendants breached cl.5.5 of the contract.

# It was urged for the defendants that their recourse to the bank guarantees was in fact pursuant to their rights under the contract and that they, in any event, were entitled to have recourse to the guarantees because of alleged breaches by Kane. I do not accept that assertion. I find that the cashing in of the guarantees constituted a repudiation of the contract and evinced an intention on the part of the defendants not to be bound by the contract. The cashing in of the bank guarantees on 6 October 2000 had all the hallmarks of a pre-emptive strike. The parties were at loggerheads over the extension of time claims and the delays with respect to the completion of the project. The defendants elected to act as they did without resort to their proper entitlements and avenues available under the contract. I find that, by their conduct up to and on 6 October 2000, the defendants placed the plaintiff in a difficult, indeed, impossible position.

# As a consequence, the plaintiff faced the alternative of continuing to perform under a contract when the defendants had shown an intention of non-compliance and breach or, alternatively, to terminate the contract. It was submitted for the plaintiff that, in the plainest terms, the defendants were not paying the plaintiff, had removed the work to be done under the contract, deducted liquidated damages, accessed the guarantees and issued revised certificates. I find that the conduct of the defendants was repudiatory and the plaintiff was entitled to terminate the contract on two grounds: firstly, on the basis that the deduction of liquidated damages was wrongful; and secondly, on the basis that the defendants were not entitled to cash in the bank guarantees provided by the builder as they did on 6 October 2000.

# Both these actions constituted significant breaches of the contract on the part of the defendants and evinced the principals’ intention to no longer be bound to the contract. I do not however accept the claim made by the plaintiff in its show cause notice and at trial that the late issuance of payment certificate 14 constituted a valid trigger for termination. Nevertheless, the plaintiff’s arguments with regard to liquidated damages and the bank guarantees demonstrate that as at 6 October 2000, the plaintiff had ample right to terminate the contract as it did.

# There is an additional matter with respect to the repudiation issue. In the course of his evidence, Sopov said that he had not intended or planned to bring the contract to an end at the earliest possible time after the show cause notice was issued at his direction on 21 September 2000. However, he also said when pressed under cross-examination, that he wanted to take the works out the builder’s hands on 29 September 2000. He said other things that were contradictory also. He said, again when pressed in cross-examination, that as at 2 October 2000 he was not planning to take the work out of the hands of the plaintiff. He also said that he wanted the plaintiff to come back.

# I do not accept the evidence of Sopov in this respect.

# In addition, at an earlier stage in the proceedings, the defendants filed a third party claim against their former solicitor, Brendan Archer, who acted for the defendants during the time of the exchange of correspondence between solicitors with respect to the show cause notices and, ultimately, the cashing in of the guarantee. There was evidence at the trial of discussions between the defendant, Sopov, and his then solicitor with Slattery. Sopov denied that he recalled the meeting with the solicitor.

# In the course of cross–examination his attention was directed to the third party claim filed in the proceedings. He conceded, thereafter, that he had not been truthful with respect to the fact of the meeting that he had with his solicitor, Archer, and Slattery on 2 October 2000. It is apparent that the purpose of the meeting was to discuss the formal contractual steps that would be taken against the builder. Ultimately, I conclude from these matters that at all relevant times Sopov had the formal intention to take the works out of the hands of the builder as soon as he could. In the course of his evidence he accepted that he planned to do so but that his then solicitor, Archer, had advised him to wait.

# I find that the evidence of Sopov in relation the events between 29 September and 6 October 2000 to have been untruthful with respect to the decision he made to access the guarantees and, also, take the work out of the hands of the plaintiff.

# Furthermore, there was evidence that Sopov formed such intention as early as 29 September 2000 by way of a notice dated 29 September 2000, a letter dated 3 October 2000 forwarding bank guarantees to Archer; and the actual letter of Archer as solicitor for the defendants to the National Bank dated 6 October 2000 which included a signed authority bearing a facsimile transmission time of 20:55 on 2 October 2000. The latter indicated receipt of that document by Archer from Sopov on 6 October 2000. All these matters lead me to affirm my previous conclusion that Sopov intended before the show cause notice, and in all likelihood as early as 29 September 2000, to take the works out of the hands of the builder and repudiate the contract. In his evidence, Sopov said that he did not make the decision to access the builders’ guarantees until 5 October 2000. I do not accept that evidence.

# The defendants complained that the plaintiff was not of genuine intention when it removed the equipment from the site. The defendants’ letter of 2 October 2000 asserted that the site sheds and equipment were removed so as to deny the defendants the right to use the equipment under cl.44.4 of the contract. That assertion was specifically denied in the letter of the plaintiff’s solicitors of 5 October 2000. In the course of his evidence, Forster said that the purpose of the plaintiff in removing the site sheds and equipment was twofold, firstly, for security reasons and, second, to prevent the defendants from having access to the equipment.

# The defendants complained in argument that the reliance on security should be rejected because the equipment was secure, it being locked up inside the building. It was also said that the sheds and some of the equipment were so large as to require substantial dismantling and removal by crane and truck. It was urged, further, that Forster falsely raised the security issue because of a desire to “mask” the true fact that Kane was abandoning the works and endeavouring to inflict maximum damage on the defendants by preventing it from being able to complete the works. It was submitted in final addresses that the Court could “infer Kane’s purpose from Mr Forster’s consciousness of guilt.”

# I do not accept that position. I accept the evidence of Forster that the plaintiff was concerned about its plant and equipment and materials that were on-site. Understandably, as from 18 September 2000, the plaintiff did not have staff on-site and I accept the evidence of Forster that he considered that there was a security risk. Furthermore, Forster was advised, and I accept it was the position, that the plant and equipment was capable of being returned and reinstated on the site within a day of the suspension being lifted or the work recommencing on some other basis. I also accept the evidence of Forster that re-establishment time of the equipment and sheds would have been reduced compared to the initial site establishment because only one half of the sheds were required to be returned to the site given the stage that the project had reached.

# I accept, further, the evidence of Forster that his reasons for removal of the equipment was not only for security purposes. Forster said in his evidence that, so far as the plaintiff was concerned, the defendants did not have any right to use the plant and equipment and that there was an anticipation that the defendants might labour under a misconception and purport to use it. Mr Forster said in his evidence that the position of the plaintiff at the time the works were suspended was that it had not been paid following submission of progress claims 14 and 15 and was confronted with a “short” seven day show cause notice (as to why the works should not be taken out of the builder’s hands). I accept the explanation of Forster.

# Ultimately, it was the position of Forster, and thereby the plaintiff, that it was ready and willing to resume the works if the defendants rectified the breaches to the contract. It was put to Forster that the plaintiff was trying to “get out of the contract”. Forster rejected the suggestion. I accept his evidence.

# With respect to the latter, my finding is supported by the letter of the plaintiff to the defendants dated 28 September 2000 wherein the plaintiff stated unequivocally that it remained willing to perform its contractual obligations under the contract. There was, also, a report by Jeffery to the National Australia Bank with respect to financial arrangements wherein he confirmed that the builder was fulfilling its contractual obligations under the contract and intended to do so. In any event, Tivendale gave evidence that the plant and equipment which was removed was capable of reinstatement within a day. He was not cross-examined on that subject. I accept the evidence of Tivendale.

# I conclude, therefore, that the defendants, by their conduct, evinced an intention not to be bound by the contract thereby constituting a repudiation so that the plaintiff was able to terminate the contract.

# It was submitted for the defendants that the circumstances of termination were such that there ought be a finding of mutual abandonment as at 6 October 2000. That is, if the defendants were found to have repudiated the contract by the drawing down of the bank guarantees, the proper analysis of the circumstances at that time was that neither the plaintiff nor the defendants intended to perform the contract in accordance with its terms. In view of my findings, it is unnecessary to consider this submission. Clearly, there was not a mutual abandonment and in light of the findings I have made the issue does not arise.

# Finally, with respect to termination, it was submitted for the defendants that, if the plaintiff was permitted to terminate the contract when it was “not performing any obligations and was not in a position to do so”, it would be manifestly unfair. It was argued that termination of the contract by the plaintiff would deprive the defendants of the benefits conferred by the contract, specifically cll.44.4 – 44.6, and enable the plaintiff to sue for damages or claim quantum meruit even though the conduct of the plaintiff would not entitle it to either. It was further submitted that the plaintiff did not act in good faith in purporting to accept the repudiation by the defendants and terminate the contract because the plaintiff had already resolved not to perform the contract.

# On the basis of my findings, an issue of good faith does not arise. I am satisfied, for the reasons already stated, that the plaintiff intended to proceed with its obligations under the contract once the defendants rectified the breaches that then existed. It follows that I reject the submission for the defendants that relief should be granted against the termination of the contract because it would be unjust and unconscientious to do so. Ultimately, it was the defendants who breached the contract, failed to rectify the breach, and then acted in a way that evinced an intention not to be bound by the contract. In my view the prospect of equitable relief does not arise.

# VARIATIONS

NPVs

# The plaintiff claimed the sum of $438,138 at the outset in respect of variations work performed by it on the project. The variations involved 164 variations claims made by the plaintiff during the course of the project. Twenty-three of the variations were not pursued at trial. The plaintiff claimed the cost of performing the variations under its quantum meruit claim, in restitution, pursuant to the principles of Liebe v Molloy, on the grounds of misleading and deceptive conduct and pursuant to cl.40 of the contract.

# It is unnecessary for me to consider the claim relating to variations under the Trade Practices Act 1974 (Cth). The plaintiff contended that by its defence and counterclaim the defendants made admissions that the variations were performed, that they were performed under the contract and, further, they were performed as directed by the superintendent. As a consequence, the plaintiff alleged that there were only two issues in dispute with respect to the variation claims made by the plaintiff. The two issues were, firstly, the application of s.33 of the Domestic Building Contracts Act and whether that operated as a bar against the variations claims; and secondly, the quantum of each of the variations.

# Evidence as to the variations claims were provided in the evidence of Le Hy Ta, Tivendale and, also, the expert witness statements of Gilfillan and Lee.

# The evidence of the witnesses has been described already. It is appropriate to revisit the relevant contractual provisions. Clause 23 empowered the superintendent to give directions under the contract. Clause 40.1 enabled the superintendent to “increase, decrease or omit any part of the work” or “executive additional work”. Clause 8.1 directed that, if such direction caused the contractor to incur more or less cost than could reasonably have been anticipated at the time of tendering, then the difference was to be valued under cl.40.5. Clause 40.5 provided that a valuation would be made and the principals would pay, or allow the contractor, or vice versa, as the case may be.

# The documentary procedure adopted by the parties and the superintendent in relation to the variations was four-fold: first, by the plaintiff would submit a request for information (an RFI); second, the superintendent would respond to the RFI by way of a direction or approval (an SA); third, the plaintiff would then submit a notice of price variation (an NPV); and finally, the superintendent would respond to the NPV by way of a variation approval (usually referred to again as an SA). This procedure was not in issue between the parties. Under the variations schedule provided by the plaintiff, claims fell within six categories. There were variations that were agreed, variations that were agreed except for margin, variations in which the valuation was disputed, variations that were not determined, variations as rejected by the superintendent and, finally, variations that the plaintiff had not submitted to the superintendent at the date of suspension of works.

# Ultimately, the plaintiff and the defendants resolved the treatment of the variations under a Scott Schedule as to the variations to be allowed.

Deduction Variations

# There was also the matter of the deduction variations. The defendants claimed an entitlement to deduction variations totalling $493,656 arising from the alleged failure of the plaintiff to provide items specified as part of the original scope of the works and, also, to give the defendants a credit where there was a price difference between the cost of items actually installed and the cost of items specified in the contract. Tables were provided by the defendants summarising the deduction variations.

# Ultimately, of the claim for deduction variations, 116 were resolved by agreement between the parties for the total sum of $40,000 as set out in category A of table A; 18 were resolved by the defendants accepting the sum of $12,341 proposed by the plaintiff as set out in category B of table A; 91 were conceded by the defendants as set out in category E of table A; and 91 were ultimately in dispute as set in categories C and D of table A. Of the 91 deduction variations in dispute, 23 were disputed by the plaintiff on the basis that the items were not specified in the original scope of works; eight were disputed by the plaintiff on the basis that the plaintiff contended that the specified item was in fact installed by it; six were disputed on the basis of price as set out in category C of table A; and as to the balance, the plaintiff disputed that the defendants were entitled to a credit for the price differential between the price of the items actually installed and the price of the items specified in the contract.

# Turning then to the latter matter, it was not in dispute that the plaintiff installed various items at cost. The defendants complained that the evidence of Le Hy Ta demonstrated that wherever a price difference flowed to the plaintiff he claimed it, but a price flow-on was only made to the defendants if and when Sopov sought the price difference. I do not accept the complaint concerning the evidence of Le Hy Ta. Clearly the plaintiff was entitled to claim a price difference if and when it arose. As to the matter of Sopov, then it was up to him to make a claim for a price differential.

# With respect to the matter of the estoppel, I can not be satisfied that the evidence makes out the various ingredients necessary to establish such estoppel. There was no evidence led by the plaintiff to establish whether any sub-contractor retained a price difference; and there was no sufficient evidence by Le Hy Ta or Tivendale as to the assumption and reliance necessary to establish the estoppel urged. Ultimately, the matter of the estoppel appeared to be an afterthought on the part of the plaintiff when the allegation appeared in the plaintiff’s later pleading.

# Ultimately, there was very little dispute between the parties with respect to the deduction variations. These were largely resolved by the time of final addresses. I accept the submissions on behalf of the defendants with respect to deduction variations.

DEFECTS

# A claim was made under the defence and counterclaim relating to defects. The defects fell into three categories: category 1 being defects in the work identified and rectified by the plaintiff prior to its suspension of works on 18 September 2000; category 2 being defects in the works which Jeffery identified at the time the defendants purported to take the works out of the hands of the plaintiff; and category 3 being defects in the works that were discovered subsequent to 6 October 2000. A separate claim in relation to defects had been made but was not pursued at trial.

# The defects claim merged into the costs to complete claim and partially into the deduction variations claims. The evidence in relation to the defects claim was given by Sopov, Jeffery and Irving. Sopov said that defects started to become a concern in November 1999 and were observed and discussed in site meetings and recorded in the minutes of those meetings. Irving, a representative of the superintendent at the time, made inspection reports which were distributed and attached to site meeting minutes. Sopov said in his evidence that he expressed his concern about the quality of the work on the area known as the metal stud partition system and, also, the plastering works. He was also concerned whether these items had been installed according to the manufacturer’s recommendations.

# Ultimately, Sopov approached Khouri, a representative of Rondo Building Services, who attended the site and inspected the steel framework. Sopov said that the plaintiff thereafter removed the plasterboard so it could perform the rectification works to the steel frameworks. The only other item that Sopov said became a concern was when he discovered that the entry steps to the area known as the art gallery were missing a concrete step. A drawing was called for and this work clearly constituted an omission, but not necessarily a defect.

# Sopov gave evidence that numerous components of work were defective: structural steel, steel wall framing and plastering, woodwork, windows, doors and Alucobond cladding, resilient and tiling finishes, air, hydraulic and fire services, electrical installation, mechanical services and other items. Jeffery said there were an enormous number of defects and provided five lists. He also gave evidence that, after the plaintiff left the site, many additional defects were found. From October 2000, the defendants set about rectifying the alleged defects and completing unfinished works. A decision was made by the defendants not to differentiate between incomplete and defective works as it was said that contractors could not distinguish between the two. Hence, they were merged.

# Tivendale gave evidence that a defects list was maintained from approximately March 2000 onwards and that current defects were discussed at site meetings up until the suspension of works on 18 September 2000. Tivendale was not challenged in relation to this evidence. The defects summary attached to site meeting minutes number 34 of 12 September 2000 revealed 86 reported defect claims. In relation to those 86 items, Tivendale said that 26 items had been inspected and approved; seven items had been notified by Kane in a letter dated 21 July 2000 to have been completed and an inspection requested; 43 items required Kane to submit a compliance certificate upon final hand-over; one item was awaiting approval by consultants Keith Long and Associates; four items related to defects that Kane was in the process of rectifying; and four items were outstanding defects.

# Tivendale concluded in his evidence that of the 86 reported defect items, only eight were, in fact, outstanding. Tivendale was not cross-examined in relation to this evidence. It stood unchallenged, notwithstanding the assertions of the defendants, in particular, Sopov and Jeffery. Tivendale said that between March and September 2000 the plaintiff attended to the rectification of notified defects by contacting the relevant sub-contractor and by ensuring that the defective work was rectified in a timely manner when that sub-contractor returned to the site.

# In any event, after the filing of witness statements for the purposes of the trial, Tivendale set about the examination of allegations in the statement of Sopov with respect to defects. For that purpose, Tivendale set about examining all of the documents referred to in the statement of Sopov concerning defects. Tivendale then provided a witness statement in reply. In that statement, Tivendale made concessions in relation to deductions from the quantum meruit claim on the basis that some costs alleged by the defendants had been caused by the plaintiff, or that there were other reasonable grounds to make the concession.

# Ultimately, the plaintiff submitted that, on analysis of a summary of the deductions conceded by Tivendale, the amount of $70,065 should be made against its quantum meruit claim. In all the circumstances, I accept the evidence of Tivendale.

# There were, however, specific items in the defects categories that warrant detailed consideration. The first of these was the wall rectification work. Tivendale stated that the stud wall issue was the subject of inspection by Khouri in the week of 20 to 25 February 2000 and on that occasion the persons present were Tivendale, Sopov and Jeffery. Discussions were held at that time about the necessary rectification works required to be performed on the partition walls and a method of rectification was agreed upon.

# The plaintiff performed all of those works within a two week period. The defendants said that the rectification of the stud walls in fact took several months. In the course of the cross-examination of Le Hy Ta, it was suggested that the work took place between March and August 2000. In fact, in re-examination of Le Hy Ta, it became apparent that between February and August 2000, the plaintiff performed a substantial amount of work under the contract in relation to plastering and wall framing.

# It was apparent, and I so find, that although the plaintiff was working during that period of some months on a range of plastering and wall framing jobs, in fact, a limited amount of that time related to rectification work. I accept the evidence of Tivendale and Le Hy Ta in this respect. The wall framing period in fact increased from 60 per cent to 99 per cent complete as certified. The plasterwork was certified as 48 per cent complete in February 2000 and 97 per cent in August 2000. These percentages of completion at the relevant time satisfy me that the work was completed as described by Tivendale. Tivendale also gave evidence that in the period from the defects schedule dated 7 March 2000 to the defect summary dated 12 September 2000, only two additional defect items were added to the list by the superintendent.

# Tivendale was not challenged in this respect as to his evidence. The evidence is important because, in the six month period immediately prior to the suspension of work, the evidence established that only two items were added to the defects list in the period and, further, that the plaintiff had substantially reduced the number of defects items, that is, from 86 to eight in number. It also established that the plaintiff was performing its contractual obligations in relation to the rectification of defective work.

# It was submitted, on behalf of the plaintiff, that of the limited number of defective works as at 18 September 2000, all such defects would have been rectified by the plaintiff in the event it remained on-site as builder. It relied upon its performance of rectification of defective work in support of the assertion. As already indicated, I accept the evidence of Tivendale and Le Hy Ta with respect to the rectification of defective works and the way in which the plaintiff went about those matters. I ultimately conclude that the deduction figure identified by Tivendale, namely the sum of $70,065, is the appropriate amount to be deducted from the quantum meruit claim of the plaintiff for the purposes of the defects claim made by the defendants.

COSTS TO COMPLETE

# The defendants claimed against the plaintiff the cost to complete the building project. It was submitted that, as the plaintiff committed a substantial breach of the contract by suspending the work in breach of cl.33.1, and upon the service by the defendants of a written notice to show cause and upon the plaintiff failing to show such cause; then the defendants were entitled to take the work out of the hands of the plaintiff. As a consequence, between 2 October 2000 and 31 March 2002, the defendants substantially completed the project. In reliance upon cl.44.6 of the contract, the defendants claimed the cost to complete the works as a debt due from the plaintiff. On 30 August 2002, the superintendent issued a certificate under cl.44.6 of the contract certifying the cost incurred by the defendants in completing the work at $1,181,548.00. The defendants submitted that the certificate issued by the Superintendent should be adjusted to the amount of $1,011,310.03 as a result of certain concessions they had made.

# Evidence as to the costs incurred by the defendants to complete the development was given by Sopov and Jeffery. The costs of completion as certified by Jeffery as superintendent fell into three categories: on-site costs; off-site costs; and a contingency for incomplete works. The on-site costs included the costs of materials, subcontractors, general labour, hire of equipment, and similar expenses required to complete the works. The on-site costs included hire of equipment, for example powerboards, compressors, welding equipment and scissor lifts; small tools and equipments such as sanding discs, screws and the like; rubbish removal, services namely, water and electricity and general construction supplies by way of adhesives and masking tape and other items.

# Under the heading of on-site costs, a claim was also made for general labour being labour as employed directly by the defendants to complete and rectify minor works, for example, tiling, plastering, grouting, sanding, painting and demolition. A claim was also made with respect to labour that included independent contractors employed by the defendants to complete and rectify other minor works. There were trade breakdowns in addition employed in direct payment of materials for specific trades; for example, plaster, timber, tiles and Alucobond, and the payment of sub-contract accounts.

# Next there was the matter of off-site costs which included the costs of administering the project such as telephones, car expenses and insurance. The off-site costs also included amounts for project management, supervision of day labour and sub-contractors and consultants’ expenses. There were 11 sub categories of off-site costs. They included, as already indicated, telephones, vehicles, salaries, works insurance, other salaries and superannuation, reimbursements, consultants, and on-site costs incurred by the defendants in completing the works. The defendants also claimed a contingency amount as certified by the superintendent. The amount was not a true cost to complete, as conceded by the defendants, but was made to allow for the fact that, as at 31 March 2002, significant areas of work remained to be completed in the areas described as the gallery, office, restaurant and studio.

# Ultimately, the matter of costs to complete essentially turned upon the extent of completion at the time that the plaintiff left the site. I accept the evidence of the plaintiff, in particular, Tivendale, that the works were 90 per cent complete at the time. The defendants’ case was that works were 60 per cent complete. More significantly, the view of the superintendent under payment certificate 14 was that the plaintiff had completed over 90 per cent of the contract work. Against this background, it is difficult to allow the defendants in the event more than the costs of the remaining 10 per cent of the works. However, as I have found that the plaintiff was entitled to terminate the contract it is unnecessary for me to consider the matter of costs to complete further.

QUANTUM MERUIT

# The primary claim in the proceeding by the plaintiff was for payment for the works performed on the basis of a quantum meruit for a specified sum. The sum constituted all expenditure incurred by the plaintiff on the project, together with a 10 per cent margin, less amounts paid by the defendants during the course of the project.

# The plaintiff claimed on a quantum meruit on the basis that if it made out its case on termination it, as an innocent party who has accepted repudiation, has the option of either suing for damages for breach of contract or suing on a quantum meruit for the work done. However, the plaintiff did not expressly state its election, although given the way it put its case, namely primary relief based on a quantum meruit, it may be taken to have so elected.  The defendants did not press the issue of election.

# In Brooks Robinson Pty Ltd v Rothfield [1951] VLR 405, Dean J (with whom Martin and Scholl JJ agreed) held that, having accepted the repudiation of a contract, the innocent party could elect to sue upon a claim in damages or in quantum meruit.  This view, espoused more than 50 years ago, apparently remains consistent in many jurisdictions; despite the potential controversy regarding the application of restitutionary remedies in this manner, subsequent to the High Court’s decision in Pavey & Matthews Pty Ltd v Paul.  For example, in the recent NSW Court of Appeal case of Abigroup Contractors Pty Ltd v ABB Service Pty Ltd (formerly ABB Engineering Construction Pty Ltd), Giles JA (with whom Tobias JA and Cripps AJA agreed) held that:

[I]t was always open to the plaintiff to litigate a quantum meruit claim in the alternative to its damages claim for repudiation and to defer electing between the two remedies until the time for judgment.

# One benefit of such an approach for the innocent party is that the contract price will not act as a ceiling to the amount that the party can recover; notwithstanding that a claimant cannot double dip in respect of the same items claimed.

# However, implicit acceptance of the view that an innocent party that has accepted a repudiation of a contract is automatically entitled to elect between damages and restitution (in this case a claim in quantum meruit) has received significant academic disapproval, given the guidance for applying restitutionary remedies that has been essayed by the High Court since Pavey & Matthews.  In particular, the appropriateness or otherwise of imposing restitutionary remedies is highlighted by the oft-quoted passage of Deane J in that case where his Honour observed that

[I]f there was a valid and enforceable agreement governing the claimant's right to compensation, there would be neither occasion nor legal justification for the law to superimpose or impute an obligation or promise to pay a reasonable remuneration. The quasi-contractual obligation to pay fair and just compensation for a benefit which has been accepted will only arise in a case where there is no applicable genuine agreement or where such an agreement is frustrated, avoided or unenforceable. In such a case, it is the very fact that there is no genuine agreement or that the genuine agreement is frustrated, avoided or unenforceable that provides the occasion for (and part of the circumstances giving rise to) the imposition by the law of the obligation to make restitution.

# More recently, in Trimis v Mina, Mason P (with whom Priestley and Handley JJA agreed) said that:

The starting point is a fundamental one in relation to restitutionary claims, especially claims for work done or goods supplied. No action can be brought for restitution while an inconsistent contractual promise subsists between the parties in relation to the subject matter of the claim. This is not a remnant of the now discarded implied contract theory of restitution. The proposition is not based on the inability to imply a contract, but on the fact that the benefit provided by the plaintiff to the defendant was rendered in the performance of a valid legal duty. Restitution respects the sanctity of the transaction, and the subsisting contractual regime chosen by the parties as the framework for settling disputes. This ensures that the law does not countenance two conflicting sets of legal obligations subsisting concurrently.

# While the High Court does not appear to have made any more explicit or recent observations relevant to this threshold question (as it applies in these particular circumstances) of whether or not an innocent party that has accepted a repudiation of a contract can automatically elect between a claim in damages and one in quantum meruit, I note the observation of Mason CJ and Dawson J in Commonwealth of Australia v Amann Aviation Pty Ltd (made in the context of considering the bases for assessing damages), where their Honours said that:

We do not regard the language of election or the notion that alternative ways are open to a plaintiff in which to frame a claim for relief as appropriate in a discussion of the measure of damages for breach of contract.

# In Brenner v First Artists’ Management Pty Ltd, Byrne J, expounded upon the basis upon which restitutionary remedies might be applied as explained by Pavey & Matthews, however his Honour did not refer to Brooks Robinson Pty Ltd v Rothfield, nor did his Honour specifically consider the potential uncertainty evident as to whether or not a successful plaintiff, such as in this case, can automatically elect between damages and a quantum meruit.

# The matter was not pressed by the defendants and in view of the way the plaintiff put its case, the matter is left to the Court.  In this regard I observe that cl.44.10 of the agreement in this case provided for common law rights in the event of repudiation and entitlement to damages.

# In the context of a particular category of case, particularly a building claim as in this case, the proposition in Pavey is difficult to implement.  The reason being, in all likelihood, Pavey, and subsequent authorities, were not concerned with the circumstances of repudiation and termination and the position of the “innocent” party.  However, the approach has developed of enabling an “innocent” contractor to elect to recover under a quantum meruit. If this is the correct approach, then the only remaining issue is whether the “innocent” party who is permitted to recover on a quantum meruit is entitled to the reasonable cost of performing the works or the value of the work performed.

# I consider that on the basis of the authorities the proper course is to allow the plaintiff in this case to recover on the basis of a quantum meruit by way of an assessment of the fair and reasonable value of the work. The plaintiff submitted figures under various categories.

# The quantum meruit claim by the plaintiff was constituted by purchase orders, sub contract accounts and a 10 per cent margin for overheads and profit. The purchase orders were derived from the Cost Type Details Report, dated 25 June 2002, and table 2 of that report which listed subcontractors’ amounts. Further, materials that were purchased and the hire of plant and equipment and some subcontractor costs were included within the purchase order. These matters were set out in the evidence of Le Hy Ta. It was the evidence of the plaintiff (through Le Hy Ta and, also, Lucas) that the plaintiff had paid all of the amounts claimed under the purchase orders and that each item related to the building project. It was also the evidence of the plaintiff, through Le Hy Ta, that the sub-contractor final accounts comprised works performed by the sub-contractors engaged by the plaintiff in relation to the project.

# In the assessment of a claim brought on a quantum meruit, a court is usually concerned to assess that which is fair and reasonable for the value of the work performed. The assessment of a reasonable sum in the context of a building case would usually be to assess the degree of completion of the work and the value of the work so completed: see Fletcher Construction Australia Limited v Lines McFarlane and Marshall Pty Ltd (No. 2). There is an obligation on the party claiming on a quantum meruit in a building context to establish the work performed and its value and, further, that it was performed with proper skill: see Riverside Motors Pty Ltd v Abrahams, Renard Constructions (ME) Pty Ltd v Minister for Public Works. The claimant must also establish that the work was completed within a reasonable time.

# The Jobpac reports were critical to the quantum meruit claim. They provided information relating to the total costs and payments made by the plaintiff. The total sum stated in the Cost Type Detail Report produced a total costs and payments amount made by the plaintiff on the project of $4,746,911. The report was produced as part of the evidence of Le Hy Ta. The defendants did not cross examine Le Hy Ta on his evidence with respect to whether the costs incurred by the plaintiff were fair and reasonable. In that respect it remained unchallenged. An issue arose in the context of the variations and the submissions with respect to that matter. However, the evidence of Le Hy Ta with respect to the quantum meruit claim and the subject of whether the costs were fair and reasonable was not attacked.

# However, in the course of cross-examination, Le Hy Ta was asked questions with respect to the committed budget figure. Le Hy Ta said that the total of the committed budget figure on Jobpac was the contract sum less the margin of the plaintiff. He said that the committed budget figure was not altered during the course of the project with respect to both variations and extension of time claims without the certification of the superintendent. It was submitted by the plaintiff, therefore, the committed budget figure did not represent the cost of works performed and excluded variations work and delay costs. I deal with that matter in the context of variations and the extension of time claims.

# Furthermore, the defendants did not challenge the evidence of Tivendale with respect to the quantum of delay costs or suggest that such costs were not necessarily incurred or were not fair and reasonable.  It was the evidence of Tivendale that Kane incurred the amounts of the delay costs and the quantum was fair and reasonable and reflective of the delay costs actually incurred. This evidence was also given by Le Hy Ta.

# With respect to the quantum meruit claim, the plaintiff also relied upon the evidence of Lucas. Lucas was the finance director of Kane and held responsibility of ensuring that the financial status of projects undertaken by the plaintiff was accurately reported for accounting purposes. Lucas dealt with matters such as accounts receivable, accounts payable, payroll, insurances and such matters. Lucas described the fact that Kane had used a computer system known as Jobpac from March 1999 and that it was a software system specifically designed for use by construction businesses so that the user can establish the revenue and costs relating to particular projects. He said that Jobpac reports record all of the direct costs incurred by the plaintiff in carrying out the project, but do not include indirect expenses. Lucas said that all suppliers’ invoices and relevant financial details are entered onto the Jobpac system under the relevant project to which they relate. He said that the details relating to a sub-contract, including claims for payment made by a sub-contractor, are also entered into the Jobpac system by the plaintiff’s account staff. Lucas described in some detail the way in which the Jobpac reports are prepared and, in particular, the Cost Type Details Report so as to identify all costs incurred and the payments made.

# In reliance upon the evidence of Le Hy Ta, Tivendale and Lucas, together with the Jobpac reports, the plaintiff urged that it had proved the quantum of the costs incurred and established that those costs were fair and reasonable. There was no challenge by the defendants to the proofs by the plaintiff of these matters under the quantum meruit claim. Further, the defendants did not dispute that the work was performed. The issue was whether the work was part of the contract or necessitated by the actions of the plaintiff.

# During the trial the defendants attacked the evidence of Thomas, the quantity surveyor called by the plaintiff to support its case that the costs under the quantum meruit were fair and reasonable. The defendants criticised Thomas and said that there was no evidence regarding the value of the work performed. It was submitted for the defendants that all Thomas in fact did was give evidence of the accuracy of tables relied upon by the plaintiff as particulars of its quantum meruit claim and his audit of a representation of those particulars. Ultimately, Thomas concluded in his witness statement that on the basis of the sample order he conducted that the costs incurred accurately reflected the actual costs incurred.

# However, the defendants attacked that evidence on the basis that Thomas relied upon invoices to satisfy himself that those invoices accorded with the claim. It was put by the defendants that the checking of the invoices and their accord, if any, with the claim did not disclose whether the costs were “necessarily incurred”. Essentially, the complaint of the defendants was that there was extensive re-work that had to be performed by them by way of removing and replacing stud walls with consequential rework by plasterers, plumbers and electricians, and that the evidence of Thomas did not take account of those matters. In essence, the complaint of the defendants was that Thomas never considered rectification or the cost of rectification works.

# It was also claimed by the defendants that less than 90 per cent of the work was completed by the plaintiff.  In light of the extent of the rectification works that were required to be performed by the defendants, it is difficult to assess the fair and reasonable aspect of the quantum meruit claim. Notwithstanding that there was no direct challenge to the evidence of Le Hy Ta as to the manner of calculating the amounts contained in the quantum meruit claim, at all times, the issue was squarely to the fore in the proceedings that the defendants claimed that the costs were incurred largely due to delays on the part of the plaintiff and, also, by the rectification works that they had to perform on the site.

# I am satisfied the works were performed and it has proved the amounts claimed. However, the issue is then whether the costs claimed were fair and reasonable. That brings matters to the questions of the delays and rectification claimed by the defendants and, also, the matter of liquidated damages.  Deductions can be made to a quantum meruit claim on the account of the cost of rectifying the work to accord with the contract: see Steele v Tardiani; or to represent or record that the work was not left in a satisfactory state: see Alucraft Pty Ltd (in liq) v Grocon Ltd.

# There is an entitlement to deduct liquidated damages from a quantum meruit amount if the work failed to reach the practical completion unconditionally before the contract was terminated: see McDonald v Dennys Lascelles Ltd; Westralian Farmers Ltd v Commonwealth Agricultural Service Engineers Ltd. It follows, therefore, that notwithstanding the making out of the quantum meruit claim by the plaintiff, the amount to which it is entitled should take account of the matters of delays; rectification and liquidated damages, if any.

# The plaintiff also included in the quantum meruit claim a component for overhead and profit margin of 10 per cent on the purchase order and sub-contract payments. In my view, the margin does not arise. In the determination of a claim based on quantum meruit the approach of the courts is to assess an amount on the basis of work actually done and on the basis that it is fair and reasonable in the circumstances. It does not seem to me that a component of a margin is one contemplated by the authorities in the context of assessing a claim based on quantum meruit. It is the actual cost of the work done that is intended to be the subject of the assessment on a quantum meruit. A profit margin seems to me to lie more properly with contractual damages rather than on a quantum meruit. Accordingly, no allowance is included in the assessment on the quantum meruit for a profit margin as claimed by the plaintiff.

# In the course of the trial, the defendants elected not to seek to prove defective works or the cost of them. However, in the course of his evidence, Tivendale conceded that some deductions are appropriate to be made against a quantum meruit claim.

OTHER RELIEF

# The plaintiff otherwise claimed restitution, rectification and undue influence. In light of my findings it is unnecessary to consider restitution and rectification. The allegation of undue influence was not made out.

MISLEADING AND DECEPTIVE CONDUCT

# The plaintiff alleged that the defendants represented that they would pay for work performed by the plaintiff pursuant to the contract in accordance with the terms and conditions of that contract relating to payment and measurement and value of work. It was argued that the representations were made between May 1999 and 20 August 1999. The plaintiff alleged that the representation was false upon the defendants filing their further amended defence on 26 February 2001, whereby the defendants purported to rely upon the provisions of s.33 of the Domestic Building Contracts Act 1995. In effect, the plaintiff purported to allege that a representation was false not at the time it was made that is, between May 1999 and 20 August 1999, but later, by virtue of an event that occurred subsequently. On that basis, the plaintiff relied upon s.51(A) of the Trade Practices Act 1974. The plaintiff carries the evidentiary burden to establish that the grounds for making the representation existed.

# For the defendants, it was argued that, at the time of the making of the representations, the defendants intended to pay for all works ordered under the contract and were unaware of the provisions of s.33 of the Domestic Building Contracts Act. On that basis, it was said that that was the end of the matter for the defendants. In light of my findings with respect to the application of the Domestic Building Contracts Act, it is unnecessary for me to determine the claim by the plaintiff under the Trade Practices Act.

DOMESTIC BUILDING CONTRACTS ACT

# The defendants pleaded that progress claim 14 was issued in breach of the contract as varied by the Domestic Building Contracts Act 1995 (“the Act”). They asserted that progress claim 14 was invalid and of no effect in that they sought to increase the contract price in breach of ss.16 and 33 of the Act.

# Notably, the defence was not taken by the defendants during the life of the building works. At no stage did the superintendent raise the issue, in particular, when he proceeded to assess progress claim 14 and later issued payment certificate 14 in response to the claim. The defendants relied upon the purported statutory defence in their defence and counterclaim that was filed a year after the plaintiff had finished work on the site.

# Section 16 of the Domestic Building Contracts Act provides for a penalty as

“16. Builder must not seek more than the contract price.

(1) A builder who enters into a Domestic Building Contract Act must not demand, recover or retain from the building owner an amount of money under the contract in excess of the contract price unless authorised to do so by this Act.

Penalty: 100 penalty units.

(2) Sub-section (1) does not apply to any amount that is demanded, recovered or retained in respect of the contract as a result of a course of action the builder may have that does not involve a claim made under the contract. “

# Section 33 is also relevant. It prohibits a builder from entering into a major domestic building contract that allows the price to change unless the builder warns to owner in the manner proscribed by s.33 (2) of the Act. Section 33 provides:

“33. Contract must contain warning if price likely to vary.

(1) 		This section applies to a major domestic building contract that 	contains a provision:

(a) that allows for the contract price to change: but

(b) that is not a cost escalation clause as defined in s.15.

(2)	A builder must not enter into such a major domestic building contract unless there is a warning that the contract price is subject to change and that warning.

(a) is placed next to that price; and

(b) is in a form approved by the Director; and

(c) specifies the provision of the contract that allow for the change.

Penalty: 50 penalty units.

(3) 	If a warning is not included in a contract as required by sub-	section (2), any provision in the contract that enables the 	contract price to change only has effect to the extent that it 	enables the contract price to decrease.”

# The defendants argued that cl.36 and cl.40 of the contract are properly construed as cost escalation clauses within the meaning of s.15 of the Domestic Building Contracts Act. The defendants argued that the plaintiff failed to provide them with a notice in a form approved by the Director explaining the effect of the clauses and the signature, seal or initials of the building owner was not endorsed next to cll.36 or 40 of the contract.  As a consequence, the defendants submitted that cll.36 and 40 of the contract were void pursuant to s.15(3) of the Act.

# It was further submitted by the defendants that under various clauses of the contract, namely, cll.3, 4, 8, 11, 12, 14, 27, 28, 30, 31, 33, 34, 41, 42, 44 and 45, provision is made for an allowance for the contract price to change. The defendants pointed to the fact that the contract did not include a warning next to the contract price in the approved form stating that the contract price was subject to change. Accordingly, so it was argued, the aforesaid clauses were effective only to the extent that they enabled the contract price to decrease as provided by s.33(3) of the Domestic Building Contracts Act. It was argued that the Court did not have a discretion in the matter. It was further submitted that, according to the prohibitions under ss.15(3) and 33(3) of the Act, the plaintiff was prohibited from arguing that the subject clauses have effect for the purpose of allowing the contract price to increase.

# The Domestic Building Contracts Act was considered by the Victorian Court of Appeal in Winslow Constructions Pty Ltd v Mt. Holden Estates Pty Ltd. In that case, the plaintiff claimed that the defendants had failed to carry out works at a development site in a proper manner and in accordance with contractual arrangements. The issue before the Court of Appeal arising from an appeal against orders made at the Victorian Civil and Administrative Tribunal (VCAT) was whether any part of the works carried out by either of the respondents fell within s.5 of the Domestic Building Contracts Act; whether the respondent was a builder as defined in the Act; and whether the dispute between the parties was a domestic building dispute as defined in the Act. The contract incorporated into the main contract was General Conditions of Contract (AS 2124-1992).  Part of the evidence before the Court was by a director and other witnesses to the effect that contracts for civil and engineering infrastructure or sub-divisional works had never been said to fall under the scope of the Domestic Building Contracts Act.  It was further opined that the contracts in issue did not conform with the Act. The appeal came before the Court arising from a review before a single judge of the Supreme Court. Hansen AJA (with whom Callaway and Buchanan, JJA.agreed) held that the construction of the relevant provisions of the Domestic Building Contracts Act had been misconstrued below. His Honour observed that the literal meaning of s.5 should be determined after considering the wider object and purpose of the Act. Hansen AJA held it was necessary to consider the existing statutory framework. His Honour turned to the framework of the Domestic Building Contracts Act:

“Turning now to the DBC Act, s.1 provides that the Act has four main purposes. These are to regulate contracts for the carrying out of domestic building work; to provide for the resolution of domestic building disputes by VCAT; to require builders to hold insurance if carrying out domestic building work; and to amend the House Contracts Guarantee Act 1987 and phase out the making of claims under that Act. It seems apparent that the DBC Act and the Sub-division Act seek to regulate two distinct activities, namely, domestic building work and sub-division of land. That the DBC Act applies to work, as distinct from land, is evident from s.5 of the DBC Act (“Building work to which this Act applies”) and the objects of the DBC Act contained in s.4.

Section 5 outlines the types of building work to which the DBC Act applies, whereas s.6 outlines the types of building works to which the DBC Act does not apply.  The DBC Act also distinguishes between two types of domestic building contract: those with a contract price above $5000 and those with a contract price of $5000 or less. In relation to the former, the builder is subject to additional obligations, and further consumer safeguards exist for the building owner. Excluded from domestic building contracts are contracts between builders and sub-contractors. This indicates that the DBC Act is only intended to apply to a restricted scope of building activity rather than building activity generally.”

His Honour continued:

“…the intent of the DBC Act is to protect individual home owners rather than commercial developers, a point which was noted by Eames JA in HIA Insurance Services.”

# Further on, Hansen AJA held:

“I also accept the appellants submission that the DBC Act was enacted to regulate the rights of home owners and builders as distinct from developers, having regard to the objects of the DCB Act in s.4 and the second reading speech.”

# While in Winslow Constructions, the views expressed by the Court of Appeal with respect to the limitations or application of the Domestic Building Contracts Act are confined to the narrow ambit before the Court on that occasion, and therefore obiter, the fact remains that the authority is of assistance in the present case. It was suggested at one point in argument that, given the fact that the present project encompassed a partially domestic building component, then it necessarily followed that the provisions of the Act applied. This cannot be so. There were components of the project that were intended for business purposes, for example, the area described as “the gallery”, and a virtually entire floor designated for office use.

# I have difficulty in accepting that in a project such as the present where it is a combined, mixed use development of residential, office and gallery and restaurant, developed by a developer, it should be subject to the protections enshrined in the Domestic Building Contracts Act. Picking up on the observations of Hansen AJA in Winslow Constructions, it seems to me that the Act was not intended to apply to developers, and for that reason alone the provisions have no bearing on the present case. Even so, the Domestic Building Contracts Act could only have application to those parts of the project intended for domestic residential use. Those parts of the development intended to be used “for business purposes” are expressly excluded from the operation of the Act by virtue of s.6(c).

# I am of the view, therefore, that the Act does not apply to a project such as the present. However, in the event that the Act did apply, it would be appropriate to consider its application so far as it went to the residential component of the development.

# It is clear in a project such as the present that the provisions of the Domestic Building Contracts Act do not, and were not intended, to apply to a document such as a progress claim in a substantial building project. More so, where the document, namely, the progress claim, seeks to claim moneys in excess of the contract price. Importantly, s.133 of the Domestic Building Contracts Act provides:

“133. Effect of a failure to comply with a requirement of this Act.

A failure by a builder to comply with any requirement in this Act in relation to a domestic building contract does not make the contract illegal, void or unenforceable, unless the contrary intention appears in this Act.”

# Furthermore, the authorities, although determined without reference to a statute such as the Domestic Building Contracts Act, are consistent in the pursuit of the principle that the principals are obliged to pay upon a certificate even in the event that error exists in relation to the certificate.

# The remaining matter to be considered, in any event, with respect to the application of the Domestic Building Contracts Act to the present case is a matter of the jurisdiction of the Court. VCAT is vested with exclusive jurisdiction over claims brought under the Act: see s.57 of the Domestic Building Contracts Act; also, ss.57 and 77 of the Victorian Civil and Administrative Tribunal Act 1998. It had transpired that proceedings were instituted before VCAT . However, in light of the proceedings in this Court, the presiding member of VCAT determined to refer the VCAT proceedings to the Supreme Court with the agreement of the parties, to be determined at the same time as the Supreme Court proceedings.

SCOTT SCHEDULE

# There were claims and cross claims between the parties as to variations, deduction variations and costs to complete. The parties agreed that all three categories would be determined by way of a Scott Schedule approach. Hence, orders were made accordingly. The relevant documents, namely the Scott Schedule and supporting documents were filed on 12 December 2003. It transpired that after consenting to that process of determination and the making of orders by consent there was a disagreement between the plaintiff and the defendants as to the content of the materials to be contained in the Scott Schedule. The plaintiff complained that the supportive documents relied upon by the defendants in their component of the schedule raised new matters and, in any event, made claims not supported by the evidence. The plaintiff filed its component of the Scott Schedule under protest.

# The consent having been given by the plaintiff, it is difficult to comprehend as to why it should be permitted to resile from that consent. No appropriate circumstances were sought to be ventilated before the Court to have the consent orders varied or set aside. In all the circumstances of this case and having read the materials included in the Scott Schedule, I am not satisfied that the orders made by consent with respect to the provision of a Scott Schedule for the various components should be varied or set aside. Indeed, I observe that to do so would have defeated the purpose of the Scott Schedule and unduly protracted the proceedings.  I observe, further, that the resolution between the parties as to the adoption of the Scott Schedule came about following extensive discussions between the parties and their representatives during the course of the trial and various adjournments allowed to facilitate those discussions and other matters.

SUMMARY OF CONCLUSIONS

# I turn then to the summary of conclusions. I am satisfied that the defendants breached the agreement by failing to pay progress certificate 14 in breach of clause 42.1. I find that no new or different obligations arose under the agreement arising from a variation to that agreement as alleged by the defendants. I further find that the defendants failed with respect to their allegations of waiver, acquiescence and estoppel said to arise from the conduct of the plaintiff in relation to progress claim 14. In addition, I find that the obligations of the parties, in particular, those of the first defendant to pay the plaintiff under payment certificate 14 were not superseded by payment certificate 15.  I find, in addition, that the submissions of the defendants with respect to the application of the Domestic Buildings Contracts Act are not made out.

# I turn then to the defendants’ claim for liquidated damages arising from the delays and, in particular, the failure to complete by the contract date. I am satisfied that at the date that the builder left the site the building works were completed to the extent of 90 per cent leaving 10 per cent of the works to be completed. In the relevant context, I further find that a portion of the EOTs claimed by the plaintiff should be allowed to the extent of 56 days and four hours.

# With respect to the defendants’ claim that the plaintiff was overpaid I find that the EOTs claimed by the plaintiff are to be allowed in part only. As a consequence, some adjustment of the amounts paid by the defendants to the plaintiff may be required.  It is a matter to be considered when the parties submit the proposed form of final orders as I will direct them to do.

# I further find that the conduct of the defendants in serving the show cause notice and subsequently drawing down the builder’s guarantee constituted repudiation of the contract and that the plaintiff was entitled to terminate the contract as it did. I also find that the defendants fail in their claim for costs to complete. Upon termination of the contract, the plaintiff, having indicated its election, became entitled to recover on the basis of a quantum meruit including allowance for the EOTs (56 days and four hours) and the other amounts claimed which require adjustment with respect to the variations and extra costs). So far as the remaining 10 per cent costs to complete are relevant, the defendants lost such entitlement when they wrongfully repudiated the contract and gave rise to the right of termination by the plaintiff. The obligations of the plaintiff ceased at that point (save with respect to the deduction variations).

# The claims of the plaintiff and the defendants in relation to the variations and the deduction variations were, by agreement, dealt with separately under the Scott Schedule.  Those matters are to be allowed for in the final orders.

# The claim of the plaintiff of undue influence with respect to the superintendent and the consequential claim for damages is not made out. It is also unnecessary for any declaratory relief to be granted in favour of the plaintiff in light of my overall findings, in particular, with respect to the application of the Domestic Building Contracts Act. It is further unnecessary for there to be any consideration of the plaintiff’s claim of misleading and deceptive conduct, namely, that the defendants would pay for the work performed.

# Finally, the defendants made claims for the cost of defective work and breach of warranties. Again, the parties agreed that these items should be subject to a Scott Schedule approach.  The items allowed therein will be adjusted and reflected in the final orders. The adjustment, will, in effect, dispose of the counter claim.

# It follows that subject to the adjustments to be made arising from the Scott Schedule items (namely, the variations, the deductions variations, the works and warranties matters) the plaintiff is entitled to recover against the defendants on the basis of a quantum meruit upon formally making its election. The defendants will succeed on their counterclaim albeit to a limited extent with respect to the deductions variations, the works and warranties.

# Orders will be made in due course. I will require the parties to submit proposed minutes of orders reflecting these reasons and the decisions set out in the Scott Schedule after an opportunity to consider these reasons.

APPENDIX A

Clause 5 Security, Retention Moneys and Performance Undertakings

5 SECURITY, RETENTION MONEYS AND PERFORMANCE UNDERTAKINGS

5.1 Purpose

# Security, retention moneys and performance undertakings are for the purpose of ensuring the due and proper performance of the Contract.

# 5.2 Provision of Security

# If it is provided in the Annexure that a party shall provide security then the party shall provide security in the amount stated in the Annexure and in accordance with this Clause.

5.3 Form of Security

# The security shall be in the form of cash, bonds or inscribed stock issued by the Australian Government or the Government of a State or Territory of Australia, interest bearing deposit in a trading bank carrying on business in Australia, an approved unconditional undertaking given by an approved financial institution or insurance company, or other form approved by the party having the benefit of the security.

# The party having the benefit of the security shall have a discretion to approve or disapprove of the form of an unconditional undertaking and the financial institution or insurance company giving it or other form of security offered. The form of unconditional undertaking attached to these General Conditions is approved.

# If the security is not transferable by delivery, it shall be accompanied by an executed transfer or such other documentation as is necessary to effect a transfer of the security.  The costs (including all stamp duty or other taxes) of and incidental to the transfer and retransfer, shall be borne by the party providing the security.

5.4 Time for Lodgement of Security

# Security shall be lodged within 28 days of the Date of Acceptance of Tender.

5.5 Recourse to Retention Moneys and Conversion of Security

# A party may have recourse to retention moneys and/or cash security and/or may convert into money security that does not consist of money where:

the party has become entitled to exercise a right under the Contract in respect of the retention moneys and/or security; and

the party has given the other party notice in writing for the period stated in the Annexure, or if no period is stated, five days of the party's intention to have recourse to the retention moneys and/or cash security and/or to convert the security; and

the period stated in the Annexure or if no period is stated, five days has or have elapsed since the notice was given.

5.6 Substitution of Security for Retention Moneys

# The Contractor shall be at liberty at any time to provide in lieu of retention moneys, security in any of the forms permitted in Clause 5.3. To the extent that such security is provided, the Principal shall not deduct retention moneys and shall forthwith release so retention moneys.

5.7 Reduction of Security and Retention Moneys

# Upon issue of the Certificate of Practical Completion, the Principal's entitlement to security and retention moneys shall be reduced to the percentage thereof stated in the Annexure or, if no percentage is stated, to 50 per cent thereof.

# Subject to the first paragraph of Clause 5.7, if in the opinion of the Superintendent it is reasonable to further reduce the Principal's entitlement to security and retention moneys, that entitlement shall be reduced to the amount which the Superintendent determines to be reasonable.

# The Principal shall, within 14 days of the Superintendent making such a determination, release security and retention moneys in excess of the entitlement.

5.8 Release of Security

# If the Contractor has provided additional security pursuant to Clause 42.4, the Principal shall release that additional security within 14 days of the incorporation into the Works of the unfixed plant or materials in respect of which the additional security was furnished.

# If the Principal has provided security, then when the Contractor has been paid all moneys finally due to the Contractor under the Contract or a Separable Portion, the Contractor shall release the security lodged by the Principal in respect of the Contract or the Separable Portion, as the case may be.

# If the Contractor has provided security, then the Principal shall release it when required by Clause 42.8.

5.9 Interest on Security and Retention Moneys

Alternative 1

# A party holding retention moneys and/or cash security shall forthwith deposit the moneys in an interest bearing account in a bank. That party shall nominate the bank and the types of account. The account shall be in the joint names of the Principal and the Contractor and shall be one from which moneys can only be drawn with the signatures of two persons, one appointed by each of the Principal and the Contractor. The moneys shall be held until the Principal or the Contractor is entitled to receive them.

# Interest earned on security lodged by the Contractor and on retention moneys belongs to the Contractor. interest earned on security lodged by the Principal belongs to the Principal.

# Upon the Principal or the Contractor becoming entitled to receive any moneys, including interest in the account, the other party shalt forthwith have that party's appointee sign all documentation necessary to withdraw the moneys and shall give the signed documentation to the other party.

Alternative 2

# A party holding retention moneys or cash security shall own any interest earned on the retention moneys or security. Except where retention moneys or cash security are held by a government department or agency or a municipal, public or statutory authority, retention moneys or cash security shall be held in trust by the party holding them for the other party until the Principal or the Contractor is entitled to receive them.

5.10 Deed of Guarantee, Undertaking and Substitution

# Where –

(a)  a party is a corporation that is related to or is a subsidiary of another corporation as defined in the Corporations Law as amended from time to time; and

(b)  the Principal has included in the tender documents a form of Deed of Guarantee, Undertaking and Substitution;

# that party shall, if requested by the other party in writing within 7 days after the Date of Acceptance of Tender lodge with the other party within 14 days after that request having been made a Deed of Guarantee, Undertaking and Substitution in the form included in the tender documents duly executed by the first party and that other corporation for the performance of the obligations and the discharge of the liabilities of the first party under the Contract.

# For the purpose of Clause 5.10, the terms `corporation' and `subsidiary' have the meanings defined in the Corporations Law.

APPENDIX B

# Clause 12 	Latent Conditions

# 12 LATENT CONDITIONS

12.1 Definition

# Latent Conditions are ---

(a)   physical conditions on the Site or its surroundings, including artificial 	things but excluding weather conditions, which differ materially from the  	physical conditions which should reasonably have been anticipated by the 	Contractor at the time of the Contractor's tender if the Contractor had —

(i)	examined all information made available in writing by the 	Principal to the Contractor for the purpose of tendering; and

(ii)	examined all information relevant to the risks, contingencies and 	other circumstances having an effect on the tender and 	obtainable by the making of reasonable enquiries; and

(ii)	inspected the Site and its surroundings; and

(b) 	any other conditions which the Contract specifies to be Latent     	Conditions.

12.2 Notification

# If during the execution of the work under the Contract, the Contractor becomes aware of a Latent Condition, the Contractor shall forthwith and where possible before the Latent Condition is disturbed, give written notice thereof to the Superintendent.

# If required by the Superintendent, the Contractor shall provide to the Superintendent a statement in writing specifying —

- the Latent Condition encountered and in what respects it differs materially;

- the additional work and additional resources which the Contractor estimates to be 50 necessary to deal with the Latent Condition;

- the time the Contractor anticipates will be required to deal with the Latent Condition and the expected delay in achieving Practical Completion;

- the Contractor's estimate of the cost of the measures necessary to deal with the Latent Condition: and

- other details reasonably required by the Superintendent.

12.3 Extension of Time and Cost

# Delay caused by a Latent Condition may justify an extension of time under 	Clause 35.5. If a Latent Condition causes the Contractor to —

(a) carry out additional work;

(b) use additional Constructional Plant; or

(c) incur extra cost (including but not limited to the cost of delay or      disruption), which the Contractor could not reasonably have anticipated at the time of tendering, a valuation shall be made under Clause 40.5.

12.4 Time Bar

# In making a valuation pursuant to Clause 12.3, regard shall not be had to the value of additional work carried out, additional Constructional Plant used or extra cost incurred more than 28 days before the date on which the Contractor gives the written notice required by the first paragraph of Clause 12.2.

APPENDIX C

CLAUSE 14 	STATUTORY REQUIREMENTS

# 14 STATUTORY REQUIREMENTS

# 14.1	Complying with  Statutory Requirements

# The Contractor shall comply with the requirements of —

# (a)  Acts of the Commonwealth;

# (b)  Acts and Ordinances of the State or Territory in which the work 			 under the Contract or any part thereof is carried out;

# (c)  Ordinances, regulations, by-laws, orders and 			 	    		 proclamations under the Acts and Ordinances;

# (d)  persons acting in the exercise of statutory powers 		          		  enabling them to give directions affecting the work under the 			  Contract.

# If a requirement is at a variance with the provision of the Contract, as soon as the Contractor discovers the variance the Contractor shall notify the Superintendent in writing specifying the difference.

# If a requirement necessitates a change to the Works or so much of the Temporary Works or method of working as may be specified in the Contract, the Superintendent shall direct a variation under clause 40.1.

# Except to the extent that the Contract provides for reimbursement in respect of a requirement referred to in Clause 14.1 the Contractor shall bear the cost of complying with the requirement, whether the requirement existed at the time of tendering or not.

# 14.2	Payment Where There is No Variation

# If a requirement does not necessitate a variation under Clause 40 but is ---

# a change after the 28th day prior to the date of closing of tenders in a requirement referred to in Clause 14.1(a), (b) or (c); or

# a requirement referred to in Clause 14.1(d), which necessitates a change in the Temporary Works or the Contractor's method of working and thereby causes the Contractor to incur more or less cost than the Contractor could reasonably have anticipated at the time of tendering, the difference shall be valued under Clause 40.5.

# 14.3 Notices and Fees

# The Contractor shall give the notices necessary to comply with the requirements referred to in Clause 14.1.

# The Contractor shall pay any-fees or charges necessary-to comply with the requirements referred to in Clause 14.1.

# If a requirement necessitates the provision or expansion of services of a municipal, public or statutory authority in relation to the Works or the Temporary Works, the Contractor shall pay any fee or charge payable to the authority for the services and to the extent to which the services are not included in the work under the Contract, the fee or charge shall be reimbursed by the Principal to the Contractor.

# If after the 14th day prior to the closing of tenders, there is required to be paid by the Contractor to a municipal, public or statutory authority in relation to the Works or the Temporary Works ---

# an increase or decrease in a fee or charge, the difference shall be valued under Clause 40.5; and

# there is a new fee or charge, that fee or charge shall be reimbursed by the Principal to the Contractor.

# 14.4 Documents Evidencing Approvals of Authorities

# The Contractor shall give the Principal copies of documents issued to the Contractor by municipal, public or other statutory authorities in respect of the work under the Contract and, in particular, any approvals of work.

APPENDIX D

CLAUSE 23		Superintendent

CLASUE 24		Superintendent’s representative.

23 SUPERINTENDENT

# The Principal shall ensure that at all times there is a Superintendent and that in the exercise of the functions of the Superintendent under the Contract, the Superintendent —

- acts honestly and fairly;

- acts within the time prescribed under the Contract or where no  time 	is prescribed, within a reasonable time; and

- arrives at a reasonable measure or value of work, quantities or  time.

# If, pursuant to a provision of the Contract enabling the Superintendent to give directions, the Superintendent gives a direction, the Contractor shall comply with the direction.

# In Clause 23 `direction' includes agreement, approval, authorization, certificate, decision, demand, determination, explanation, instruction, notice, order, permission, rejection, request or requirement.

# Except where the Contract otherwise provides, a direction may be given orally but the Superintendent shall as soon as practicable confirm it in writing.

# If the Contractor in writing requests the Superintendent to confirm an oral direction, the Contractor shall not be bound to comply with the direction until the Superintendent confirms it in writing.

24 SUPERINTENDENT'S REPRESENTATIVE

# The Superintendent shall ensure that at all times there is appointed a registered architect as Superintendent’s Representative under the contract to exercise the usual duties of a supervising architect but not more than one Superintendent's Representative shall be delegated the same function at the same time. The appointment of a Superintendent's Representative shall not prevent the Superintendent from exercising any function.

# The Superintendent shall forthwith notify the Contractor in writing of

- the appointment and the name of any Superintendent's Representative and the 50 functions delegated to the Superintendent's Representative;

- the termination of the appointment of a Superintendent's

Representative.

# If the Contractor makes a reasonable objection to the appointment of a representative, the Superintendent shall terminate the appointment.

APPENDIX E

CLAUSE 29 MATERIALS, LABOUR AND CONSTRUCTIONAL PLANT

29 MATERIALS, LABOUR AND CONSTRUCTIONAL PLANT

29.1 Provision of Materials, Labour and Constructional Plant

# Except to the extent that the Contract otherwise provides, the Contractor shall supply everything necessary for the proper performance of the Contractor's obligations and discharge of the Contractor's liabilities under the Contract.

29.2 Removal of Materials and Constructional Plant

# From time to time the Superintendent may by written notice to the Contractor direct the Contractor not to remove from the Site Constructional Plant or materials. Thereafter, the Contractor shall not remove the materials or the Constructional Plant without the prior written approval of the Superintendent, which approval shall not be unreasonably withheld.

29.3 Manufacture and Supply of Materials

# The Superintendent may direct the Contractor to supply particulars of

(a)	the mode and place of manufacture;

(b)	the source of supply;

(c)	the performance capacities; and

(d)	other information,

in respect of any materials, machinery or equipment to be supplied by the Contractor under or used in connection with the Contract.

30 MATERIALS AND WORK

30.1 Quality of Materials and Work

# The Contractor shall use the materials and standards of workmanship required by the Contract. In the absence of any requirement to the contrary, the Contractor shall use suitable new materials.

30.2 Quality Assurance

# The Contractor shall, if requirements are so stated in the Contract —

(a)	plan, establish and maintain a quality system which conforms to those requirements;

(b)	provide the Superintendent with access to the quality system of the Contractor and each of the subcontractors of the Contractor to enable monitoring and quality auditing.

# Any such quality system shall be used only as an aid to achieving compliance with the Contract and to document such compliance. Such system shall not relieve the Contractor of the responsibility to comply with the Contract.

NOTE: The inclusion of Quality Assurance requirements in a contract will require detailed clauses in the Specification or elsewhere in the Contract which have regard to the Quality Standard selected for the work.

30.3 Defective Materials or Work

# If the Superintendent discovers material or work provided by the Contractor which is not in accordance with the Contract, the Superintendent may direct the Contractor to-

(a)	remove the material from the Site;

(b)	demolish the work;

(c)	reconstruct, replace or correct the material or work; or

(d)	not to deliver the material or work to the Site.

# The Superintendent may direct the times within which the Contractor must commence and complete the removal, demolition, replacement or correction.

# If the Contractor fails to comply with a direction issued by the Superintendent pursuant to Clause 30.3 within the time specified by the Superintendent in the direction and provided the Superintendent has given the Contractor notice in writing that after the expiry of 7 days from the date on which the Contractor receives the notice the Principal intends to have the work carried out by other persons, the Principal may have the work of removal, demolition, replacement or correction carried out by other persons and the cost incurred by the Principal in having the work so carried out shall be a debt due from the Contractor to the Principal.

30.4 Variations due to Defective Materials or Work

# Instead of a direction under Clause 30.3, the Superintendent may direct a variation pursuant to Clause 40. The variation shall be valued under Clause 40.5 and —

(a)	if the variation causes an increase or decrease in the value to the Principal of the Works, regard shall also be had to the increase or decrease; and

(b)	if the variation results in the Contractor incurring more or less cost than would reasonably have been incurred had the Contractor been given a direction under Clause 30.3, regard shall also be had to the difference.

30.5 Acceptance of Defective Material or Work

# Instead of a direction under Clause 30.3 or 30.4, the Superintendent may notify the Contractor that the Principal elects to accept the material or work notwithstanding that it is not in accordance with the Contract. In that event the resulting increase or decrease in the value to the Principal of the Works and any other loss suffered by the Principal shall be valued under Clause 40.5.

30.6 Generally

# The Superintendent shall give either a direction under Clause 30.3 or 30.4 or a notice under Clause 30.5 as soon as practicable after the Superintendent becomes aware that material or work is not in accordance with the Contract. The Superintendent may give the direction or notice at any time before the issue of the Final Certificate under Clause 42.8.

# Except to the extent that to do so would be inconsistent with a direction under Clause 30.4 or a notice under Clause 30.5 and notwithstanding that the Superintendent has not given a direction under Clause 30.3, the Contractor shall promptly remove, demolish, replace or correct material or work that is not in accordance with the Contract.

# A progress payment, or a lest or a failure by the Superintendent or anyone else to disapprove any material or work shall not prejudice the power of the Superintendent to subsequently give a direction under Clause 30.3 or 30.4 or a notice under Clause 30.5.

# Nothing in Clause 30 shall prejudice any other right which the Principal may have against the Contractor arising out of the failure of the Contractor to provide material or work in accordance with the Contract.

# The Superintendent shall not be obliged to give a direction under Clause 30.4 or a notice under Clause 30.5 to assist the Contractor.

APPENDIX F

CLAUSE 33  PROGRESS AND PROGRAMMING OF THE WORKS

33 PROGRESS AND PROGRAMMING OF THE WORKS

33.1 Rate of Progress

# The Contractor shall proceed with the work under the Contract with due expedition and without delay.

# The Contractor shall not suspend the progress of the whole or any part of the work under the Contract except where the suspension is under Clause 44.9 or is directed or approved by the Superintendent under Clause 34.

# The Contractor shall give the Superintendent reasonable advance notice of when the Contractor requires any information, materials, documents or instructions from the Superintendent or the Principal.

# The Principal and the Superintendent shall not be obliged to furnish any information, materials, documents or instructions earlier than the Principal or the Superintendent, as the case may be, should reasonably have anticipated at the Date of Acceptance of Tender.

# The Superintendent may direct in what order and at what time the various stages or parts of the work under the Contract shall be performed. If the Contractor can reasonably comply with the direction, the Contractor shall do so. If the Contractor cannot reasonably comply, the Contractor shall notify the Superintendent in writing, giving reasons.

# If compliance with the direction causes the Contractor to incur more or less cost than so otherwise would have been incurred had the Contractor not been given the direction, the difference shall be valued under Clause 40.5.

33.2 Construction Program

# For the purposes of Clause 33, a 'construction program' is a statement in writing showing the dates by which, or the times within which, the various stages or parts of the work under the Contract are to be executed or completed.

# A construction program shall not affect rights or obligations in Clause 33.1. The Contractor may voluntarily furnish to the Superintendent a construction program.

# The Superintendent may direct the Contractor to furnish to the Superintendent a construction program within the time and in the form directed by the Superintendent.

# The Contractor shall not, without reasonable cause, depart from —

(a)	a construction program included in the Contract; or to

(b)	a construction program furnished to the Superintendent.

# The furnishing of a construction program or of a further construction program shall not relieve the Contractor of any obligations under the Contract including the obligation to not, without reasonable cause, depart from an earlier construction program.

APPENDIX G

Claim 34 Suspension of the works

34 SUSPENSION OF THE WORKS

34.1 Suspension by Superintendent

# If the Superintendent considers that the suspension of the whole or part of the work under the Contract is necessary —

(a)	because of an act or omission of —

(i)	the Principal, the Superintendent or an employee, consultant   or agent of the Principal; or

(ii)	the Contractor, a subcontractor or an employee or agent of either;

(b)	for the protection or safety of any person or property; or

(c)	to comply with an order of a court,

the Superintendent shall direct the Contractor to suspend the progress of the whole or part of the work under the Contract for such time as the Superintendent thinks fit.

34.2 Suspension by Contractor

# If the Contractor wishes to suspend the whole or part of the work under the Contract, otherwise than under Clause 44.9, the Contractor shall obtain the prior written approval of the Superintendent. The Superintendent may approve of the suspension and may impose conditions of approval.

34.3 Recommencement of Work

# As soon as the Superintendent becomes aware that the reason for any suspension no longer exists, the Superintendent shall direct the Contractor to recommence work on the whole or on the relevant part of the work under the Contract.

# If work is suspended pursuant to Clause 34.2 or 44.9, the Contractor may recommence work at any time after reasonable advance notice to the Superintendent.

34.4 Cost of Suspension

# Any cost incurred by the Contractor by reason of a suspension under Clause 34.1 or Clause 34.2 shall be borne by the Contractor but if the suspension is due to an act or 40 omission of the Principal, the Superintendent or an employee, consultant or agent of the Principal and the suspension causes the Contractor to incur more or less cost than otherwise would have been incurred but for the suspension, the difference shall be valued under Clause 40.5.

34.5 Effect of Suspension

# Suspension shall not affect the Date for Practical Completion but the cause of suspension may be a ground for extension of time under Clause 35.5.

APPENDIX H

CLAUSE 35 TIMES FOR COMMENCEMENT AND PRACTICAL COMPLETION

35 TIMES FOR COMMENCEMENT AND PRACTICAL COMPLETION

35.1 Time for Commencement of Work on the Site

# The Contractor shall give the Superintendent 7 days' notice of the date upon which the Contractor proposes to commence work on the Site.

# The Superintendent may reduce the period of notice required.

# The Contractor shall commence work on the Site within 14 days after the Principal-has given the Contractor possession of sufficient of the Site to enable the Contractor to commence work.

# The Superintendent may extend the time for commencement of work on the Site.

35.2 Time for Practical Completion

# The Contractor shall execute the work under the Contract to Practical Completion by the Date for Practical Completion.

Upon the Date of Practical Completion the Contractor shall give possession of the Site and the Works to the Principal.

35.3 Separable Portions

# The interpretations of

(a)	Date for Practical Completion;

(b)	Date of Practical Completion;

(c)	Practical Completion,

and Clauses 5.7, 16, 35, 37, 38, 42.3 and 42.5 shall apply separately to each Separable Portion and references therein to the Works and to work under the Contract shall mean so much of the Works and the work under the Contract as is comprised in the relevant Separable Portion.

# If the Contract does not make provision for the amount of security, retention moneys, liquidated damages or bonus applicable to a Separable Portion, the respective amounts applicable shall be such proportion of the security, retention moneys, liquidated damages or bonus applicable to the whole of the work under the Contract as the value of the Separable Portion bears to the value of the whole of the work under the Contract.

35.4 Use of Partly Completed Works

# If a part of the Works has reached a stage equivalent to that of Practical Completion but another part of the Works has not reached such a stage and the parties cannot agree upon the creation of Separable Portions, the Superintendent may determine that the respective parts shall be Separable Portions.

# In using the Separable Portion that has reached Practical Completion, the Principal shall 30	not hinder the Contractor in the performance of the work under the Contract.

35.5 Extension of Time for Practical Completion

# When it becomes evident to the Contractor that anything, including an act or omission of the Principal, the Superintendent or the Principal's employees, consultants, other contractors or agents, may delay the work under the Contract, the Contractor shall promptly notify the Superintendent in writing with details of the possible delay and the cause.

# When it becomes evident to the Principal that anything which the Principal is obliged to do or provide under the Contract maybe delayed, the Principal shall give notice to the Superintendent who shall notify the Contractor in writing of the extent of the likely delay.

# If the Contractor is or will be delayed in reaching Practical Completion by a cause described in the next paragraph and within 28 days after the delay occurs the Contractor gives the Superintendent a written claim for an extension of time for Practical Completion setting out the facts on which the claim is based, the Contractor shall be entitled to an extension of time for Practical Completion.

# The causes are —

(a)	events occurring on or before the Date for Practical Completion which are beyond the reasonable control of the Contractor including but not limited to —

(i)	industrial conditions;

(ii)	inclement weather;

(b)	any of the following events whether occurring before, on or after the Date for Practical Completion —

(i)	delays caused by-

- the Principal;

- the Superintendent;

- the Principal’s employees, consultants, other contractors or agents;

(ii)	actual quantities of work being greater than the quantities in the Bill of Quantities or the quantities determined by reference to the upper limit of accuracy stated in the Annexure (otherwise than by reason of a variation directed under Clause 40);

(iii)	latent conditions;

(iv)	variations directed under Clause 40;

(v)	repudiation or abandonment by a Nominated Subcontractor;

(vi)	changes in the law;

(vii)	directions by municipal, public or statutory authorities but not where the direction arose from the failure of the Contractor to comply with a requirement	to referred to in Clause 14.1;

(viii)	delays by municipal, public or statutory authorities not caused by the Contractor;

(ix)	claims referred to in Clause 17.1(v);

(x)	any breach of the Contract by the Principal;

(xi)	any other cause which is expressly stated in the Contract to be a cause for extension of time for Practical Completion.

# Where more than one event causes concurrent delays and the cause of at least one of those events, but not all of them, is not a cause referred to in the preceding paragraph, then to the extent that the delays are concurrent, the Contractor shall not be entitled to an extension of time for Practical Completion.

# In determining whether the Contractor is or will be delayed in reaching Practical Completion regard shall not be had to-

- whether the Contractor can reach Practical Completion by the Date for Practical Completion without an extension of time;

- whether the Contractor can, by committing extra resources or inclining extra expenditure, make up the time lost.

# With any claim for an. extension of time for Practical Completion, or as soon as practicable thereafter, the Contractor shall give the Superintendent written notice of the number of days extension claimed.

# If the Contractor is entitled to an extension of time for Practical Completion the Superintendent shall, within 28 days after receipt of the notice of the number of days extension claimed, grant a reasonable extension of time. If within the 28 days the Superintendent does not grant the full extension of time claimed, the Superintendent shall before the expiration of the 28 days give the Contractor notice in writing of the reason.

# In determining a reasonable extension of time for an event causing delay, the Superintendent shall have regard to whether the Contractor has taken all reasonable steps to preclude the occurrence of the cause and minimise the consequences of the delay.

# Notwithstanding that the Contractor is not entitled to an extension of time the Superintendent may at any time and from time to time before the issue of the Final Certificate by notice in writing to the Contractor extend the time for Practical Completion for any reason.

# A delay by the Principal or the failure of the Superintendent to grant a reasonable extension of time or to grant an extension of time within 28 days shall not cause the Date for Practical Completion to be set at large but nothing in this paragraph shall prejudice any right of the Contractor to damages.

35.6 Liquidated Damages for Delay in Reaching Practical Completion

# If the Contractor fails to reach Practical Completion by the Date for Practical Completion, the Contractor shall be indebted to the Principal for liquidated damages at the rate stated in the Annexure for every day after the Date for Practical Completion to and including the Date of Practical Completion or the date that the Contract is terminated under Clause 44, whichever first occurs.

# If after the Contractor has paid or the Principal has deducted liquidated damages, the time for Practical Completion is extended, the Principal shall forthwith repay to the Contractor any liquidated damages paid or deducted in respect of the period up to and including the new Date for Practical Completion.

35.7 Limit on Liquidated Damages

# The Contractor's liability under Clause 35.6 is limited to the amount stated in the Annexure.

35.8 Bonus for Early Practical Completion

# If the Date of Practical Completion is earlier than the Date for Practical Completion the Principal shall pay the Contractor the bonus stated in the Annexure for every day after the Date of Practical Completion to and including the Date for Practical Completion.

# The total of the bonus shall not exceed the limit stated in the Annexure.

APPENDIX I

CLAUSE 36 Delay or Disruption Costs

36 DELAY OR DISRUPTION COSTS

# Where the Contractor has been granted an extension of time under Clause 35.5 for any delay caused by any of the events referred to in Clause 35.5 (b)(i), the Principal shall pay to the Contractor such extra costs as are necessarily incurred by the Contractor by reason of the delay.

# Where the Contractor has been granted an extension of time under Clause 35.5 for any delay caused by any other event for which payment of extra costs for delay or disruption is provided for in the Annexure or elsewhere in the Contract, the Principal shall pay to the Contractor such extra costs as are necessarily incurred by the Contractor by reason of the delay.

# Nothing in Clause 36 shall -

(a)	oblige the Principal to pay extra costs for delay or disruption which 	have 	already been included in the value of a variation or any other 	payment under  the Contract; or

(b)	limit the Principal's liability for damages for breach of contract.

APPENDIX J

Clause 40 Variations

40 VARIATIONS

40.1 Variations to the Work

# The Superintendent may direct the Contractor to

(a)	increase, decrease or omit any part of the work under the Contract;

(b)	change the character or quality of any material or work;

(c)	change the levels, lines, positions or dimensions of any part of the work under the  Contract;

(d)	execute additional work; and/or

(e)	demolish or remove material or work no longer required by the Principal.

# The Contractor shall not vary the work under the Contract except as directed by the Superintendent or approved in writing by the Superintendent under Clause 40.

# The Contractor is bound only to execute a variation which is within the general scope of the Contract.

# The Contractor shall not be bound to execute a variation directed after Practical Completion unless the variation is in respect of rectification work referred to in Clause 37.

40.2 Proposed Variations

# Upon receipt of a notice in writing from the Superintendent advising the Contractor of a proposed variation under Clause 40, the Contractor shall advise the Superintendent whether the proposed variation can be effected. If the variation can be effected, the Contractor shall —

(a)	advise the Superintendent of the effect which the Contractor anticipates that the variation will have on the construction program and time for Practical Completion; and

- provide an estimate of the cost (including delay costs, if any) of the proposed variation.

# The Principal shall reimburse the Contractor for the reasonable costs of complying with the requirements of Clause 40.2.

40.3 Pricing the Variation

# Unless the Superintendent and the Contractor agree upon the price for a variation, the variation directed or approved by the Superintendent under Clause 40.1 shall be valued 45 under Clause 40.5.

# The Superintendent may direct the Contractor to provide a detailed quotation for the work of a variation supported by measurements or other evidence of cost.

40.4 Variations for the Convenience of the Contractor

# If the Contractor requests the Superintendent to approve a variation for the convenience of 50 the Contractor, the Superintendent may do so in writing. The approval may be conditional.

# Unless the Superintendent otherwise directs in the notice approving the variation, the Contractor shall not be entitled to —

(a)	an extension of time for Practical Completion; or

(b)	extra payment,

in respect of the variation or anything arising out of the variation which would not have arisen had the variation not been approved.

# The Superintendent shall not be obliged to approve a variation for the convenience of the Contractor.

40.5 Valuation

# Where the Contract provides that a valuation shall be made under Clause 40.5, the Principal shall pay or allow the Contractor or the Contractor shall pay or allow the Principal as the case may require, an amount. ascertained by the Superintendent as follows —

(a)	if the Contract prescribes specific rates or prices to be applied in determining the is value, those rates or prices shall be used;

(b)	if Clause 40.5(a) does not apply, the rates or prices in a Priced Bill of Quantities or Schedule of Rates shall be used to the extent that it is reasonable to use them;

(c)	to the extent that neither Clause 40.5(a) or 40.5(b) apply, reasonable rates or prices shall be used in any valuation made by the Superintendent;

(d)	in determining the deduction to be made for work which is taken out of the Contract, the deduction shall include a reasonable amount for profit and overheads;

(e)	if the valuation is of an increase or decrease in a fee or charge or is a new fee or charge under Clause 143, the value shall be the actual increase or decrease or the actual amount of the new fee or charge without regard to overheads or profit;

(f)	if the valuation relates to extra costs incurred by the Contractor for delay or disruption, the valuation shall include a reasonable amount for overheads but shall not include profit or loss of profit;

(g)	if Clause 11(b) applies, the percentage referred to in Clause 11(b) shall be used for valuing the Contractor's profit and attendance; and

(h)	daywork shall be valued in accordance with Clause 41.

# When under Clause 40.3 the Superintendent directs the Contractor to support a variation with measurements and other evidence of cost, the Superintendent shall allow the Contractor the reasonable cost of preparing the measurements or other evidence of cost that has been incurred over and above the reasonable overhead cost.

APPENDIX K

42 CERTIFICATES AND PAYMENTS

42.1 PAYMENT CLAIMS, CERTIFICATES, CALCULATIONS AND TIME FOR PAYMENT

# At the times for payment claims stated in the Annexure and upon issue of a Certificate of Practical Completion and within the time prescribed by Clause 42.7, the Contractor shall deliver to the Superintendent claims for payment supported by evidence of the amount due to the Contractor and such information as the Superintendent may reasonably require. Claims for payment shall include the value of work carried out by the Contractor in the performance of the Contract to that time together with all amounts then due to the Contractor arising out of or in connection with the Contract or for any alleged breach thereof.

# Within 14 days after receipt of a claim for payment, the Superintendent shall issue to the Principal and to the Contractor a payment certificate stating the amount of the payment which, in the opinion of the Superintendent, is to be made by the Principal to the Contractor or by the Contractor to the Principal. The Superintendent shall set out in the certificate the calculations employed to arrive at the amount and, if the amount is more or less than the amount claimed by the Contractor, the reasons for the difference. The Superintendent shall allow in any payment certificate issued pursuant to this Clause 42.1 or any Final Certificate issued pursuant to Clause 42.8 or a Certificate issued pursuant to Clause 44.6, amounts paid under the Contract and amounts otherwise due from the Principal to the Contractor and/or due from the Contractor to the Principal arising out of or in connection with the Contract including but not limited to any amount due or to be credited under any provision of the Contract.

# If the Contractor fails to make a claim for payment under Clause 42.1, the Superintendent may nevertheless issue a payment certificate.

# Subject to the provisions of the Contract, within 28 days after receipt by the Superintendent of a claim for payment or within 14 days of issue by the Superintendent of the Superintendent's payment certificate, whichever is the earlier, the Principal shall pay to the Contractor or the Contractor shall pay to the Principal, as the case may be, an amount not less than the amount shown in the Certificate as due to the Contractor or to the Principal as the case may be, or if no payment certificate has been issued, the Principal shall pay the amount of the Contractor's claim. A payment made pursuant to this Clause shall not prejudice the right of either party to dispute under Clause 47 whether the amount so paid is the amount properly due and payable and on determination (whether under Clause 47 or as otherwise agreed) of the amount so properly due and payable, the Principal or Contractor, as the case may be, shall be liable to pay the difference between the amount of such payment and the amount so properly due and payable.

# Payment of moneys shall not be evidence of the value of work or an admission of liability or evidence that work has been executed satisfactorily but shall be a payment on account only, except as provided by Clause 42.8.

# Notwithstanding Clause 42.4, the Principal shall be obliged to pay for any item of unfixed plant and materials where that item is—

- to be imported into Australia, provided the Contractor has given the Principal a clean on board bill of lading or its equivalent, drawn or endorsed to the order of the Principal and, where appropriate, a custom's invoice for the item; or

- listed in the Annexure and which is not an item to be imported into Australia, provided the Contractor establishes to the satisfaction of the Superintendent that the Contractor has paid for the item, and the item is properly stored, labelled the property of the Principal and adequately protected.

# Upon payment to the Contractor of the amount which includes the value of the item, the item shall be the property of the Principal free of any lien or charge.

# Except as provided in the Contract, the Principal shall not be obliged to pay for any item of unfixed plant and materials which is not incorporated in the Works.

42.2 Correction of Payment Certificates

# At any time and from time to time, the Superintendent may by a further certificate correct any error which has been discovered in any previous certificate, other than a Certificate of Practical Completion or Final Certificate.

42.3 Retention Moneys

# The Principal may deduct from moneys otherwise due to the Contractor amounts up to the limit of the percentages, if any, stated in the Annexure of so much of the value of the to respective items stated in the Annexure as is included in the calculation of a payment.

42.4 Unfixed Plant and Materials

Alternative 1

# If the Contractor claims payment for plant or materials intended for incorporation in the Works but not incorporated, the Principal shall not be obliged to make payment for the plant or materials unless the Contractor provides additional security in one of the forms provided by Clause 5.3 in an amount equal to the payment claimed for the plant or materials.

Alternative 2

# If the Contractor claims payment for plant or materials intended for incorporation in the Works but not incorporated the Principal shall not be obliged to make payment for such plant or materials but the Principal may make payment, if the Contractor establishes to the satisfaction of the Superintendent that

- such plant or materials have reasonably but not prematurely been delivered to or adjacent to the Site;

- ownership of such plant and materials will pass to the Principal upon the making of the payment claimed; and

- such plant or materials are properly stored, labelled the property of the Principal and adequately protected.

# Upon payment to the Contractor of the amount claimed, the plant or materials the subject of the claim shall be the property of the Principal free of any lien or charge.

Alternative 3

# The Contractor shall not be entitled to payment for plant or materials not incorporated in the Works.

42.5 Certificate of Practical Completion

# The Contractor shall give the Superintendent at least 14 days notice of the date upon which the Contractor anticipates that Practical Completion will be reached.

# When the Contractor is of the opinion that Practical Completion has been reached, the Contractor shall in writing request the Superintendent to issue a Certificate of Practical Completion. Within 14 days of the receipt of the request, the Superintendent shall give to the Contractor and to the Principal a Certificate of Practical Completion certifying the Date of Practical Completion or give the Contractor in writing the reasons for not issuing the Certificate.

# When the Superintendent is of the opinion that Practical Completion has been reached, the Superintendent may issue a Certificate of Practical Completion whether or not the Contractor has made a request for its issue.

42.6 Effect of Certificates

# The issue of a payment certificate or a Certificate of Practical Completion shall not constitute approval of any work or other matter nor shall it prejudice any claim by the Principal or the Contractor.

42.7 Final Payment Claim

# Within 28 days after the expiration of the Defects Liability Period, or where there is more than one, -the last to expire, the Contractor shall lodge with the Superintendent a final payment claim and endorse it `Final Payment Claim'.

# The Contractor shall include in that claim all moneys which the Contractor considers to be due from the Principal under or arising out of the Contract or any alleged breach thereof.

# After the expiration of the period for lodging a Final Payment Claim, any claim which the Contractor could have made against the Principal and has not been made shall be barred.

42.8 Final Certificate

# Within 14 days after receipt of the Contractor's Final Payment Claim or, where the Contractor fails to lodge such claim, the expiration of the period specified in Clause 42.7 for the lodgement of the Final Payment Claim by the Contractor, the Superintendent shall issue to the Contractor and to the Principal a final payment certificate endorsed `Final to Certificate'. In the certificate the Superintendent shall certify the amount which in the Superintendent's opinion is finally due from the Principal to the Contractor or from the Contractor to the Principal under or arising out of the Contract or any alleged breach thereof.

# Unless either party, either before the Final Certificate has been issued or not later than 15 days after the issue thereof, serves a notice of dispute under Clause 47, the Final Certificate shall be evidence in any proceedings of whatsoever nature and whether under the Contract or otherwise between the parties arising out of the Contract, that the Works have been completed in accordance with the terms of the Contract and that any necessary effect has been given to all the terms of the Contract which require additions or deductions to be made to the Contract Sum, except in the case of —

- fraud, dishonesty or fraudulent concealment relating to the Works or any part thereof or to any matter dealt with in the said Certificate;

- any defect (including omission) in the Works or any part thereof which was not apparent at the end of the Defects Liability Period, or which would not have been 25 disclosed upon reasonable inspection at the time of the issue of the Final Certificate; or

- any accidental or erroneous inclusion or exclusion of any work, plant, materials or figures in any computation or any arithmetical error in any computation.

# Within 14 days after the issue of a Final Certificate which certifies a balance owing by the Principal to the Contractor, the Principal shall release to the Contractor any retention moneys or security then held by the Principal.

42.9 Interest on Overdue Payments

# If any moneys due to either party remain unpaid after the date upon which or the expiration of the period within which they should have been paid then interest shall be payable thereon from but excluding the date upon which or the expiration of the period within which they should have been paid to and including the date upon which the moneys are paid. The rate of interest shall be the rate stated in the Annexure and if no rate is stated the rate shall be 18 percent per annum. Interest shall be compounded at six monthly intervals.

42.10 Set Offs by the Principal

# The Principal may deduct from moneys due to the Contractor any money-due from the Contractor to the Principal otherwise than under the Contract and if those moneys are insufficient, the Principal may, subject to Clause 5.5, have recourse to retention moneys and, if they are insufficient, then to security under the Contract.

42.11 Recourse for Unpaid Moneys

# Where, within the time provided by the Contract, a party fails to pay the other party an amount due and payable under the Contract, the other party may, subject to Clause 5.5, have recourse to retention moneys, if any, and, if those moneys are insufficient, then to security, under the Contract and any deficiency remaining may be recovered by the other so party as a debt due and payable.

APPENDIX L

Clause 44 Default or Insolvency

44 DEFAULT OR INSOLVENCY

44.1 Preservation of Other Rights

# If a party breaches or repudiates the Contract, nothing in Clause 44 shall prejudice the right of the other party to recover damages or exercise any other right.

44.2 Default by the Contractor

# If the Contractor commits a substantial breach of contract and the Principal considers that damages may not be an adequate remedy, the Principal may give the Contractor a written notice to show cause.

# Substantial breaches include but are not limited to —

- suspension of work, in breach of Clause 33.1;

- failing to proceed with due expedition and without delay, in breach of Clause 33.1;

- failing to lodge security in breach of Clause 5;

- failing to use the materials or standards of workmanship required by the Contract, in breach of Clause 30.1;

- failing to comply with a direction of the Superintendent under Clause 30.3, in breach of Clause 23;

- failing to provide evidence of insurance, in breach of Clause 21.1; and/or

- in respect of Clause 43, knowingly providing a statutory declaration or documentary evidence which contains a statement that is untrue.

44.3 Requirements of a Notice by the Principal to Show Cause

# A notice under Clause 44.2 shall —

- state that it is a notice under Clause 44 of the General Conditions of Contract;

- specify the alleged substantial breach;

- require the Contractor to show cause in writing why the Principal should not exercise a right referred to in Clause 44.4;

- specify the time and date by which the Contractor must show cause (which time shall not be less than 7 clear days after the notice is given to the Contractor); and

- specify the place at which cause must be shown.

44.4 Rights of the Principal

# If by the time specified in a notice under Clause 44.2 the Contractor fails to show reasonable cause why the Principal should not exercise a right referred to in Clause 44.4, the Principal may by notice in writing to the Contractor —

- take out of the hands of the Contractor the whole or part of the work remaining to be completed; or

- terminate the Contract.

# Upon giving a notice under Clause 44.2, the Principal may suspend payments to the Contractor until the earlier of —

- the date upon which the Contractor shows reasonable cause;

- the date upon which the Principal takes action under Clause 44.4(a) or (b); or

- the date which is 7 days after the last day for showing cause in the notice under Clause 44.2.

44.7 Default of the Principal

# If the Principal commits a substantial breach of contract and the Contractor considers that damages may not be an adequate remedy, the Contractor may give the Principal a written notice to show cause.

# Substantial breaches include but are not limited to —

- failing to make a payment, in breach of Clause 42.1;

- failure by the Superintendent to either issue a Certificate of Practical Completion or give the Contractor, in writing, the reasons for not issuing the Certificate within 14 days of receipt of a request by the Contractor to issue the Certificate, in breach of to Clause 42.5;

- failing to produce evidence of insurance, in breach of Clause 21.1;

- failing to give the Contractor possession of sufficient of the Site, in breach of Clause 27.1, but only if the failure continues for longer than the period stated in the Annexure; and/or

- failing to lodge security in breach of Clause 5.

44.8 Requirements of a Notice by the Contractor to Show Cause

# A notice under Clause 44.7 shall —

- state that f1 is a notice under Clause 44 of the General Conditions of Contract;

- specify the alleged substantial breach;

- require the Principal to show cause in writing why the Contractor should not exercise a right referred to in Clause 44.9;

- specify the time and date by which the Principal must show cause (which shall not be less than 7 clear days after the notice is given to the Principal); and

- specify the place at which cause must be shown.

44.9 Rights of the Contractor

# If by the time specified in a notice under Clause 44.7 the Principal fails to show reasonable cause why the Contractor should not exercise a right referred to in Clause 44.9, the Contractor may by notice in writing to the Principal suspend the whole or any part of the work under the Contract.

# The Contractor shall lift the suspension if the Principal remedies the breach but if within 28 days after the date of suspension under Clause 44.9, the Principal fails to remedy the breach or, if the breach is not capable of remedy, fails to make other arrangements to the reasonable satisfaction of the Contractor, the Contractor may by notice in writing to the Principal terminate the Contract.

# The Contractor shall be entitled to recover from the Principal any damages incurred by the Contractor by reason of the suspension.

44.10 Rights of the Parties on Termination

# If the Contract is terminated under Clause 44.4(b) or Clause 44.9 the rights and liabilities of the parties shall be the same as they would have been at common law had the defaulting party repudiated the Contract and the other party elected to treat the Contract as at an end and recover damages.

44.11 Insolvency

# If —

- a party informs the other party in writing or creditors generally that the party is insolvent;

- a party commits an act of bankruptcy;

- a bankruptcy petition is presented against a party;

- a party is made bankrupt;

- a meeting of creditors of a party is called with a view to—

- entering a scheme of arrangement or composition with creditors; or

- placing the party under official management;

- a party enters a scheme of arrangement or composition with creditors;

- a resolution is passed at a meeting of creditors to place a party under official management;

- a party is placed under official management;

- a receiver of the property or part of the property of a party is appointed;

- an application is made to a court for the winding up of a party and not stayed within 14 days;

- a winding up order is made in respect of a party; and/or

- execution is levied against a party by creditors, debenture holders or trustees or under a floating charge—

- where the other party is the Principal, the Principal may, without giving a notice to show cause, exercise the right under Clause 44.4 (a);

- where the other party is the Contractor, the Contractor may, without giving a notice to show cause, exercise the right under Clause 44.9.

# The rights given by Clause 44.11 are in addition to any other rights and may be exercised notwithstanding that there has been no breach of contract.

---

Third further amended statement of claim filed 29 October 2003.

Being the standard form building agreement at that time together with the documents annexed to it.

The terms “Practical Completion” and “Date for Practical Completion” were both defined by cl.2 of the contract.

A New Tax System (Goods and Services Tax) Act 1999.

Pursuant to s.82 of the Trade Practices Act 1974 and s.37 of the Fair Trading Act 1985.

For example: light switch samples, handle and door knob samples.

Clause 8.

The significant clauses of the contract are included at the end of the judgment as appendices. The relevant clause is set out in full in the particular appendix.

Cl.5.1.

Cl.5.3.

Cl.14.1.

Cl.14.1.

Cl.30.1.

Cl.34.1.

Cl.34.2.

Cl.35.2.

Provided is Part A of the annexure of the contract.

Cl.35.5

Under cl.17.1(v).

Cl.35.6.

Cl.38.7 provided for a limit on liquidated damages under cl.35 as specified in the annexure to the contract. Part BA of the annexure to the contract provided “no limit” of liquidated damages under cl.35.7 of the contract.

Cl.42.9.

As provided in Part A of the annexure to the contract and cl.42.9.

Cl.44.2 of the contract.

Cl.44.3.

Cl.44.7.

Cl.44.10.

(2002) 6 VR 1.

# Superintendent’s Direction CAMC 33, 17 September 2000.

Ibid. at [84].

All the figures exclude GST.

(2001) NSWLR 705.

(1990) 24 FCR 313.

Makita at 729; Arnotts at 349.

See Appendix D of the Judgment.

Clause 35.6

Clause 35.5.

Plaintiff’s closing submission dated 30 October 2003.

See, for example, Allcard v Skinner (1887) 36 Ch D 145; Union Bank of Australia Ltd v Whitelaw [1906] VLR 711; Commonwealth Bank of Australia Ltd v Amadio (1983) 151 CLR 447; Peter Birks and Chin Nyuk, ‘On the Nature of Undue Influence’ in Jack Beatson and Daniel Friedmann (eds), Good Faith and Fault in Contract Law (1995) 57; N C Seddon and M P Ellinghaus, Cheshire and Fifoot’s Law of Contract (8th ed, 2002) Ch 14.

[1969] 2 NSWR 530.

[1988] 13 NSWLR 661.

Ibid at 672.

Ibid.

Citing Spotts v. Baltimore & Ohio Railroad Co. 102 F (2d) 160,162 (1939).

[1989] 1 ACSCR 93.

Ibid. at 110.

See Hudson’s Building and Engineering Contracts in Australia: including the duties and liabilities of architects, engineers and surveyors (11th ed., 1995) at 821; also, Baulderstone Hornibrook Pty Ltd v Qantas Airways Ltd [2003] FCA 174 at [89].

Ibid. at 822.

Citing Lord Esher MR in McDonald v  Mayor of Workington (1983) 9 TLR 230.

Ibid.

Eg. See John Holland Construction and Engineering Pty Ltd v Majorca Projects Pty Ltd [1996] 13 BCL 235; Hickman v Roberts [1913] AC 229; Multiplex Constructions v SOR Pty Ltd [2001] 17 BCL 174; Baulderstone Hornibook Pty Ltd v Qantas Airways Ltd [2003] FCA 174.

Page v Landaff and Dinas Powis Rural Council [1901], Hudson, Building Contracts (4th ed) , vol. 2, p.316.

Hickman v. Roberts, Ibid. at 233.

Ibid.

Ibid.

Ibid. at 239.

Ibid. at 240.

Ibid. at 233, 238.

Ibid. 238.

Ibid. at 233.

Baulderstone Hornibrook Pty Ltd v Qantas Airways Ltd; Ibid. at [97].

Hickman v. Roberts,  Ibid at 236.

(2002) 18 BCL 322.

Ibid. at [50].

In their final submissions dated 30 October 2003, Kane said that “the plaintiff accepts that EOT 4 was submitted for 32 days and a contingency of 15 days and does not seek to assert that the claim was submitted for 47 days… However, Tivendale asserts that in reality the Plaintiff was delayed 47 days by the structural steel”.  I note that in the plaintiff’s consolidated particulars dated 9 November 2001, the plaintiff stated that its request for EOT 4 – as made in writing and dated 8 October 1999 – requested a total of 32 days for his EOT, with no mention of the 15 day “contingency” later inserted by Tivendale.  Given the plaintiff’s vacillation on the point, I have taken their submission to mean that they claimed 32 days and not 47 days overall for EOT 4.

Note that when added up, the various delays claimed for each component of EOT 4 exceed the total claim for 32 days. Whether the breakdown figures given in the plaintiff’s submissions were incorrect or whether Kane claimed a lesser amount overall as a result of concurrent delays (or for other reasons), it is unclear.

(2002) 18 BCL 15.

(1992) 58 BLR 1.

Ibid.

McAlpine Humberoak Ltd v McDermott International Inc, Commentary 58 BLR 5.

Ibid.

Ibid.

McAlpine Humberoak Ltd v McDermott International Inc (1990) 51 BLR 34.

(1992) 58 BLR 1, 17.

Woolf and Russell LJJ.

(1992) 58 BLR 1, 28.

Ibid. at 22.

(1902) 86 LT 764.

Peak Construction (Liverpool) Ltd v McKinney Foundations Ltd (1970) 1 BLR 114; The Cape Hatteras [1982] 1 Lloyd’s Rep 518; and SMK Cabinets v Hili Modern Electrics Pty Ltd [1984] VR 391.

(1992) 58 BLR 1.

(1992) 58 BLR 1, 22.

Ibid. at 35.

Ibid. The court also stated that despite this detail (or perhaps indeed because of it) the pleadings of the plaintiff failed to properly identify cause and effect. With this in mind, Lloyd L.J. made the following comment: “The very fact that the total entitlement claimed by [McAlpine] … came to £1m more than their actual costs should surely have put the judge and his assessors on inquiry.”

The principles are broadly discussed in Keith Pickavance, Delay and Disruption in Construction Contracts (1st ed,1997) 486.

Fletcher Construction Australia Ltd v Lines MacFarlane & Marshall Pty Ltd (No. 2) [2002] VSCA 189.

For example, breakdowns of claims regarding masonry was given on 20 August 1999; regarding hydraulics and other items on 14 August 2000 and trade finishes on 21 August 2000.

Information was requested regarding hydraulics, Alucobond and resilient finishes on 8 August 2000 and provided on 14 August 2000. There was a further request regarding tiles on 21 August 2000 and it was provided on the same day.

See, eg, Algons Engineering Pty Ltd v Abigroup Contractors Pty Ltd (1997) 14 BCL 215, per Rolfe J; Daysea Pty Ltd v Watpac Pty Ltd [2001] QCA 49 at 18-22, per Williams JA.

See, eg, Minson Nacap Pty Ltd v Aquatec-Maxcon Pty Ltd (2001) 17 BCL 269 at [19]-[20] per Byrne J. See generally Adrian Baron, ‘Progress claims, payment certificates and legal stability’ (2003) 19 Building and Construction Law 271.

Brewarrina Shire Council v Beckhaus Civil Pty Ltd (2003) 19 BCL 177.

Brewarrina Shire Council v Beckhaus Civil Pty Ltd (2003) 19 BCL 177 at [91], citing Federated Seaman’s Union of Australasia v Commonwealth Steamship Owners’ Association (1922) 30 CLR 144.

(2004) 8 VR 16.

[2001] QCA 49.

See, eg, Algons Engineering Pty Ltd v Abigroup Contractors Pty Ltd (1997) 14 BCL 215.

The existence of such a condition precedent was considered by the NSW Court of Appeal in Brewarrina Shire Council v Beckhaus Civil Pty Ltd (2003) 19 BCL 177 and has been approved by the Victorian Court of Appeal in Aquatec-Maxcon Pty Ltd v Minson-Nacap Pty Ltd (2004) 8 VR 16; notwithstanding the significant academic discussion that has ensued: see, eg, Adrian Baron, ‘Progress claims, payment certificates and legal stability’ (2003) 19 Building and Construction Law 271.

(2004) 8 VR 16.

See for instance Byrne J’s analysis in Zauner Construction Pty Ltd v No 2 Pitt Street Pty Ltd (2001) 17 BCL 357 and the view of the Queensland Court of Appeal in Daysea Pty Ltd v Watpac Pty Ltd [2001] QCA 49.

Aquatec-Maxcon Pty Ltd v Minson-Nacap Pty Ltd (2004) 8 VR 16 at [12]-[13].

Ibid. at [26].

Ibid. at [24].

(2001) 17 BCL 357.

[2001] QCA 49.

Blue Chip Pty Ltd v. Concrete Constructions Group Pty Ltd (1966) 13 B.C.L. 31; Algons Engineering Pty Ltd v Abigroup Contractors Pty Ltd (1997) BCL 215.

The unauthorised deduction of liquidated damages point in this case is to be distinguished from the liquidated damages argument raised by the defendant contractor in State of Tasmania v Leighton Contractors [2004] TASSC 132. In that case, Cox CJ determined that the liquidated damages clause of the contract was not a genuine pre-estimate of the principal’s (i.e. the State government’s) damages. Rather, the sums deducted were “extravagant and exorbitant” and amounted to a penalty. The State was therefore ordered to pay back in full the amount of $1,832,000 deducted as liquidated damages.

See Commonwealth v Verwayen (1990) 170 CLR 394 at 444; Walton Stores Ltd v Maher (1988) 164 CLR 387.

$1,216,546.

$132,618.

$374,618.

The show cause notice was issued on 8 September 2000.

$1,216,546.64

$340,562

Le Hy Ta recorded, for instance, that Jeffery made a request for delivery dockets on 6 September 2000, the day of the site inspection for progress certificate 15. Le Hy Ta also organised for a copy of delivery dockets to be provided to Jeffery on 14 September 2000, the same day the original payment certificate no. 15 was received from Jeffery.

(1940) 3 All E.R. 60 at 71.

(1884) 9 App. Cas. 434, per Lord Selbourne.

Ibid.

(1982) 149 C.L.R. 620.

Per Gibbs C.J. in Ibid. at 625–6.

Per Deane and Dawson J.J. in Laurinda Pty Ltd v Capalaba Park Shopping Centre Pty Ltd (1988) 166 C.L.R. 623 at 658.

Per Lord Mansfield in Boone v. Eyre (1777) 1 H.Bl. 273n; see also D.W. Greig & J.L.R. Davis The Law of Contract (1987) 1201-3.

See Luna Park (NSW) Ltd v. Tramways Advertising Pty Ltd (1938) 61 C.L.R. 286 and Federal Commerce and Navigation v. Molena Alpha Inc. [1979] A.C. 757; see also Paterson, Robertson & Heffey in the Principles of Contract Law (2nd ed., 2005) at 371.

Ibid. As examples of cases involving parties attempting to terminate a contract where no such right exists, see Petrie v. Dwyer (1954) 91 C.L.R. 99; and Ogle v. Comboyuro Investments Pty Ltd (1976) 136 C.L.R. 444.

[1964] 2 Q.B. 699 at 734; also cited in DTR Nominees Pty Ltd v Mona Homes Pty Ltd (1978) 138 C.L.R.423 at 432.

See DTR Nominees Pty Ltd v Mona Homes Pty Ltd (1978) 138 C.L.R.423; see also Paterson, Robertson & Heffey in the Principles of Contract Law (2nd ed., 2005) at 371-2.

See for example DTR Nominees Pty Ltd v Mona Homes Pty Ltd (1978) 138 C.L.R. 423 at 431-3.

Ibid.

(1978) 138 CLR 423 at 431.

[1996] 1 W.L.R. 270 at 276-7.

(1978) 138 C.L.R. 423.

See McDonald v Dennys Lascelles Ltd (1933) 48 C.L.R. 457 at 476-477, per Dixon C.J.

Foran v Wight [1989] 168 CLR 385, 408; Shevill v Builders Licensing Board [1982] 149 CLR 620, 625-6; Laurinda Pty Ltd v Capalaba Park Shopping Centre Pty Ltd [1989] 166 CLR 623, 634.

See also DTR Nominees Pty Ltd v Mona Homes Pty Ltd [1978] 138 CLR 423, 431.

There was evidence that the first defendant later settled third party proceedings against the solicitor.

(1906) 4 CLR 347.

The tables were contained in the final address materials  “accompanying folders of materials provided by the defendants in support of their claim”.

See Waltons Stores (Interstate) Ltd v. Maher (1988) 164 C.L.R. 387, 413.

Amended reply and defence to counterclaim.

Certain subcontractors were identified: Custom Chassis, Iser Kitchens, Premium Shower Screens.

Renard Constructions (ME) Pty Ltd v Minister for Public Works (1992) 26 NSWLR 234, 277; Pavey & 	Matthews Pty Ltd v Paul (1986) 162 C.L.R. 221, 236, 256, 263; Brenner v First Artists’ Management Pty Ltd 	(1993) 2 VR 221, 256.

See also Appleby v Myers (1867) LR 2 CP 651, 659; Lodder v Slowey [1904] AC 442, 453.

For example NSW and Queensland: see Renard Constructions (ME) Pty Ltd v Minister for Public Works (1992) 26 NSWLR 234; Iezzi Constructions Pty Ltd v Watkins Pacific (Qld) Pty Ltd [1995] 2 Qd R 350.

(1987) 162 CLR 221.

[2004] NSWCA 181 (Unreported, Giles and Tobias JJA and Cripps AJA) [159].

See Renard Constructions (ME) Pty Ltd v Minister for Public Works (1992) 26 NSWLR 234; Iezzi 	Constructions Pty Ltd v Watkins Pacific (Qld) Pty Ltd [1995] 2 Qd R 350.  See also GEC Marconi Systems 	Pty Limited v BHP Information Technology Pty Limited (2003) 128 FCR 1, [646] (Finn J).

See Baltic Shipping Co v Dillon (1993) 176 CLR 344.

See, eg, Keith Mason and J W Carter, Restitution Law in Australia (1995) 563-6, 577-581.

(1987) 162 CLR 221.

Ibid 256.

[1999] NSWCA 140 (Unreported, Mason P, Priestley and Handley JJA, 16 July 1999) [54], as cited by Finn J in GEC Marconi Systems Pty Limited v BHP Information Technology Pty Limited (2003) 128 FCR 1, [655].

(1991) 174 CLR 64, 85.

[1993] 2 VR 221.

See Jennings Constructions Ltd  v QH & M Birt Pty Ltd , unreported judgment of the Supreme Court of  	NSW, 16 October 1988; The Minister for Public Works v. Renard Constructions (ME) Pty Ltd, Ibid.

See Jennings Constructions Ltd, Ibid; Renard Constructions, Ibid; also, Iezzi Constructions, Ibid.

(2002) 6 VR 1.

[1945] VLR 45.

Unreported judgment of Brownie J of the Supreme Court of New South Wales, 15 February 1989.

See Cremean, DJ, Brooking on Building Contracts, (3rd ed.) (1995), p.87.

Paragraph 5.

(1946) 72 CLR 386, 394.

Unreported judgment of Smith J of the Supreme Court of Victoria, 22 April 1994.

(1933) 48 CLR 457,476-477.

(1936) 54 CLR 361, 379.

Pavey & Matthews Pty Ltd v Paul (1987) 162 CLR 221.

See Tivendale’s reply statement on quantum meruit deductions.

See Phoenix Court Pty Ltd v Melbourne Central Pty Ltd (1997) ATPR 46-179.

“Delay or Disruption Costs”.

“Variations”.

[2004] VSCA 159. (Unreported, Callaway and Buchanan JJA and Hansen AJA, 8 September 2004)

Ibid. at [94].

Ibid. at [95].

Ibid. at [102-103].

Ibid. at [104]

Ibid. at [110].

Ibid. at [78]

Lubenham Fidelities and Investments Co. Ltd. v South Pebrokeshire DC (1986) 33 BLR 39; Cove Corp Construction Pty Ltd v Indigo Projects Pty Ltd [2002] QSC 322; Algons Engineering Pty Ltd v Abigroup Contractors, unreported judgment of the Supreme Court of New South Wales, dated 1 August 1997; Zauner Construction Pty Ltd v No.2 Pitt Street Pty Ltd (2001) 17 BCL 357.

s.96(1) Victorian Civil and Administrative Tribunal Act 1998.

Sought by the plaintiff.

Sought by the defendants.

Sought by the defendants.

See Dorter & Sharkey, Building and Construction Contracts in Australia, (2nd ed.) , (1990), Chapter 14.416.

On 31 October 2003 requiring the filing of documents.

Cf. Chamberlain v DCT (1991) 28 FCR 21; Logwon Pty Ltd v Warringah Shire Council (1993) 33 NSWLR 13 at 30.